Independent Evaluation of the Fleming Fund Grants Programme

Volume II: Summative Report Annexes

Date: 24 April 2024

Authors: Tim Shorten, Giada Tu Thanh, Ankur Gupta-Wright, Jennifer Armitage, Abbas Syed, Archie Drake, Julie-Anne Darsley, Juliette Gautron & Paul Balogun

Submitted by Itad

List of figures, boxes and tables	v

List of acronyms	vii

Introduction	10

Annex 1: Terms of Reference	11

Annex 2: Evaluation Matrix	38

Annex 3: Overview of Evaluation	40

1.1	Objectives of the evaluation	40

1.2	Methodology	42

1.3	Main analytical methods	46

1.3.1	Contribution analysis	46

1.3.2	Alignment and coherence	51

1.3.3	National policy agenda analysis	52

1.3.4	Examples of use of data at the facility level	54

1.3.5	Value for money	55

1.3.6	Sustainability analysis	57

1.3.7	Cross-case synthesis	59

Annex 4: Data collection and analysis	62

Country visits	62

Country document review	62

Key informant interviews	64

Site visits	65

Global and Regional Grants analysis	66

Global and Regional Grants Document review	66

Global, Regional and Direct Grants KIIs	67

Ensuring quality in the evaluation	67

Annex 5: Mapping of evaluation questions to report sections	70

Annex 6: Value for money	71

Background	71

Findings	71

DHSC and MA’s approach to VfM	71

Have DHSC and MA managed for VfM at country level?	72

VfM Measures	75

Annex 7: One Health	85

Background	85

Evaluation question	86

Starting position: What is One Health	86

Evolving approach to One Health and its evaluation	87

Evaluation questions and approach	88

Key findings	89

Situation in 2018	89

Progress made across 16 countries	89

Variation and possible explanations	92

Headline messages	94

Annex 8: Quality and quantity	96

Changes in quantity of AMR data	96

Situation in 2018	96

Data on changes in quantity of AMR at national level	98

Data on changes in quantity of AMR at international level	102

Performance compared to the MA implementation plan targets	106

Changes in quality of AMR data	107

Annex 9: Data use	111

Observed data use at the national level	111

National policy agenda analysis (Kingdon Multiple Streams Analysis MSA)	114

Examples of use at facility level	119

Annex 10: Sustainability	122

Annex 11: Departures from the ToRs	125

Annex 12: Ethics and safeguarding	128

Annex 13: Risks, Challenges and Mitigating Strategies	135

Annex 14: Evaluation Management and Roles and Responsibilities	149

Annex 15: Country Categorisation	156

Annex 16: Participation of Stakeholders	158

Annex 17: Use and Influence Plan	160

Purpose of use and influence plan	160

Target audience and key stakeholders	160

Planned activity	161

The Plan	164

Dependencies:	165

How we will monitor and report on learning and dissemination:	165

Proposed Indicators For Learning And Dissemination Activities	166

Annex 18: Fleming Fund programme theory of change	168

Annex 19: Bibliography	169

Annex 20: List of consultees	172

Global KIIs	172

Host Institutions KIIs	172

Regional Grants KIIs	173

Bangladesh	174

Bhutan		175

Ghana		176

Indonesia	178

Kenya		179

Laos		181

Nepal		183

Nigeria		184

Pakistan	185

Pilot		185

Country Visit 2022	186

Senegal		187

Sierra Leone	189

Tanzania	190

Timor-Leste	192

Uganda		193

Vietnam	194

Zambia		195

Pilot		195

Country Visit 2022	196

Annex 21: Line of sight between findings, conclusions and recommendations	198

Annex 22: Contribution Analysis visual summaries	204

C1a Changes in quantity of HH AMR data	204

C1b Changes in quality of HH AMR data	205

C2a Changes in quantity of AH AMR data	206

C2b Changes in quality of AH AMR data	207

C3 Changes in data sharing with relevant committees	208

C4 Changes in data sharing with GLASS	209

C5 Changes in data sharing with WOAH	210

Annex 23: Examples of Itad support to adaptations within phase 1 of the Fleming Fund	211

Annex 24: Alignment and coherence of Fleming Fund interventions	213

Annex 25: Mapping of grants by sample country	220

Annex 26: Data Collection Tools: KII guides	221

KII Guide for AH AMR FP	221

KII Guide for AH Fellows	228

KII Guide for AH NRL	234

KII Guide for AH Site	240

KII Guide for AMRCC	246

KII Guide for CG teams	252

KII Guide for FAO	264

KII Guide for GLASS FP	268

KII Guide for HH AMR FP	275

KII Guide for HH Fellows	281

KII Guide for HH NRL	287

KII Guide for HH Site	292

KII Guide for HI teams	296

KII Guide for MA Regional teams	302

KII Guide for OIE FP	305

KII Guide for Other decision makes	312

KII Guide for other DPs	318

KII Guide for Policy Fellows	321

KII Guide for WHO	327

List of figures

Figure 1 Organogram of Fleming Fund workstreams	41

Figure 2 Six EQs or ‘agreed measures of success’	42

Figure 3 Overview of evaluation framework	45

Figure 4 Six steps of contribution analysis	48

Figure 5 Fleming Fund country-level ToC for contribution analysis	50

Figure 6 Six steps of necessary and sufficient analysis	52

Figure 7 An indicative example of cross-case synthesis	60

Figure 8 Fleming Fund Country Grants Expenditure September 2019 to June 2022 by budget category (Source: Management Agent)	83

Figure 9 Fleming Fund Country Grants Expenditure September 2019 to June 2022 by investment area (Source: Management Agent)	83

Figure 10 One Health partnerships in Fleming Fund- Implementation Plan (June 2017)	86

Figure 11 MA Position paper on assessing One Health Implementation (September 2019)	87

Figure 12 Other ways of characterising One Health partnerships (Itad literature review)	88

Figure 13 Characterising One Health partnerships, by strength of integration (Itad literature review)	88

Figure 14 Approach to evaluating One Health across different country visits	89

Figure 15 Functional status of One Health partnerships (expectations and findings)	90

Figure 16 Nature of One Health partnerships, Country Visit 2 and Country Visit 3	90

Figure 17 Strength of One Health partnerships, Country Visit 2 and Country Visit 3	91

Figure 18 GLASS pathogens tested in national systems	100

Figure 19 Number of countries reporting	104

Figure 20 Percentage of countries reporting more data	104

Figure 21 Number of Fleming Fund supported HH sites showing progress through the LSHTM roadmap	110

Figure 22 Number of Fleming Fund supported AH sites showing progress through the LSHTM roadmap	110

Figure 23 Diagram of the Multiple Streams Approach	116

Figure 24 Local/facility level Examples of Use across Fleming Fund countries evaluated (EoU)	120

Figure 25 Human Health Examples of Use	120

Figure 26 Governance and internal management structure for the Evaluation Supplier	149

Figure 27 Country Categorisation	156

Figure 28 Hierarchy of learning uptake indicators	166

Figure 29 Fleming Fund ToC diagram	168

List of boxes

Box 1 Key findings on Efficiency	79

Box 2 Key messages from the Itad literature review [here]	92

Box 3 Observations from countries – Two different ways in which One Health has been operationalised	94

Box 4 Kingdon's Multiple Streams Analysis	115

Box 5 COVID-19 and national AMR agendas, 2020-22	118

List of tables

Table 1 The Evaluation Matrix	38

Table 2 Summary of sampling strategies	43

Table 3 Possible outcomes that may be prioritised by the countries	53

Table 4 Themes for assessment of country and regional grants	56

Table 5 Expected and planned pillars of sustainability	58

Table 6 Rubrics applied to generate RAG ratings for each key sustainability pillar	58

Table 7 Documents reviewed per country	62

Table 8 Number of documents reviewed by theme	63

Table 9 Key Informant Categories and their estimated numbers	64

Table 10 Criteria for selecting sites to be visited	66

Table 11 Direct and regional grants reviewed	66

Table 12 Number of documents reviewed per document type	67

Table 13 Framework for ensuring quality in the evaluation	68

Table 14 Example of overbudgeting in RG FF10/11	72

Table 15 VfM Measures of Economy achieved across country grants	75

Table 16 VfM Measures of Economy achieved across regional grants	75

Table 17 Rubric for VfM Measures of Economy	76

Table 18 Budgeted and Actual Overhead costs in CGs	77

Table 19 VfM measures of efficiency	77

Table 20 VfM Measures of Efficiency achieved across regional grants	78

Table 21 Rubric for VfM Measures of Efficiency	78

Table 22 VfM measures of effectiveness	79

Table 23 Country grant rating based on the change from baseline and contribution analysis rubric scoring matrix	81

Table 24 Mapping of investment areas to contribution analysis drivers	82

Table 25 NAPs in place in 2018	96

Table 26 Availability of AMR data in 2018	97

Table 27 Human Health AMR data from country visits	99

Table 28 Data for AH AMR collected during country visits and from document review	100

Table 29 GLASS Data	102

Table 30 Country data on AMU reporting to WOAH (from KIIs)	105

Table 31 MA implementation plan targets (v2.5)	106

Table 32 Mapping duration of support with available evidence on whether data is being generated	106

Table 33 Quality of AMR data - data collection template	107

Table 34 Changes in quality of AMR data (Human Health)	108

Table 35 Changes in quality of AMR data (Animal Health)	109

Table 36 Examples of use of relevant data for decision making	111

Table 37 Examples where use in decision making looks promising but is not confirmed	112

Table 38 Data sharing not yet connected with action/current systematic collation and analysis leading towards data use	113

Table 39 Progress towards data sharing/developments increasing potential for future data use	113

Table 40 No substantial progress towards data sharing/unclear prospects for future data use	114

Table 41 Notes on changes in analysis, 2020-2022 (reflections on Fleming Fund contribution in wider policy context)	116

Table 42 Sustainability Data – Animal Health	122

Table 43 Sustainability Data – Human Health	123

Table 44 Sustainability Data Rubric	124

Table 45 Risks and mitigating strategies	135

Table 46 Evaluation team members	151

Table 47 Country Categorisation A-D	157

Table 48 Participation of stakeholders	158

Table 49 Proposed indicators for L&D Activities	167

List of acronyms

AH	Animal Health

AMC	Antimicrobial Consumption

AMR	Antimicrobial Resistance

AMRCC	Antimicrobial Resistance Coordinating Committee

AMS	Antimicrobial Stewardship

AMU	Antimicrobial Use

ASLM	African Society for Laboratory Medicine

ASM	American Society for Microbiology

AST	Antimicrobial Susceptibility Test

BBLK	Balai Besar Laboratorium Kesehatan

BL	Baseline

CAPTURA	Capturing Data on AMR Patterns and Trends in Use in Regions of Asia

CCM	Country Coordination Meeting

CDC	Centers for Disease Control and Prevention

CG	Country Grant/ee

CoI	Conflict of Interest

CVL	Central Veterinary Laboratory

CVRI	Central Veterinary Research Institute (Zambia)

CwPAMS	Commonwealth Pharmacists Association

DAC	Development Assistance Committee

DFID	Department for International Development

DGDA	Directorate General of Drug Administration

DHSC	Department of Health and Social Care

DLS	Department of Livestock Services

DP	Delivery Partner

DVS	Directorate of Veterinary Services

EAG	Expert Advisory Group

ECTAD	Emergency Centre for Transboundary Animal Diseases

EML	List of Essential Medicines

EoU	Examples of Use

EQ	Evaluation Question

EQA	External Quality Assurance

EQuALS	Evaluation QA and Learning Service

ES	Evaluation Supplier

EUCAST	European Committee on Antimicrobial Susceptibility Testing

FAO	Food and Agriculture Organization

FCDO	Foreign, Commonwealth & Development Office

GAP	Global Action Plan

GARP	Global Antibiotic Resistance Partnership

GHS	Global Health Security

GLASS	Global Antimicrobial Resistance Surveillance System

GRAM	Global Research on Antimicrobial Resistance

HI	Host Institution

HH	Human Health

HMG	His Majesty’s Government

HMT	His Majesty's Treasury

IDDS	Infectious Diseases Detection and Surveillance

IEDCR	Institute of Epidemiology, Disease Control and Research

IPA	International Procurement Agent

IPC	Infection Prevention & Control

IVI	International Vaccine Institute

KEMRI	Kenya Medical Research Institute

KI	Key Informant

KII	Key Informant Interview

L&D	Learning and Dissemination

LMICs	Low-and Middle-Income Countries

LSHTM	The London School of Hygiene & Tropical Medicine

LY	Latest Year

M&E	Monitoring and Evaluation

MA	Managing Agent (Mott MacDonald)

MAAP	Mapping Antimicrobial Resistance and Antimicrobial Use Partnership

MoHS	Ministry of Health and Sanitation

MOAF	Ministry of Agriculture and Forests

MoLF	Ministry of Agriculture Livestock Fisheries and Cooperatives

MONFSR	Ministry of National Food Security & Research

MSA	Multiple Streams Analysis

MSP	Multisector Partnerships

MTaPs	The Medicines, Technologies, and Pharmaceutical Services Programme

NAO	National Audit Office

NAP	National Action Plan

NCAH	National Centre for Animal Health

NCDC	Nigeria Centre for Disease Control

NE	No Evidence

NIH	National Institute of Health

NRL	National Reference Laboratory

NVL	National Veterinary Laboratories

OECD	Organisation for Economic Co-operation

PE	Political Economy

PHSG	Public Health Surveillance Group

PPS	Point Prevalence Survey

QA	Quality Assurance

QR	Quarterly Report

RA	Research Analyst

RADAAR	Regional Antimicrobial resistance Data Analysis for Advocacy, Response and Policy

RAG	Red, Amber, Green

RC	Regional Coordinator

RCDC	Royal Center for Disease Control

RFP	Request for Proposal

RG	Regional Grant

RGOB	Royal Government of Bhutan

RT	Regional Teams

SMT	Senior Management Team

SOP	Standard Operating Procedure

STG	Standard Treatment Guidelines

TAG	Technical Advisory Group

ToC	Theory of Change

ToR	Terms of Reference

TrACSS	Global Database for Tracking AMR Country Self-Assessment Survey

TWG	Technical Working Group

UN	United Nations

UNOPS	United Nations Office for Project Services

USAID	United States Agency for International Development

VfM	Value for Money

WGS	Whole Genome Sequencing

WHO	World Health Organization

WOAH	World Organisation for Animal Health

ZNPHI	Zambia National Public Health Institute

Introduction

This document forms part of the Summative Report of the Evaluation of The Fleming Fund Grants Programme. We have split the report into two distinct sections to aid readability:

Volume I: 	The main report is deliberately kept short and focuses on the evaluation findings and recommendations.

Volume II: 	The Annexes included in Volume II provide further detail on how the evaluation was conducted.

The following text (Volume II) provides the detail on how the evaluation was conducted and should be read in conjunction with Volume I.

Annex 1: Terms of reference

Executive Summary

This section provides information on the Fleming Fund, and the independent Evaluation Supplier role (the latter being the subject of this requirement).

1. Introduction

  - The Department of Health (DHSC) has launched the Fleming Fund, a £265 million One Health programme to support low and middle income countries (LMICs) in tackling antimicrobial resistance (AMR).

  - To help deliver the Fleming Fund, DHSC is intending to contract a supplier to deliver an independent evaluation of the Fleming Fund country and regional level projects.

  - The Evaluation Supplier will evaluate how far the outputs of the portfolio of country and regional grants will contribute to the outcomes and impact defined within the agreed Fleming Fund Theory of Change (see Annex B). It is understood that this analysis would be indicative, due to the amount of external variables which could affect the desired Fleming Fund impact as stated.

  - The formative aspect of the evaluation (see section 5.10 for detailed information) will indicatively answer the evaluation questions agreed during the inception phase, and produce recommendations to guide the portfolio of country and regional grants in how their outputs can best achieve and contribute to the outcomes and impact of the Fleming Fund. The formative report will be a key opportunity for any course correction suggestions.

  - The have contributed, or will contribute, to the outcomes and impact of the overarching Fleming summative aspect of the evaluation (see section 5.10 for detailed information) will answer the evaluation questions agreed during the inception phase and evaluate how far the outputs of the portfolio of country and regional grants Fund.

  - This document outlines the shape of the Fleming Fund Programme, initial work already underway and the specification for an Evaluation Supplier.

  - AMR is a global problem that needs concerted action at both national and global levels using a One Health approach that spans work across the human, veterinary, environment and development sectors. The UK is at the forefront of action to address the threat of AMR.

  - Drug-resistant infections could kill an extra 10 million people across the world every year by 2050 if they are not tackled. By this date they could also cost the world around $100 trillion in lost output: more than the size of the current world economy1. See Annex A for detailed background information on the challenge of AMR in LMICs.

  - Ongoing systematic collection, analysis, and interpretation of health data is essential to the planning, implementation and evaluation of public health practice, closely integrated with the dissemination of these data to those who need to know and linked to prevention and control.2

  - Both the Prime Minister and Chief Medical Officer are clear that tackling AMR at home and abroad is a key priority and that the UK will help lead a global response.

  - The Fleming Fund will aim to improve laboratory capacity and diagnosis as well as data and surveillance of AMR in LMICs.

  - The Fleming Fund itself is funded through Official Development Assistance (ODA).3 Evaluating the impact and lessons of aid programmes is a crucial part of ODA funded work. A high quality evaluation helps ensure funding is being spent effectively to meet the aim of the Fund.

- Programme Description and Features

Programme aims, activities and approach

  - The aim of the Fleming Fund is to improve laboratory capacity and diagnosis as well as data and surveillance of AMR in LMICs through a One Health approach: building capacity to collect drug resistance data; enabling the sharing of drug resistance data locally, regionally and internationally; collating data on AMR; and encouraging the application of these data to promote the rational use of antimicrobials.

  - The Fund will do this by:

  - Building laboratory capacity for diagnosis.

  - Collecting drug resistance data.

  - Enabling the sharing of drug resistance data locally, regionally and internationally.

  - Collating and analysing data on the sale and use of antimicrobial medicines, particularly antibiotics.

  - Advocating the application of these data to promote the rational use of antimicrobials for human health, animal health and agriculture.

  - Shaping a sustainable system for AMR surveillance and data sharing.

  - 2.3	For details of initial scoping activities, technical support and guidance, and Fleming Fund Core Principles, see Annex G.

Country and regional focus

  - Country focus: The Fund will have a focus principally on countries which are encompassed by a high level set of priority principles set out by DHSC such as ODA eligibility, countries in Sub-Saharan Africa, Southern and South Eastern Asia, and countries with existing UK diplomatic relations. These high level principles will be the first maker in country selection and are detailed in Annex C. Within this selection the Management Agent - the identification of which is the subject of a separate procurement exercise - will be expected to work with DHSC to further shortlist countries through a series of country assessments to understand where investments will be most effectively targeted. Fleming Fund country investments will benefit from being implemented alongside other DFID programming where relevant, but projects will not be limited to DFID priority countries.

  - Regional focus: The Management Agent will be expected to run a call for regional grants to support the development of networks and data sharing. However, the makeup of a regional network can remain flexible to reflect geographical proximity, a specific collection of countries with similar priorities or regional partnerships.

  - Cross-border thematic focus: The Fleming Fund will target country and regional grants which can demonstrate a clear path to impact through a One Health approach4; this may include a One Health commitment from governments as part of AMR National Action Plans.

Technical focus

  - The Fleming Fund will focus on detecting and reporting on pathogenic bacteria-antibacterial drug combinations in line with those that were identified as of international public health concern by WHO in the Antimicrobial Resistance Global Report on Surveillance 20145, subject to adaptation to suit local priorities and infectious disease prevalence (including zoonotic infections). DHSC expects that programmes will include some of the following pathogenic bacteria-antibacterial drug combinations:

- Escherichia coli vs. 3rd generation cephalosporins and fluoroquinolones.

- Klebsiella pneumoniae vs. 3rd generation cephalosporins and carbapenems.

- Staphylococcus aureus vs. methicillin.

- Streptococcus pneumoniae vs penicillin.

- Salmonella species vs. fluoroquinolones.

- Shigella species vs. fluoroquinolones.

- Neisseria gonorrhoeae vs. 3rd generation cephalosporins.

  - Specific countries and regions may have identified priorities within this list dependent on their country burden of disease and reported resistance, or additional priorities such as tuberculosis. The aim of the Fund, aligned with the Global Health Security Agenda (GHSA) AMR target, is to encourage each country receiving Fleming funding to begin improving laboratory capacity for, and surveillance of, a minimum of three of the above pathogenic bacteria antibacterial drug combinations as a starting point, with the ambition of improving capacity to test for all. However, in consultation with country governments and national stakeholders, the Programme can support additional pathogens alongside those in the WHO list, if this is a national priority.

What the programme will not fund

  - Research: although it will be informed by research agendas, have close links with researchers and generate useful new knowledge on AMR, the prime objective of the Fund is not AMR research.

  - New product development: other funding mechanisms and relationships will be required to do this.

  - Support to non-ODA eligible countries.

  - Financial disbursements directly to governments.

- Programme Activities

  - With initial projects underway (see Annex G), DHSC is commissioning a set of Fleming Fund projects which will be sustained through the five year funding cycle. The following represents the shape of the programme as a whole over this five year period with detail on each work stream.

  - The Fleming Fund Programme will be managed by DHSC and will be made up of five interdependent workstreams as shown below. DHSC is separately tendering to procure a Management Agent who will deliver the country and regional projects and the Fleming Fellows (workstreams 1 and 2), although alignment is expected between all workstreams in the Programme. The current tender is to procure an Evaluation Supplier to deliver an independent evaluation of the country and regional projects.

  - Work stream 1 and 2 and 5 will be structured into two phases:

- phase 1: The eight month inception phase to design the programme portfolio of country and regional grants, Fleming Fellows and the independent evaluation alongside DHSC.

- phase 2: The implementation phase to set up and manage the portfolio of country and regional grants, Fleming Fellows and the delivery of the independent evaluation.

Figure 1. Organogram of Fleming Fund workstreams

  - Work stream 1 – Portfolio of country and regional projects (Management Agent): This work stream is the focal point of the Fleming Fund and will be delivered by the selected Management Agent supplier.

  - The focus of country and regional grants will be to improve laboratory capacity for diagnosis as well as surveillance on AMR, and surveillance of the use of antimicrobial medicines. It is recognised that any improvements to laboratory infrastructure and capacity will not happen in isolation, but will rather need to complement the sustaining ecosystem around the laboratory including: external quality assurance; effective collection of samples; flow of samples to the laboratory; trained staff to undertake sample testing; and efficient mechanisms to share data.

  - Country One Health grants during implementation phase may include but are not limited to:

- Equipping and refurbishing laboratories so that they are able to reliably undertake bacterial diagnosis and antimicrobial sensitivity testing.

- Supporting biosafety and biosecurity improvements within and around the laboratory and sample sharing context.

- Training staff on diagnosis and antimicrobial sensitivity testing, using laboratory equipment and undertaking AMR surveillance.

- Running hardware and software to support epidemiological investigation and improved surveillance of resistance trends.

- Developing surveillance systems that are capable of delivering real time AMR surveillance that can be shared nationally, regionally and globally.

- Undertaking point prevalence studies to gain a snapshot of the AMR burden in specific areas.

- Collating and analysing data on the sale and use of antimicrobial medicines, particularly antibiotics at a country level.

- Undertaking policy and advocacy work with national governments, using AMR data and analysis collected to make the case for evidence-based public health interventions.

- Improving national capacity to regularly collate and upload data to an international data sharing platform represented by GLASS6, and other data sharing platforms such as the Institute of Health Metrics Evaluation (IHME) GBD7

  - National grants must be effectively embedded in national public health systems, acceptable under principles for support set out by the relevant Ministry of Health in the chosen location and integrated as part of a sustainable plan to improve laboratory capacity for bacterial diagnosis, data collection and surveillance on AMR long term. Grants should align with wider national work on achieving the International Health Regulation Core Capacities8 and make a measurable contribution to this progress.

  - Regional One Health grants during implementation may include but are not limited to:

- Enhancing the capability of existing regional surveillance networks.

- Training and development on laboratory testing, AMR surveillance at a regional level and undertaking regional quality assurance of surveillance data.

- Delivering external quality assurance services.

- Improving regional capacity to regularly collate and upload data to an international data sharing platform represented by GLASS, and other data sharing platforms such as the GBD.

- Collating and analysing data on the sale and use of antimicrobial medicines, particularly antibiotics at a regional level.

- Convening regional meetings and conferences to share skills and learning on improving laboratory capacity, data collection and surveillance of AMR in low resource settings.

- Developing Massive Open Online Courses (MOOCs) to disseminate information on AMR, infection prevention control, surveillance protocols and other relevant subject areas required to improve national, regional and international understanding.

  - Country eligibility for receipt of grant funding will be:

- An ODA eligible country with a particular focus on the low or lower-middle income group9.

- Evidence of a robust National Action Plan or considerable effort towards developing this plan

- Evidence of recognition and commitment to Fleming Fund projects by the national government. This may be a memorandum of understanding or letter of intent with the relevant Ministry of Health with details of any national engagement or resources that could be used to support the projects.

The Fleming Fund will not expect explicit country financial or in-kind buy-in to receive Fleming Fund investments but evidence of country ownership and commitment to support the Fund’s activities will be a requirement.

  - Between £200 and £235 million (excluding VAT) will be utilised through the selected Management Agent, profiled to rise incrementally over the five year period to reach the total budget. There may also be a possibility of absorbing additional budget into the Fund from other donors to further increase the capacity of the programme.

  - Funding by region

DHSC will not prescribe the exact split of funding across the two key regions, but will rather look to country and regional capability assessments carried out by the Management Agent during the design of the implementation phase to dictate the number of countries selected between the two regions and the absorptive capacity for funding of each of these countries to make up the total regional budget available. At a minimum, it is expected that a single region would receive 30% of the total budget for country and regional projects.

  - Funding by country

DHSC will not prescribe how many grants can be agreed in each country, but where multiple grants are agreed in a country there is an expectation that they will link together or align, and this may need to be supported through the Management Agent coordination function. During the design of the implementation phase, DHSC will decide with the Management Agent whether the amount of funding per country will be allocated in advance of a call for funding, and the number of grants will depend on the amount of projects that can be funded under this budget; or rather if the budget allocated per country will depend on the total budget of the accepted grants.

  - During implementation, the Management Agent is expected to manage the portfolio of country and regional grants.

  - The Fleming Fund will initially run for a five year period from 2016 to 2017. Individual grants under the Fleming Fund would normally be expected to run for between two to three and a half years. The independent evaluation carried out by the Evaluation Supplier, which is the subject of this procurement, will evaluate how far the outputs of the portfolio of country and regional grants will contribute, or have contributed, to the outcomes and impact defined within the agreed Fleming Fund Theory of Change (see Annex B), while suggesting areas for course correction and improvement throughout the programme lifecycle. This will help to inform any decision by the UK government to extend funding beyond the initial five year period. Additional funding from other partners or host governments may be considered.

  - Work Stream 2 – Fleming Fellows (Management Agent): The Fleming Fellowship scheme will be a network of practitioners from different disciplines and sectors such as laboratory technicians, clinicians, policymakers, community leaders, hospital managers and more. The network will focus on professional development facilitating the cross-pollination of ideas and experience, peer-to-peer learning, and finding creative solutions as part of a multidisciplinary network to tackle AMR in LMICs. The scheme would facilitate the kind of cross-pollination of experience and ideas that cannot be delivered on a course or through academic programmes. Our offer to Fellows can include:

- Mentoring: Fleming Fellows will be allocated a regional mentor who is an expert in their field and could offer support and advice for tackling AMR in their specific context.

- Secondments: With agreement from their home institutions, Fellows could be offered the opportunity to spend three months on placement being given formal training on their subject matter e.g. for laboratory technicians spending time at a high quality laboratory in their region to gain experience and bringing back learning to their host country of standards and processes used.

- Training: Fellows will be offered written and verbal communication training to present their findings and support them as key influencers in their fields.

- Support for travel: Fellows would be alerted to learning opportunities in their region around infectious disease and drug-resistant infections and given travel and subsistence funding to make the most of these opportunities.

- Networks: Fellows will be linked into a network of other Fellows and Friends of the Fleming Fund working on drug-resistance and brought together annually to share their learning and experiences at a regional conference.

- Collaborative projects: Fellows would commit a set period of time within their one or two year fellowship to join together with other Fellows to undertake scoping work, link with in-country Fleming Fund projects, travel to regional or other country projects, share experiences and bring local challenges to the network to find creative solutions as a group.

- Other initiatives: Small amounts of funding would be available to support Fleming Fellows projects or initiatives/solutions devised as a group.

The Management Agent will be expected to design this Fellowship scheme during inception phase and launch during implementation. Fellows may choose to bid for country funding or may be identified out of developed relationships with country grantees. Conflict of interest must be monitored by the Management Agent closely, but Fellows will be identified for their unique influence on country AMR laboratory and surveillance systems, which could be an asset to the portfolio of country and regional grants. Fellowships will be piloted initially in a small number of countries.

  - To support the portfolio of country and regional projects, additional activities will be commissioned through the Fleming Fund. These three workstreams are detailed below.

  - Work Stream 3 – Grants to multilateral organisations (DHSC): An essential part of delivering the ambition of the Fleming Fund is to ensure there is support for international AMR surveillance and alignment of activities at the international level. WHO, FAO and OIE have a central role in providing global leadership not only within each of their sectors, but also through their tripartite collaboration in promoting the One Health approach. Going forward, the expectation is that the three organisations continue to work together to drive forward the international work on data and surveillance and directly linked to this, for them to be supported in providing additional support to LMICs in developing, agreeing and implementing National Action Plans.

  - It is intended that grants be agreed for the first three years of the Fleming Fund aimed predominantly at supporting LMIC development. The Management Agent will be provided with the outputs of these activities, planned activities and key contacts to ensure alignment of international and country/regional level activities. The management and disbursement of funds to these organisations will remain with DHSC.

  - Work Stream 4 – Surveillance protocol and platform (DHSC): DHSC is commissioning the writing of a set of tiered protocols for initiating AMR surveillance in low resource settings. This will build on the recently published WHO manual for early implementation of GLASS.

  - The aim of the work stream is to develop of a set of standard protocols for improving laboratory capacity and initiating AMR surveillance that:

- Are suitable for use by low income countries, recognising the context of different health systems.

- Are based on an assessment of available evidence and review of established protocols in comparable resource settings.

- Provide a basis for early collection and analysis of data on AMR that will help countries to rapidly assess the impact of AMR and participate in global and regional surveillance (GLASS).

- Take into account the need for epidemiological and statistical validity and quality assurance, so that the data can be used, shared and combined (multicentre and multinational analysis) to provide evidence of prevalence of AMR and effectiveness of interventions with confidence.

- Are structured as a set of tiered options so that countries can select the types of surveillance, samples and scale of operation to suit their circumstances, with the ability to expand and broaden the scope of surveillance with time.

- Can be used as a basis for supporting the development of National Action Plans, and assessing applications to the Fleming Fund.

- Provide a roadmap for how to improve laboratory capacity, data collection and surveillance for AMR with an effective One Health approach.

  - It is anticipated that the above set of protocols will be completed by the time the Management Agent and Evaluation Supplier have been selected.

  - The protocols will then be tested with experts and will be available for piloting by the Management Agent supplier during the inception phase. Fleming Fund country and regional projects will need to demonstrate how they contribute to and improve the use of these surveillance protocols.

  - The Fleming Fund will require all grants to share data on an international platform represented by GLASS and will provide financial support to ensure these platforms are fit for purpose.

  - In addition to sharing data through GLASS, the Fleming Fund will expect partners to share data on other international platforms such as the GBD.

  - Work stream 5 – Independent Evaluation (Delivered by the independent Evaluation Supplier): A core principle of the Fleming Fund is a robust and independent evaluation, which is being commissioned to run alongside and evaluate the portfolio of country and regional projects. This evaluation will be carried out by an Evaluation Supplier procured by DHSC and is the subject of this procurement exercise. The selected Evaluation Supplier will be expected to work alongside the Management Agent to design a monitoring strategy that can feed information into the evaluation.

  - DHSC aims to award a contract to both the independent Evaluation Supplier and Fleming Fund Management Agent at around the same time, at which point both organisations will commence their inception phase expected to last eight months.

  - The Fleming Fund has been designed so that, in having the Evaluation Supplier and Management Agent working together closely during the inception phase, evaluation considerations are ‘embedded’ in the programmes across the project cycle. This means clear assessments of the evidence for what does or doesn’t work in the initial stages of programme design, analysis of baseline data and effective evaluation over the life of the programme and beyond. It is key, however, that the Evaluation Supplier retains independence in order to deliver their independent evaluation of the programme as delivered by the Management Agent to ensure a balanced, accurate and unbiased evaluation.

  - The Evaluation Supplier will evaluate how far the outputs of the portfolio of country and regional grants will contribute to the outcomes and impact defined within the agreed Fleming Fund Theory of Change (see Annex B). It is understood that this analysis would be indicative, due to the amount of external variables which could affect the desired Fleming Fund impact as stated.

  - The formative aspect of the evaluation will indicatively answer the evaluation questions agreed during the inception phase, and produce recommendations to guide the portfolio of country and regional grants in how their outputs can best achieve and contribute to the outcomes and impact of the Fleming Fund. The formative report will be a key opportunity for any course correction suggestions.

  - The summative aspect of the evaluation will answer the evaluation questions agreed during the inception phase and evaluate how far the outputs of the portfolio of country and regional grants have contributed, or will contribute, to the outcomes and impact of the overarching Fleming Fund.

  - The evaluation questions (see ‘Proposed Evaluation Questions’ at 5.4 below, and ‘Indicative Evaluation Sub-Questions’ at Annex D) will be used to evaluate the overall impact of the Fund at agreed intervals.

- Programme Approach and Governance

Programme approach

  - For details on Technical Support and Guidance, see Annex G.

Collaboration and partnership with Department of Health

  - The DHSC is dedicated to ensuring that a close and collaborative working relationship is developed with the Evaluation Supplier and Management Agent. A key focus of evaluating Evaluation Supplier and Management Agent bids will be to assess the strength of proposals for working with the DHSC in both the inception and implementation phases.

  - The DHSC has one dedicated Full-Time Equivalent (FTE) acting as lead for country and regional project delivery for the Fleming Fund, who will work closely with the selected Management Agent, and one dedicated FTE policy and programme adviser who will act as the point person dedicated to delivering the evaluation. This lead will be the main DHSC focal point for the selected Evaluation Supplier; however, additional support is available from an AMR expert consultant working with the department and further policy support within the Global Health Security Team.

  - Consultation time with the programme Senior Responsible Officer (SRO) and access to the Chief Medical Officer will be coordinated through the Fleming Fund country lead. There will be considerable scope for regular discussions, particularly while shaping and designing the portfolio of country and regional grants.

Governance

Red lines indicate accountability chains and blue lines indicate a working relationship.

  - Governance during inception phase - Figure 2: The inception stage of the programme assumes regular collaboration between the DHSC Fleming Fund Project Team, the Evaluation Supplier and the Management Agent, as well as other key grantees such as the WHO. The following represents the governance of the inception phase.

Figure2: Governance of the inception phase of the programme

A: During inception phase - proposals, decisions and approaches will be discussed and approved by this group of DHSC seniors, including the SRO for the Global Health Security portfolio.

B: The Fleming Fund is part of the DHSC portfolio of work on Global Health Security. This work is regularly reviewed and governed by a Global Health Security Programme Board chaired by the DHSC SRO for the funds. The Project Team will report progress on the Fleming Fund design into this group.

C: The Fleming Fund is part of the broader Ross Fund, which is a joint initiative between DHSC and DFID as announced in the 2015 government Spending Review. To ensure all activities across Whitehall are aligned and on track, a cross-Whitehall group will meet to review and discuss interdependencies between projects and give assurance to ministers that planned activities are on track.

D: The Technical Advisory Group will be a small group of multidisciplinary experts that DHSC, the Management Agent or the Evaluation Supplier are able to call on during either the inception or implementation phases to advise, input or quality assure elements of the wider Fleming Fund.

  - Governance during the implementation phase – Figure 3: The implementation phase of the programme will devolve much of the day-to-day management decisions to the Management Agent with approvals being taken and decisions reviewed where necessary by a Steering Committee. The Steering Committee will be a high-level group, including representatives from the key programme areas.

Figure 3: Governance of the implementation phase of the programme

E: When fully operational, the Fleming Fund portfolio of country and regional grants will be governed by a Steering Committee. Representation on this committee will include, but not be limited to, senior members of DHSC, DFID, the Management Agent and the Evaluation Supplier, and may also include independent experts. This group will likely meet to review and approve key documents including the funding call specification, proposed grantees, annual reports, results and recommendations from the independent evaluation. This group will have the opportunity to provide strategic challenge and will be charged with using their remit of challenge and approval to keep the programme working towards the desired impact in the most effective and efficient way. The terms of reference for this group will be defined between the Management Agent, the Evaluation Supplier and DHSC during the inception phase. Although day-to-day management for the Fund will be devolved to DHSC, the Management Agent and the Evaluation Supplier respectively, all elements of the Fund will be accountable to this group.

F: Country and regional grant holders will be accountable directly to the Management Agent on financial and delivery related matters. Devolved responsibility for decision making, monitoring, risk, and management with these suppliers rests with the Management Agent. If required, an issue can be escalated to either the DHSC Project Team informally or formally to the Fleming Fund Steering Committee.

Specific Governance for the Evaluation Supplier

  - The Evaluation Supplier and Management Agent are viewed as equal independencies, both of whom will report through the governance structures outlined above. To ensure independence of the Evaluation Supplier through the inception phase, the Evaluation Supplier will have an advisory and consultancy role whilst working collaboratively with the Management Agent in designing the monitoring strategy of the Fund, but ultimate accountability for the strategy put in place will rest with the Management Agent. Furthermore, if required, conflict of interest can be declared at any time.

  - During implementation, the Management Agent will answer to the Steering Committee if they are not collecting the data based on the best advice provided by the Evaluation Supplier.

- Scope and Deliverables of the Fleming Fund Evaluation

  - The ultimate desired impact of the Fleming Fund Theory of Change is reduced morbidity and mortality associated with AMR. The Evaluation Supplier will evaluate how far the outputs of the portfolio of country and regional grants will contribute to the outcomes and impact defined within the agreed Fleming Fund Theory of Change (see Annex B). It is understood that this analysis would be indicative, due to the amount of external variables which could affect the desired Fleming Fund impact as stated.

  - The formative aspect of the evaluation will indicatively answer the evaluation questions agreed during the inception phase, and produce recommendations to guide the portfolio of country and regional grants in how their outputs can best achieve and contribute to the outcomes and impact of the Fleming Fund. The formative report will be a key opportunity for any course correction suggestions.

  - The summative aspect of the evaluation will answer the evaluation questions agreed during the inception phase and evaluate how far the outputs of the portfolio of country and regional grants have contributed, or will contribute, to the outcomes and impact of the overarching Fleming Fund.

Proposed evaluation questions

  - The following are the minimum proposed evaluation questions to be answered by the successful Evaluation Supplier as part of the provision of the services:

- How relevant are the Fleming Fund investments to influencing data use within the country context? (OECD DAC Criteria – Relevance)

- What is the effect of a common protocol(s) to collect AMR data on programme implementation and results? (OECD DAC Criteria – Efficiency)

- To what extent has the AMR data collected been used to support national level policy and regulation of antimicrobials? (OECD DAC Criteria – Effectiveness)

- To what extent has the AMR data collected impacted on clinical and social practice surrounding antimicrobials? (OECD DAC Criteria – Effectiveness)

- To what extent has the AMR data collected been used on an international level to inform relevant agenda? (OECD DAC Criteria – Effectiveness)

- How successfully has the Fleming Fund aligned with other international work on AMR? (OECD DAC Criteria – Efficiency)

  - Indicative sub-questions for the evaluation are presented in Annex D. The successful bidder will be expected to develop and refine these questions during the inception phase.

  - DHSC welcomes advice on any other products which may be of value when evaluating the Fleming Fund projects and the programme as a whole. Bidders are encouraged to include any suggestions in their proposals.

  - DHSC would welcome any suggestions around how counterfactual or quasi-experimental designs could be built into the evaluation process linked to improvements in AMR data collection processes.

Evaluation Supplier Deliverables

  - The expected deliverables for the Evaluation Supplier are detailed below.

  - Inception Phase

The selected Evaluation Supplier will be required to achieve, at a minimum, the following deliverables (see Table 1 below) during the inception phase.

Table 1: Expected activities and deliverables during the inception phase

|  | Inception Phase Milestone/Deliverable | Expected activities and deliverables |
| --- | --- | --- |
| 1 | An approved joint strategy between the Evaluation Supplier and the Management Agent | The Evaluation Supplier is expected to agree a draft protocol for ways of working with the Management Agent including proposed meetings and workshops inviting the Authority. The Evaluation Supplier is expected to agree with the Management Agent a draft monitoring and evaluation framework for the portfolio of country and regional grants, containing at a minimum the following: - Key data collection points. - A detailed description of the focus for analysis and the outputs to be analysed throughout the evaluation. - A monitoring and evaluation framework for the portfolio of country and regional grants. |
| 2 | An approved refined Theory of Change | The independent Evaluation Supplier will collaborate with the Authority and with the appointed Management Agent to refine the theory of change set out in Annex B of the Specification. The theory of change document will be submitted to DHSC for approval. |
| 3 | An approved evaluation approach/ methodology | The Evaluation Supplier will be required to work collaboratively with DHSC and with the appointed Management Agent during the inception phase in order to create a detailed methodology for the evaluation This work will include discussions and decisions about what data and information will need to be collected regularly by the Management Agent in order to feed the analysis needed for the evaluation questions. This, in turn, will help to shape and feed into the monitoring strategy. The Evaluation Supplier will refine, expand and revise the evaluation questions laid out at paragraph 5.4 of the Specification. The Evaluation Supplier will refine, expand and revise the indicative evaluation sub questions laid out at Annex D of the Specification. It is expected that the evaluation implementation and reporting will comply with the OECD-DAC quality standards for development evaluation The methodology submitted to DHSC for approval will include, but is not limited to: - The final evaluation questions and sub-questions. - Key data collection points. - A detailed description of the focus for analysis and the outputs to be analysed throughout evaluation. - A detailed evaluation approach, including a framework of collaborative typologies and levels to be used in the mapping and sample selection. |
| 4 | Regular reporting - Quarterly - Continued collaboration with the Authority Representative / appointed Contract Manager | Regular reporting will be in the form of an activity update to DHSC submitted on a quarterly basis, either through a document, presentation with PowerPoint summary or a face-to-face meeting. This opportunity will allow the Evaluation Supplier to provide evidence of working against the agreed activities, as well as a chance to share lessons learnt. DHSC will require interim reporting throughout the life of the contract to ensure progress and that the financial status of the evaluation is monitored as being within planned funding / budget, as well as ensuring continued learning from the analysis throughout the programme. |
| 5 | An approved Implementation Plan | The Evaluation Supplier will be expected to conduct workshops with the Management Agent and with grantees from the pilot schemes to gather learning and help to ensure that learning from these projects informs the Implementation Plan. The independent Evaluation Supplier will be expected to support and work with the Management Agent to design and draft the Implementation Plan for the Fleming Fund. This early involvement of the Evaluation Supplier is intended to ensure that evaluation considerations are ‘embedded’ within the Implementation Plan. It is expected that the evaluation implementation and reporting will comply with the OECD-DAC quality standards for development evaluation. The Evaluation Supplier will hold regular meetings with the Authority and Management Agent to discuss requirements and progress of the draft Implementation Plan. The format of the meetings will be agreed between the parties. The Evaluation Supplier will collaborate with the Authority and Management Agent to identify data collection required to answer the evaluation questions developed and approved in accordance with Milestone/Deliverable 3. The Evaluation Supplier will work with the Management Agent to provide a draft Implementation Plan, to be submitted by the Management Agent to the Authority by a date to be agreed. The draft Implementation Plan must contain, but is not limited to: - A detailed methodology for data collection, analysis and regular reporting, including proposals for verifying the baseline information for each project granted funding by the Management Agent. - A detailed work plan outlining timeframe, details of the final project time, defined output payments and a detailed financial plan for the implementation phase. The financial plan must draw on the pricing structures provided by the Evaluation Supplier within the tendered rate cards, and be accompanied by narrative explanation and reasoning for any planned costs exceeding the average price given within those rate cards. Any costs exceeding the maximum price given within those rate cards will require the Authority’s prior written approval before the costs can be incurred. - The evaluation methodology, questions and sub questions approved in accordance with Milestone/Deliverable 3. - Any learning gathered from the workshops conducted in relation to the pilot schemes. - A proposed approach for working with grantees and other key stakeholders throughout the life of the contract. - Proposals for detailing the service levels in Annex 1 to Part A of Schedule 6 (Service Levels and Performance Monitoring). - Proposals for delay payments for Part A of Schedule 4 (Inception Plan) and Annex 1 of Schedule 2 (Implementation Plan). - Proposals for the capability-building activities to be undertaken with grantees in understanding the Monitoring and Evaluation (M&E) and the theory of change laid out in Annex B of the Specification. - Proposals to ensure compliance with the quality standards referred to in paragraph 5.13 of the Specification, or equivalent quality standards. - A detailed business continuity and disaster recovery plan. - Proposals for the provision of a mid-point review report, which answers the evaluation questions indicatively and supplies formative recommendations for the remainder of the Fleming Fund. - Proposals for the provision of a final summative evaluation report that answers the evaluation questions agreed in accordance with Milestone/Deliverable 3. |

  - Implementation Phase

Specific objectives and Deliverables for the implementation phase will be developed in consultation between the Evaluation Supplier and DHSC during the inception stage of the Contract. The Evaluation Supplier will be held financially accountable for the agreed outputs and should show effective progress towards these targets through the lifetime of the programme.

Although specific objectives, Deliverables and Milestones will be defined in consultation with DHSC during inception phase, the table indicates the minimum expected Deliverables.

|  | Implementation Phase Milestone/Deliverable | Expected activities and minimum Deliverables |
| --- | --- | --- |
| 1 | Regular reporting - Quarterly - Continued collaboration with the Authority Representative / appointed Contract Manager | Regular reporting will be in the form of an activity update to DHSC submitted on a quarterly basis, either through a document, presentation with PowerPoint summary or a face-to-face meeting. This opportunity will allow the Evaluation Supplier to provide evidence of working against the agreed activities as well as a chance to share lessons learnt. DHSC will require interim reporting throughout the life of the contract to ensure progress and the financial status of the evaluation is monitored as being within planned funding / budget, as well as ensuring continued learning from the analysis throughout the programme. |
| 2 | Continued collaboration, data analysis and provision of recommendations for course correction with the Management Agent | The Evaluation Supplier will gather data from the Management Agent and undertake analysis during the programme’s implementation period. Country and regional grants under the Fleming Fund may start at different times, will be at different stages of implementation, and will have had different levels of engagement with the linked scientific and clinical institutions (such as local hospitals and universities). The Evaluation Supplier will be required to take account of this in its approach and analysis. The Evaluation Supplier will be expected to verify the baseline information for each project granted funding, completed by the Management Agent. Any formative recommendations would be made through the reporting mechanism built into the programme structure which will be finalised during the inception phase. |
| 3 | Strong stakeholder collaboration and support to grantees | DHSC will encourage strong collaboration between key stakeholders throughout the evaluation period. This will include national and international policymakers. The Management Agent is expected to complete advocacy work with national governments, and so will be able to provide entry points to national government officials where necessary for the purposes of evaluating the programme. DHSC is managing the relationship with multilaterals such as WHO, FAO and OIE and therefore will be able to provide entry points and contacts within such organisations. The Evaluation Supplier will be expected to provide workshops with grantees in order to support understanding of Monitoring and Evaluation and the theory of change (see Annex B for Theory of Change). |
| 4 | Formative report | The Independent Evaluation Supplier will be expected to complete and submit for approval a mid-point review of the programme, indicatively answering the evaluation questions agreed during the Inception Phase, and producing recommendations to guide the portfolio of country and regional grants in how their outputs can best achieve and contribute to the outcomes and impact of the Fleming Fund. The formative report will be a key opportunity for any course correction suggestions It is expected that the evaluation implementation and reporting will comply with the OECD-DAC quality standards for development evaluation. Generally, the Evaluation Supplier should seek to - Support grantees at appropriate points during the life of the Fund, supporting an adaptive approach to implementation that is able to continually improve the quality of the programme and help to achieve the stated outcomes of each project; - If possible, analyse how effectively the application of the standard surveillance protocols is working across the portfolio of country and regional projects and contributing to the collection and sharing of global surveillance data through the WHO Global AMR Surveillance System (GLASS). - Evaluate how far the outputs of Fleming Fund portfolio of country and regional grants have contributed/are contributing to the outcomes and impact of the Fleming Fund Theory of Change. The formative aspect of the evaluation will encourage the grantees to provide honest reflections on their achievements and challenges and be open to recommendations from the Evaluation Supplier that aim towards continual improvement for the portfolio of grants. It will also encourage grantees, as well as the Management Agent and DHSC, to see how each project fits with the overarching aim of the Fund and ensure the outcomes of each project are aligned and relevant to achieving the outcomes and impact of the Fleming Fund as a whole. Formative recommendations would be made through the reporting mechanism built into the programme structure which will be finalised during the inception phase. DHSC is keen to ensure that the evaluation results in learning for: - DHSC; - Country and regional grantees during the life of the Fleming Fund; - Ministries of Health, Agriculture and Finance in Fleming Fund investment countries; - AMR policy community more broadly, including Ministries of Health, Agriculture and Finance in countries broader than the Fleming Fund investment countries; - AMR scientific community; - Multilateral organisations, such as the World Health Organization (WHO), Food and Agriculture Organisation (FAO) and the World Organisation for Animal Health (OIE) and their respective member states. |
| 5 | Summative final report | The Evaluation Supplier is expected to complete and submit for approval an evaluation report at the agreed time within the Implementation Plan, answering the evaluation questions agreed during the Inception Phase and evaluating how far the outputs of the portfolio of country and regional grants have contributed, or will contribute, to the outcomes and impact of the overarching Fleming Fund. It is expected that the evaluation implementation and reporting will comply with the OECD-DAC quality standards for development evaluation. The summative aspect of the evaluation will, at a minimum, - Answer the agreed evaluation questions and sub-questions identified during the inception phase - Discuss how far portfolio outputs contributed to the desired outcomes and impact of the Fleming Fund. It is understood that this analysis would be indicative, due to the amount of external variables which will impact the level of mortality and morbidity due to AMR. - Analyse how effectively the application of the standard surveillance protocols have worked across the projects and contributed to the collection and sharing of global surveillance data through the WHO Global AMR Surveillance System (GLASS). - Identify which funded approaches/projects have been the most effective in delivering the desired outcomes and impact. DHSC is keen to ensure that the evaluation results in learning for: - DHSC; - Country and regional grantees during the life of the Fleming Fund; - Ministries of Health, Agriculture and Finance in Fleming Fund investment countries; - AMR policy community more broadly, including Ministries of Health, Agriculture and Finance in countries broader than the Fleming Fund investment countries; - AMR scientific community; - Multilateral organisations, such as the World Health Organization (WHO), Food and Agriculture Organisation (FAO) and the World Organisation for Animal Health (OIE) and their respective member states. |
| 6 | Evidence briefs of key thematic lessons. | An evidence brief is designed to provide an overview of the key evidence included in a systematic review/evaluation, to assist policy-makers and researchers in assessing the evidence in the field being researched. It summarises key findings, and provides links and references to the included studies. DHSC is keen to ensure that the evaluation results in learning for: - DHSC; - Country and regional grantees during the life of the Fleming Fund; - Ministries of Health, Agriculture and Finance in Fleming Fund investment countries; - AMR policy community more broadly, including Ministries of Health, Agriculture and Finance in countries broader than the Fleming Fund investment countries; - AMR scientific community; - Multilateral organisations, such as the World Health Organization (WHO), Food and Agriculture Organisation (FAO) and the World Organisation for Animal Health (OIE) and their respective member states. |

Available Data

  - It is anticipated that the Evaluation Supplier would join the project during inception phase and would help to shape the data collected by the programme in order to best answer the proposed evaluation questions. Below are the resources available to the selected Bidder:

- Scoping reports commissioned by DHSC to the Wellcome Trust on: an analysis of approaches to laboratory capacity strengthening; networks and education resources supporting drug resistant infection surveillance; and an analysis of the human/animal interface with a focus on LMICs;

- Individual project start up forms (showing project outcomes and indicators, many of which involve a specific outcome on learning and collaboration);

- Project baseline information;

- The bidding institutions supporting documents, such as operational reports;

- Any existing quantitative and qualitative data already being collected by projects’ own monitoring and evaluation systems (although it is important, as with the general approach taken throughout the evaluation, that this is approached in a manner that is sensitive to grantees’ capacities and avoids overburdening grantees). The quality of the data available is likely to be variable.

  - Also available to the Evaluation Supplier throughout the programme will be:

- Annual project reports submitted by grantees to Management Agent (including progress against each project outcome indicators).

- Annual reports from the Management Agent to DHSC.

Quality Standards

  - It is expected that the evaluation implementation and reporting will comply with the OECD-DAC quality standards for development evaluation.10

  - Bidders are expected to outline an appropriate quality assurance process for the evaluation implementation and outputs, and the ethical guidelines they will follow in carrying out the evaluation in their response.

  - The evaluation products produced by the Evaluation Supplier will also be submitted to DHSC and peer reviewed before being published.

- Contracting Phases and Management

Contracting Phases and Outputs

  - The evaluation will follow three distinct phases, with an indicative schedule as follows.

Figure 4: Indicative evaluation phases and schedule

| Period of Activity | Timeline | Activities and Outputs |
| --- | --- | --- |
| Inception phase (8 months) | Autumn 2016 – Spring 2017 | See table of deliverables and activities above, at 5.9 |
| Implementation – Data analysis mid-programme | Spring 2017 – Autumn 2019 | See table of deliverables and activities above, at 5.10 |
| Implementation – Data analysis and final reporting | Autumn 2019 – Autumn 2021 | See table of deliverables and activities above, at 5.10 |

Contract Period

  - DHSC intend to award one single contract to the successful bidder for the five year funding period to cover both inception and implementation phase. The contract will include a break clause after:

- 8 months, at the end of the inception period;

- 3 years.

  - Ahead of the break point at the end of the inception phase, DHSC will review the Evaluation Supplier deliverables and Implementation Plan. At this point a final set of objectives and deliverables will be agreed and payment schedule suggested. Subject to strong performance by the supplier during the inception phase, and on basis that DHSC has fully accepted all proposals, work-plans and budgets for the implementation period, DHSC will proceed to the implementation phase.

  - If there is ongoing need and further funding is available beyond the original five year period DHSC may seek to extend this contract by any period up to a further five years. This would only be considered if it makes sense from a Value for Money perspective, and further break points would be included.

Payment by Results

  - DHSC is committed to ensuring value for money through the commissioning of the Evaluation Supplier contract. DHSC will look to agree an output or milestone based payment model, recognising the need to release payments for both the evaluation outputs and key activities. Bidders must propose a detailed output/milestone based payment schedule for the Inception phase of the contract within Pricing Schedule Two.

Resources available to the Evaluation Supplier

  - DHSC and the Management Agent will provide support to the Evaluation Supplier in contacting and liaising with grantees, particularly at the start of the evaluation.

  - The Evaluation Supplier is expected to supply and manage its own logistics, including for in-country visits, and to be responsible for the organisation and delivery of all events carried out under the evaluation. Multi-country evaluations can raise significant logistical and coordination challenges, and proposals will need to demonstrate that the Evaluation Supplier has sufficient management and coordination structures and processes to address these challenges.

Duty of care

  - The Evaluation Supplier will be responsible for the safety and well-being, including appropriate security arrangements for its team. The Evaluation Supplier will also be responsible for the provision of suitable security arrangements for their domestic and business properties. The Evaluation Supplier is responsible for ensuring appropriate safety and security briefings for all of its Personnel working under the Evaluation Supplier contract. Travel advice is available on the FCO website and the Evaluation Supplier must ensure that it is up to date with the latest position. Please also see Annex E and Annex F for DFID Duty of Care Assessments for Sierra Leone and Burma, which are likely to be pilot countries.11

  - Bidders must develop their proposal on the basis of having a duty of care towards, and being fully responsible for, their Personnel in line with the details provided in section 6.8 above. Bidders must confirm in the proposal that they have capability to manage their duty of care responsibilities throughout the life of the Evaluation Supplier contract. Bidders should consider the following questions in this regard:

- Have you completed an initial assessment of potential risks that demonstrates your knowledge and understanding, and are you satisfied that you understand the risk management implications?

- Have you prepared an outline plan that you consider appropriate to manage these risks at this stage and are you confident/comfortable that you can implement this effectively?

- Have you ensured or will you ensure that your Personnel (if any), are appropriately trained (including specialist training where required) before they are deployed and will you ensure that on-going training is provided where necessary?

- Have you an appropriate mechanism in place to monitor risk on a live / on-going basis?

- Have you ensured or will you ensure that your Personnel (if any) are provided with and have access to suitable equipment and will you ensure that this is reviewed and provided on an on-going basis?

- Have you appropriate systems in place to manage an emergency / incident if one arises?

Authority Responsibilities

  - Alongside the work detailed at paragraphs 4.2-4.4 above, DHSC and the Management Agent will provide support to the Evaluation Supplier in contacting and liaising with grantees, particularly at the start of the evaluation;

  - DHSC will appoint a nominated Contract manager (the Authority Representative) to oversee the Services, in accordance with Clause 15 of the Contract terms and conditions;

Supplier Responsibilities

  - The Supplier shall

- Appoint a Contract manager (Supplier Representative) in accordance with Clause 15 of the Contract terms and conditions to oversee the work and liaise with / report as DHSC requires to DHSC’s Authority Representative;

- The Evaluation Supplier is expected to supply and manage its own logistics, including for in-country visits, and to be responsible for the organisation, logistics and delivery of all events carried out under the evaluation (which should be included in the Charges submitted as part of the bidder’s proposal). Multi-country evaluations can raise significant logistical and coordination challenges, and bidder’s proposals will need to demonstrate that the evaluation team has sufficient management and coordination structures and processes to address these challenges.

- Monitor the quality of the Service provision to ensure customer satisfaction in accordance with the key performance indicators outlined in the Contract (Schedule 6: Service Levels and Performance Monitoring), unless otherwise approved by the Authority Representative;

- Provide regular reporting as and when required by the Authority Representative. This will be in the form of, at a minimum, a quarterly activity and financial update to DHSC either through a document, presentation or a face-to-face meeting. This opportunity will allow the Evaluation Supplier to provide evidence of working against the agreed activities detailed in the inception report as well as being a continuing opportunity to provide lessons learnt.

- Provide updates on costs to be incurred under the Contract on a quarterly basis.

- Attend meetings on site by phone or by video conference to review progress and discuss the Service, as required by the Authority Representative;

- Attend a post Contract review with DHSC to discuss the Evaluation Supplier’s final evaluation report, and review whether the objectives of the Contract were met, to review the benefits achieved and to identify any lessons learnt for future projects.

- DHSC has a zero tolerance approach to corruption. Although the appointed Management Agent will have full responsibility for monitoring and mitigating the risk of fraud and corruption in the procurement and delivery of country and regional grants, the Evaluation Supplier will be expected to report any suspected corruption to the Authority Representative.

- Annex 2: Evaluation matrix

In section 1.2 of the Summative report and in Annex 3, we have set out an overarching framework for the evaluation design. This provides an overview of the relationship between evaluation questions (EQs), data sources, analytical methods, and evaluation workstreams and outputs. This overview is unpacked in the evaluation matrix below, with an indication of which methods and data sources will be used to address each EQ.

Table 1 The Evaluation Matrix

| criteria | Evaluation Questions | Indicators | Analytical Methods | Data Sources |
| --- | --- | --- | --- | --- |
| Relevance & effectiveness | (EQ1) What has been the increase in the quantity and/or quality of data on Antimicrobial Resistance (AMR) at a country level and to what extent has the Fleming Fund contributed to this increase? | Changes in availability of HH and AH data: - # patients tested - # isolates - # samples - # rounds of active sampling (AH only) # surveillance sites # GLASS pathogens tested | Contribution analysis Cross-case Synthesis Quantity and Quality analysis | AMR National Action Plan (NAP) monitoring reports and reports on the implementation of the Global Antimicrobial Resistance Surveillance System (GLASS) Managing Agent (Mott MacDonald) (MA) within grant monitoring reports. Key Informant Interviews (KIIs) |
| coherence | (EQ2) To what extent have the Fleming Fund's investments been aligned and coherent with other relevant investments at the country level? | Alignment of FF interventions with national priorities as set out in NAPs Evidence of internal coordination and coherence between CGs, RGs, Fleming Fellowships and global projects Alignment of FF interventions with interventions funded by other donors | Contribution analysis Alignment and Coherence Analysis Cross-case Synthesis | MA’s assessment of the surveillance systems and responses in grant assessment formats KIIs Documentation of other delivery partners (DPs) on their support |
| sustainability | (EQ3) How likely are the Fleming Fund's country-level results to be sustained? | Existence of current and planned arrangements to ensure key pillars of sustainability in place: - Resources - Capacity - Motivation - Plans (e.g. exit strategies) | Sustainability Analysis Cross-case Synthesis | MA’s assessment of the surveillance systems and responses in grant assessment formats MA within grant monitoring reports evidence on KIIs |
| Effectiveness | (EQ4) Has, or is it likely that, the increase in AMR data influenced: (a) changes in national policies/regulations; and/or (b) changes in practice and attitudes in country? | Existence of key conditions to promote use of AMR surveillance data for national-level policy/regulation change Evidence of use of AMR surveillance data at facility level | National policy agenda analysis (Multiple Streams Analysis) Stories of change case studies (Examples of USE analysis) Contribution analysis Cross-case Synthesis | AMR NAP monitoring reports TrACSS survey National AMR policy literature MA within grant monitoring reports KIIs |
| Relevance & effectiveness | (EQ5) What has been the increase in quality data shared and reported internationally and has the Fleming Fund contributed to this? | - # patients tested - # isolates - # samples - # rounds of active sampling (AH only) # surveillance sites # GLASS pathogens tested | Contribution analysis Quantity and Quality analysis | MA within grant monitoring reports. World Health Organization (WHO) GLASS reports late 2017, late 2019, and late 2021 KIIs |
| Efficiency | (EQ6) Did the Fleming Fund's investments at the country level offer Value for Money (VfM)? | Evidence that systems to manage for VfM are in place and aligned with best practice Evidence that VfM systems are delivering VfM in terms of economy, efficiency, effectiveness. | VfM analysis Contribution analysis Cross-case Synthesis | MA’s assessment of the surveillance systems and responses in grant assessment formats on efficiency and economy MA within grant monitoring reports evidence of efficiency and economy achieved KIIs |

- Annex 3: Overview of evaluation

This section provides an overview of our evaluation design described in more detail in our inception report, the methods that have been used to address the EQs, and a description of our sampling approach. The analytical methods include contribution analysis, national policy agenda analysis, data use analysis, alignment and coherence analysis, VfM analysis, sustainability analysis, data quantity and quality analysis and cross-case synthesis. For each method, we describe what the method is, what it was used for, and why we felt it was appropriate.

In Annex 4 a description of core data collection tools is included, before highlighting our approach to cross-case synthesis and to ensuring quality in the evaluation.

Objectives of the evaluation

The Department of Health and Social Care (DHSC) commissioned Itad to undertake an independent evaluation of the Fleming Fund grants programme. The focus of the evaluation is on how far the outputs of the portfolio of country and regional grants, and the Fleming Fellowships have contributed to the outcomes and impact identified by the DHSC. As such the results from workstreams 3 and 4 in the overall Fleming Fund (outlined in Figure 1) are within scope; outputs from workstreams 1 and 2 are not directly evaluated, except to the extent that they are identified as contributing to change in surveillance systems and outcomes in the countries in which we evaluate workstreams.

Over the past five years, the evaluation has had both learning and accountability objectives. Between 2018 and 2021, the evaluation identified instances of good practice to inform course correction and adaptation. It also identified challenges to the achievement of the Fund's objectives under workstreams 3 and 4 (outlined in Figure 1). The evaluation outputs have also been used to inform the decision by the DHSC and His Majesty's Treasury (HMT) on whether to fund another phase of work under the Fleming Fund and how the approach might be strengthened based on experience to date. A second phase of the Fleming Fund, worth £193.5 million over three years (Financial year 22/23 to financial year 24/25) has been approved. Formative work from the evaluation has been delivered to the DHSC but is not covered in this report.

Figure 1 Organogram of Fleming Fund workstreams

In 2021, the evaluation focus shifted to provide an independent summative judgement of the Fund's results and achievements as set out in the main report. We present evidence for six EQs (or ‘agreed measures of success’) which reflect the priorities of both Ministers and the Chief Medical Officer within the DHSC. These EQs (outlined in Figure 2) have been used to structure data collection and analysis, but not to structure this report.

Figure 2 Six EQs or ‘agreed measures of success’

Methodology

To address the EQs we have collected data in 16 case study countries, selected to maximise the extent of implementation evidence. This is based on our understanding of the MA’s country roll-out schedule, and the number of countries in which data/results will be available ahead of each of the key evaluation deliverables. At the time of finalising the inception report in mid-2018, the MA’s implementation plan indicated that second round country grants would have been rolled out across a total of 23 countries by the time data collection for the summative report needed to be done. To answer the EQs, it was important to allow some time for each second-round grant to demonstrate effectiveness and to generate data on outcomes prior to the evaluation. To facilitate this, in our view, at least six months of second grant implementation was required before evaluation activities took place in order to strike the balance between data availability and maximising the number of countries in the sample. It was anticipated that, by the end of Q2 2020, second round grants would have been rolled out in 14 to 18 countries. This would have allowed for potential implementation delays, and on careful consideration of available resources, we proposed to include 16 countries in our sample. These were the 16 where implementation began first – i.e. those not included in our sample were the last recipients of second round grants. A summary of our sampling strategy across key data sources is included in table 2.

In each country we used standard interviewing techniques for qualitative work, starting with an agreed list of KIs and then snowballing. We proposed snowball sampling because it is an appropriate and cost-effective approach for the identification of relevant stakeholders across multiple countries, where we did not have established and up-to-date networks of relevant stakeholders. Technically, we looked to stop interviewing people when we reached analytical saturation; however, in reality we snowballed to the degree that we could within the available time and resources.

Our focus is on the country- as opposed to regional- or global-level changes at three distinct levels across human, animal and environment sectors: 1) at the level of the surveillance system (EQ2, EQ3 and EQ6), to see if changes are sustainable and have been delivered with economy, efficiency and effectiveness – including the extent to which interventions are aligned with the work of others; 2) at the level of availability of more and better data, where our focus is on what has been the increase in the quantity and/or quality of data on AMR at country level and to what extent has the Fleming Fund contributed to this increase (EQ1); at outcome level - whether the availability of more and better data leads to a significant change in the country or the availability of more and better data internationally (EQ2, EQ3, EQ4, EQ5 and EQ6). The Fleming Fund has adopted a One Health approach to improving the capacity of Low-and Middle-Income Countries (LMICs) to collect data, enable its sharing, collation and use to encourage the appropriate use of antibiotics. As such the evaluation has focused on Human Health (HH) and Animal Health (AH) surveillance systems but in a more limited number of countries, also the environment.

Table 2 Summary of sampling strategies

| Data source | Purpose / target | Sampling strategy |
| --- | --- | --- |
| Documents | - Comprehensive overview of design and implementation. Primarily generated MA or it’s subgrantees, but sometimes other sources such as DHSC or wider literature for context. | All relevant available documents were reviewed. |
| Countries | - Unit of data collection, to provide basis for cross-country/portfolio-level analysis. - Not aiming to draw out lessons, so generalisability less of a concern. - But important to have geographic balance across four regions: East & Southern Africa, West Africa, South Asia, South East Asia. | - Selection designed to balance availability of data for the summative report while covering as many countries as possible. The eight that are not included in our sample will be the last recipients of second round grants. - Sample included countries that were due, at the time of finalising our inception report in mid-2018, to receive at least six months of support under second country grants. Therefore, those countries had the greatest prospect of substantive results and were the countries that were most relevant to answering our EQs. |
| Grants | - Understand Fleming Fund expected outputs (and actual delivery) in order to inform EQs. | - All active MA grants in sample countries were included - All MA grants that were non-country specific were included - Direct grants managed by DHSC were not included. |
| Key informant interviews | - Qualitative perspective from multiple stakeholder groups to generate evidence against EQs and enable cross country comparison. - To ensure maximum coverage and representation of key stakeholders in order to enhance and complement data from documentation, especially for areas that are were not well covered and/or that require more qualitative information. - Number of interviews determined by resources – approximately 15-20 per country visit (not including site visits). Number of global and Regional KIIs determined by number of non-country grants and number of thematic leads within MA team. | - Stakeholder analysis to identify relevant people in each country - Balanced perspectives across key categories of KI (identified through above stakeholder analysis): Country grantee, AMR focal point, OIE/GLASS focal point, National Reference Lab staff, Fleming Fellows, AMRCC members, other decision makers, development partners. - Purposive sample. Country leads within the evaluation team worked with country grantees to identify specific individuals for each category up to an indicative maximum as set out in guidance developed by evaluation senior leadership team. - Snowballing: including additional KIs suggested by other KIs when deemed relevant. Technically, we looked to stop interviewing people when we reached analytical saturation; however, in reality we snowballed to the degree possible within the available time and resources. |
| Site visits | - To generate a more granular understanding of how Fleming Fund support worked in practice, albeit on an illustrative rather than representative basis. - To enable identification of examples of use at facility-level. - 3-5 sites per sector | Criteria for selecting sites: - At least one Human Health (HH) and one Animal Health (AH) surveillance site should be visited; ideally two or three for each sector. It may be preferable therefore to focus on sites where HH and AH are supported in the same location and sites that are easy to reach. - Sites that have received investment in either physical infrastructure/renovation or equipment; and or training. - Sites that have a Quality Manager in place - Sites that can be expected to have implemented SOPs developed through FF support - Sites that have given examples of use at facility level |

Our overall evaluation framework is reflected in Figure 3 below. This highlights that the agreed EQs provide the foundation of our framework and that we will draw on a range of data sources to answer each evaluation question through the application of a mixed methods approach, using a range of analytical methods. (It should be noted that the main analytical methods have changed from what was outlined in the inception report to what was used in the summative evaluation (outlined above). The analytical methods used were selected to best answer the EQs and the overarching evaluation objective. Details on why the chosen methods were suitable are outlined later in section 1.3.). It is not a theory-based evaluation, but we have supported the DHSC to articulate a portfolio-level Theory of Change (ToC) as set out in Annex 18 which has informed our data collection and analysis. The specific application of methods and data sources to each EQ is set out in an evaluation matrix in Annex 2. Our framework also highlights the evaluation’s twin objectives around learning and accountability, as described above.

Whilst the entire phase 1 evaluation has been conducted from 2018 to 2022, the data collection and analysis for this summative report started in September 2021 and concluded in July 2022. Tools were piloted in two of our 16 focus countries (Zambia and Pakistan) and revisions were made to rationalise and ensure they were fit for purpose. Data collection was completed in two waves, with the identification of preliminary findings and further rationalisation of tools completed in March 2022. In total our analysis reflected on an evidence base of over 1,900 documents (Vol. II, Annex 4) and over 400 KIIs (Vol. II, Annex 20), plus work completed in the period 2018-2021. The evaluation team ‘thematic leads’ completed data analysis for each EQ, including at a cross-theme workshop in September 2022. A draft report was reviewed by our Evaluation Advisory Group in November 2022, in parallel with checks for factual accuracy by the MA (which were incorporated as required in the final draft).

Figure 3 Overview of evaluation framework

Main analytical methods

The main analytical methods that were used in the evaluation were contribution analysis, alignment, and coherence analysis, national policy agenda analysis, data use analysis, sustainability analysis, data quantity and quality analysis, and VfM analysis. The following sections will provide more detail on each of these methods.

Contribution analysis

What the method is

Contribution analysis is a method that is used to answer EQs about how and why things happened, rather than to establish whether they happened. It is a method that is based on the existence of, or the development of, a postulated ToC for the intervention being examined. A ToC sets out how and why it is believed that the intervention’s activities will lead to a contribution to the intended results. Contribution analysis then tests this theory against the evidence available on the results observed and the various assumptions behind the ToC and examines the role of other influencing factors. The analysis either confirms—verifies—the postulated ToC or suggests revisions in the theory (based on iterations of data collection and analysis) where the reality appears otherwise.

Which EQs does this method help answer?

Directly EQ1 What has been the increase in the quantity and/or quality of data on AMR at country level and to what extent has the Fleming Fund contributed to this increase? EQ5 What has been the increase in quality data shared and reported internationally and has the Fleming Fund contributed to this? Indirectly EQ2 To what extent have the Fleming Fund's investments been aligned and coherent with other relevant investments at country level? EQ6 Did the Fleming Fund's investments at country level offer VfM?

How was it applied?

Contribution analysis is usually applied through six clear steps (see Figure 4 below). It is important to note that these steps incorporate a process of iteration around the ToC and the contribution story (steps 4, 5, and 6) which can lead to revising the ToC if appropriate.

Figure 4 Six steps of contribution analysis

In the context of this evaluation, we have operationalised Contribution Analysis through three clear steps to build a ‘contribution story’ for each of the five changes in each of our 16 sample countries as a unit of analysis.

Firstly, we assessed the extent to which five key changes were observable within the implementation timeframe:

- C1: Changes in the quantity (C1a) and quality (C1b) of country-level HH AMR/C/U data generated at country level.

- C2: Changes in the quantity (C2a) and quality (C2b) of country-level AH AMR/C/U data generated at country level.

- C3: Changes in the quantity of HH/ AH AMR/C/U data shared at the country level with relevant committees (Antimicrobial Resistance Coordinating Committee (AMRCC)).

- C4: Changes in the quantity of country-level HH AMR data shared internationally with WHO GLASS.

- C5: Changes in the quantity of country-level AH AMU data shared internationally with World Organisation for Animal Health (WOAH formerly OIE).

Secondly, for each key change, we established what the three key drivers had been.

Thirdly, our contribution analysis approach then assessed the extent to which it is plausible to believe that CGs, RGs, and Fleming Fellowships have collectively contributed to the observed changes vis-à-vis the contribution of other influencing factors. We have considered three types of contributors:

Contribution by CGs, RGs, and Fleming Fellowships (that are directly in scope for our evaluation);

Contribution by the DHSC-managed Fleming Fund grants (known as Global Projects);

Other influencing factors – i.e. interventions by other development partners (such as USA Centers for Disease Control and Prevention (CDC) and Food and Agriculture Organization (FAO) with non-Fleming Fund funds), and government-funded interventions.

In cases in which there has not been a visible/measurable change, we have used our contribution analysis approach to document the main reasons why, and whether and how the Fleming Fund is supporting progress in the right direction.

To assess the relative contribution against each main driver we used the following scale:

- Vital: Fleming Fund interventions were the only or main contributor to the driver. Without them, the change would not have materialised or would be most likely much smaller than observed.

- Important: Fleming Fund interventions were one of the main contributors to the driver. Without them, the extent of change would have most likely been smaller than observed.

- Some: Evidence points to Fleming Fund interventions being one of the contributory factors to the driver, among multiple others.

- Limited: It is hard to establish a causal link between Fleming Fund interventions and the driver of change being in place, but it is possible that such links exist.

- None: We could not observe any links between Fleming Fund interventions and the driver of change.

Our contribution stories set out whether and why it is reasonable to assume that the interventions supported by the Fleming Fund have contributed to the observed changes. The evaluation team then assessed how credible these stories were and looked for additional evidence through further data collection and sense checking of the ‘contribution story’ with grantees, the MA and external stakeholders such as other development partners.

For standardisation and given that what the Fleming Fund is trying to achieve in each country is fairly similar, we used a standardised country-level ToC (Figure 5) based on the Fleming Fund portfolio level ToC and further thinking done during the design phase of the summative evaluation.

Figure 5 Fleming Fund country-level ToC for contribution analysis

Annex 8 (on quantity and quality) and section 1.3.4 (on data use) set out the methodology we have applied to measure what changes in these areas could be observed at the time of data collection in 2022, compared to the baseline we have collected (2018).

Why is contribution analysis an appropriate method for this evaluation?

Contribution analysis was an appropriate method because the stakeholders wanted to understand what works and why, and the complex multistakeholder field in which AMR interventions are being implemented. A number of methods were considered for answering these questions. Experimental and quasi-experimental methods were rejected because the basic pre-conditions needed for credibly using such methods were not in place. Basically, given the bottom-up implementation design process used, the ’treatment’ in each country and surveillance system, would be different, while all other factors would not be the same across the 23 countries, while change is likely to come from the complex interaction of several factors. As flagged in a 2012 paper on impact evaluation for the Department for International Development (DFID) there are many alternative theory-based methods we could have selected but we chose contribution analysis as the most appropriate for the following reasons. First, it is currently the main method used in development evaluation when using theory-based methods to verify a programme’s theory, based on evaluation of empirical evidence, and we have strong and extensive experience in how to use it well. Second, it is the method that other stakeholders are most likely to be familiar with, which enhances the possibility of their getting value from the results. Third, we concluded that the application of the other possible methods, such as process tracing, was unlikely to deliver a significantly more credible and robust evaluation. Fourth, we had the scope to conclude three trips through the evaluation, which enabled us to iteratively build and refine a ‘contribution story’.

Alignment and coherence

What the method is

According to the Development Assistance Committee (DAC) definition of coherence, our approach is both internal coherence (addressing the synergies and interlinkages between the intervention and other interventions carried out by the same institution/government, as well as the consistency of the intervention with the relevant international norms and standards to which that institution/government adheres) and external coherence (considering the consistency of the intervention with other actors’ interventions in the same context). This includes complementarity, harmonisation and coordination with others, and the extent to which the intervention is adding value while avoiding duplication of effort).

Which EQs does this method help answer?

EQ2 To what extent have the Fleming Fund's investments been aligned and coherent with other relevant investments at country level?

While previous rounds of data collection have focused on approaches to internal coherence and linkages between CG, RG, and Fellowship investments alone, the summative evaluation has focused on 1. alignment with national priorities; 2. internal coherence (including coherence with Global Projects); and 3. external coherence with interventions by other DPs. We have also looked at mechanisms to maximise alignment and coherence and to coordinate with other DPs, with a focus on Country Coordination Mechanisms (CCMs) established in 2019/20.

National policy agenda analysis

What is national policy agenda analysis and what did we use it for?

National policy agenda analysis is an approach to understanding public policy which concentrates on how countries take action, based on the decisions of governments and other actors like legislatures.

We used national policy agenda analysis as a structure for assessing national-level AMR data use comparatively across the Fleming Fund countries. This was a useful approach because it located national AMR data use in the context of broader political economy (PE) dynamics.

Which evaluation question does this method help answer?

This method will be used to answer the following evaluation question:

EQ4 Has, or is it likely that, the increase in AMR data influenced: a) changes in national policies/ regulations? and/or b) changes in practice and attitudes in country?

How we applied the method

Our application of national policy agenda analysis in this instance drew on two main approaches, the process from necessary and sufficient analysis; and theory from Multiple Streams Analysis (MSA). We used necessary and sufficient analysis to assess whether conditions are in place that make it plausible to believe that AMR surveillance data will be used to affect policy/regulatory behaviour change at the national level. This analysis was in turn based on Kingdon’s multiple streams framework which is a well-developed theory explaining how policy processes happen, how evidence can contribute to them and what other conditions need to be in place for successful evidence-informed policymaking. See Annex 9 for more detail on Kingdon’s approach and the results of our MSA.

Our approach included six steps as shown in Figure 6, and described in more detail below.

Figure 6 Six steps of necessary and sufficient analysis

Step 1. Identifying the outcomes prioritised by the AMR Coordinating Committee or other key stakeholders.

In any one country, there are multiple outcomes where change may plausibly happen. Additionally, how the use of more or better-quality evidence on AMR might contribute to change at the outcome level will vary significantly both within and between outcomes. For instance, the role of evidence in changing government policy or regulation is different from in a stewardship initiative within a health facility or nationally. Working with the MA, we were able to identify the outcomes that have been prioritised by AMRCCs. NAPs and associated documentation were also reviewed to identify any cases of variation from the Global Action Plan (GAP) structure for action on AMR, or evidence of action from implementation or resourcing plans and evaluative material (where available).

Table 3 Possible outcomes that may be prioritised by the countries

| Outcome of interest | Related to which sector: |  |  |
| --- | --- | --- | --- |
|  | Human health | Animal Health | Environment |
| Has, or is it likely that the increase in AMR data influenced changes in national policies/regulations? | ? | ? | ? |
| Has, or is it likely that the increase in AMR data influenced changes in practice and attitudes in country? | ? | ? | ? |

Step 2.	Clarifying how the stakeholders believe more, or better, evidence will or has been used to contribute towards the achievement of the outcome.

Through refinement of the programme ToC (Annex 18), we clarified how stakeholders believe more, or better, data will or has been used to contribute towards the achievement of the outcomes.

Step 3. Identifying the underlying theory for how and why this approach will work.

John Kingdon’s Multiple Streams Framework theory on agenda setting was identified as the most appropriate theory for the necessary and sufficient analysis. Kingdon’s theory posits that policy agendas are set and influenced by a range of conditions that form three process streams. These streams include:

- Problem stream: how social conditions come to be defined as a problem to policymakers.

- Policy stream: the solutions generated to address problems.

- Political stream: political factors, including the influence of interest groups, the ‘national mood’ and turnover of elected officials.

Kingdon’s theory is well-suited to the assessment of the influence of data or evidence on the action in this instance for several reasons, including substantial conceptual and applied elaboration in the field of health policy and policy in LMICs.

Step 4.	Casting the theory as a set of necessary and sufficient conditions that need to be in place for change to happen at the outcome level.

According to Kingdon’s research, issues have a high propensity to attract the attention of policymakers when the above process streams converge to create a ‘policy window’. During this period of opportunity, actors can influence policy processes, for example, through the introduction of existing or new evidence. The evaluation team reviewed Kingdon’s model, identifying various conditions under each of the three process streams.

See Annex 9 for details of the substantive results of our MSA applying Kingdon’s theory to the national policy agenda context of Fleming Fund countries.

Step 5.	Gathering empirical evidence to test whether necessary and sufficient conditions are in place.

Once conditions have been identified through theory, the method then requires that we define how we will judge that the condition is either present or absent in a country. Systematic searches were undertaken for relevant documentary evidence (including from research, official and media sources) at specified time intervals (2020 and 2022). This material was then reviewed using Kingdon MSA subcomponents as an analytical structure, leading to summary statements on each of the three streams generated from across the subcomponent observations. Any crucial insights or gaps for each country were then tested in conversation with key stakeholders as part of the KIIs, especially focusing on the problem stream.

Step 6.	Judging whether the Fleming Fund’s investments are focused on influencing the right conditions.

Finally, the information assembled through this analytical process was fed into overall judgements about the conditions necessary for national data use, with contribution analysis observations on data use considered for assessments of phase 1’s focus.

Why was national policy agenda analysis an appropriate method for this evaluation?

National policy agenda analysis was especially helpful in answering part (a) of EQ4, which concerns changes in national policies/regulations. It was deployed in combination with contribution analysis (see 1.3.1 above), which provided insight into what has happened to date as a result of AMR data increases, in order to add predictive power (what can be considered likely to happen in the future) and to broaden the scope through which data influence is considered. Applying national policy agenda analysis for this evaluation enabled us to draw on previous evidence of how and why change happens, grounding the data use assessments in a large body of theoretically based policy research and linking it to state-of-the-art development practice for adaptive management in political contexts. This enhances the credibility of our judgements about what is plausible to expect in the 23 countries.

Examples of Use of data at the facility level

What are Examples of Use and what did we use them for?

‘Examples of Use’ (EoU) were short-form narrative reports in a consistent format gathered from Fleming Fund stakeholders as part of data collection for this evaluation with a specific focus on uses of AMR data at the facility level. These were small, local versions of ‘Stories of Change’ which were developed to offer facility-level stakeholders a way of communicating results from Fleming Fund’s phase 1. The EoU approach was developed by our evaluation team, in conversation with the MA and the DHSC, to improve evaluative insights at the facility level, responding to growing programme interest in results at that level.

The immediate purpose for developing and implementing the EoU approach as part of evaluation methods was outcome harvesting. Outcome harvesting is a method in evaluation practice that addresses longer-term, higher-level (i.e. outcome or impact) results in complex settings with low reliance on established programme theory.

Which evaluation question did this method help answer?

This method will be used to answer the following evaluation question:

EQ4 Has, or is it likely that the increase in AMR data influenced: a) changes in national policies/ regulations? and/or b) changes in practice and attitudes in country?

How we applied the method

The EoU method was applied over a standard design – implement – analyse – reflect cycle.

The EoU approach was developed for maximum simplicity. A one-page template was developed for facility-level narrative reporting of examples of data use. Template completion was integrated into the wider evaluation data collection as an opportunity for a repeated offering to stakeholders including the MA and CG collaborating on country data collection and KIIs when making claims about local data uses. This approach was piloted in the initial evaluation data collection countries, with adjustments then made for wider application.

EoU were then gathered country by country as part of wider engagement for evaluation data collection, using an approach akin to snowball sampling in which EoU were requested following any indication that stakeholders may have relevant information to provide. For example, the MA and CG were invited to submit EoU in order to communicate programme results, key informants (KIs) were prompted to back up any verbal claims about local change by providing the details on an EoU form, and staff engaged in laboratory visits were invited to complete an EoU to record known uses of the data they produce.

EoU analysis proceeded using basic qualitative techniques. Individual EoU were first checked for inclusion based on valid claims about data use. No independent verification was attempted. EoU were then added to a database assigning categories to each example, for example, based on the assessment of the evident objective (Antimicrobial Stewardship (AMS), Infection Prevention and Control (IPC), both or other) and result (attitudes, practice, policy, regulation) of the specified data use. Simple thematic analysis was also undertaken, notably considering text from the ‘what changed’ section of the EoU form.

Final reflections were then generated based on EoU analysis, notably combining EoU insights with observations from other methods relevant to data use evaluation (i.e. national policy agenda analysis and contribution analysis – see 1.3.1 above).

Why were Examples of Use an appropriate method for this evaluation?

EoU were especially helpful in answering part (b) of EQ4, which concerns changes in practice and attitudes in country. The existing evidence for practice and attitudes around AMR data use is relatively weak and unreliable, forming one aspect of the relative under-development of AMR social science. Typically, isolated local studies in LMIC indicate cause for concern about AMR practices and attitudes generally, often implied from the assessed issues of awareness and knowledge. There is little evidence of the relationship of AMR data to local practices or attitudes at the facility level and none that might be used to assess the results of Fleming Fund investments. It was therefore appropriate to seek primary data collection about these phenomena.

EoU design as an Outcome Harvesting approach was appropriate because the phase 1 ToC was not very specific about the intended facility-level changes and results. Although facility-level change was considered as a possible priority at the inception phase, ToC outcome statements were left relatively open and the Results Framework emphasised national-level change. Growing programme demand for evaluative insights into facility-level change therefore required the application of an inductive approach rather than the deductive techniques more favoured by convention.

EoU were also appropriate for this evaluation because of the way that they combined Outcome Harvesting with Stories of Change narrative reporting techniques. This is a constructive approach to Outcome Harvesting aimed at maximum learning, emphasising the benefits of stakeholder participation in ‘bottom-up’ approaches to programme implementation and the potential for improved communication of programme results. Its validity is confirmed by prior His Majesty’s Government (HMG) experience with evaluation in global programmes involving development partnership subject to high levels of potential contextual variation across countries and several layers of reporting between ‘ground truth’ and the investing agency decision-making. See Annex 9 for more detail on EoU.

Value for money

Our approach

Which EQs does this method help answer?

VfM analyses have been used to answer the following EQ:

EQ6 Did the Fleming Fund's investments at country level offer VfM?

To answer this, we addressed two sub-questions, as follows:

- EQ6A To what extent did the Fleming Fund (MA and DHSC) manage for VfM? Have resources been managed to achieve impact at country level?

- EQ6B To what extent did the Fleming Fund deliver VfM? Has phase 1 achieved what it set out to do at country level and delivered good VfM?

Methods

We applied the UK National Audit Office (NAO) 3E (Economy, Efficiency, Effectiveness) framework to review if the Fleming Fund managed VfM both at country and regional levels. Our approach looks at how well resources have been managed to achieve impact (EQ6A – management) as well as what the Fleming Fund has delivered in terms of VfM (EQ6B – measurement). We used this framework to assess both CGs and RGs.

Table 4 Themes for assessment of country and regional grants

|  | EQ6A themes | EQ6B themes |
| --- | --- | --- |
| Economy | - Evidence of arrangements in place for the planning, controlling and monitoring of financial resources at country and regional level. - Evidence of steps taken to maximise economy in operational support - Evidence that inputs are being purchased at the appropriate quality and the right price at country and regional level. | - VfM Savings (not including leveraging) - Unit costs - costs contained |
| Efficiency | - Evidence of arrangements being in place for activity planning, review and adaptation. - Evidence of a monitoring and evaluation (M&E) system in place to support the delivery of quality results - Evidence of risk management | - Percentage overhead - Activity and budget implementation rates - Value of leveraged resources |
| Effectiveness | - Evidence that grants were set up to deliver impact at country and regional level. - Evidence that processes were in place to support learning and adaptive management to deliver improved results at the (intermediate) outcome level. | - Evidence of increased quantity and quality of AMR data - (intermediate) Outcomes have been achieved as expected: Evidence of data use/ in GLASS |

Data for the analyses were retrieved in two ways:

- Desk reviews: The following documents were reviewed to provide answers to the questions:

  - Grant recommendations, the DHSC Response, Grant Agreement: provided useful information on the grant-making process for countries, especially in terms of competitive tendering for the CGs and RGs. Reviewing the grant processes also revealed the feedback provided on grantee budgets and cost drivers, especially with regard to overheads and comparative pricing, all essential processes of achieving economy. For a few countries, documents for grant extension were also available and reviewed.

  - Annex 9A and 9B: These documents provided evidence that budgets were reviewed and signed at the grant kick-off.

  - Quarterly Reports for CGs: These highlighted good M&E practices, provided evidence of risk management, and highlighted good VfM practices.

  - Previous country and regional VfM Grant Reviews: most CGs and RGs had at least one VfM review which showed grant performance for economy and efficiency domains, as well as recommendations for improvements.

  - Notes from KIIs: conducted during the earlier stages of implementation showed how the issues identified from the interviews had been addressed.

  - Financial reports: were not available for all countries, and where available in some cases, were not summarised by intervention areas.

It is important to note that the information for the effectiveness section at the country level, especially with regards to improvements in quantity, quality and use of HH and AH data, was retrieved from the general coding workbook and revealed outcome level results by country.

- KIIs were conducted with members of the regional team (RT) and CG teams to supplement and/or provide clarification for information available through the desk review. The KIIs provided a lot of views/experiences on the implementation approach in each country and region and were conducted between January and August 2022. A full list of interviews conducted with the country and RTs is available in Annex 20. KIIs with the global team were also reviewed for insights into their management approach.

Data from the above sources were analysed and synthesised via the following processes:

- Coding workbook: Available source documents were reviewed based on the themes set out in the framework and relevant information was inputted into the coding workbook based on the relevant themes across Economy, Efficiency and Effectiveness domains.

- Assessment framework: All CGs and RGs were rated based on the degree to which they each achieved economy and efficiency. Where information identified from the desk review was conflicting because it was captured at different points during implementation, e.g. multiple VfM reviews, the latest data was used as the basis for rating the CG/RG.

- Contribution analysis: This served to identify the drivers of the results seen for the outcome level results (Effectiveness) by quantifying and rating the strength of the underlying drivers of positive improvements in the quality and quantity of HH and AH data seen.

We encountered a few limitations during these analyses:

- Outcome level results were unavailable for the review of regional level grants and therefore limited the VfM reviews and analyses that could be completed.

- Financial reporting by grant/location/intervention areas for countries and regions were not all available.

Why is VfM analysis an appropriate method for this evaluation?

We believe VfM analysis is appropriate for this evaluation because it directly addresses EQ6. Our approach to VfM is consistent with best practices within the sector, and is aligned with DFID guidance. We have drawn on a variety of sources, including from the MA, external benchmarks and KIIs. Quantitative information has been analysed against the plan, trend, and where possible, against external benchmarks. Qualitative evidence has been used to assess how VfM has been embedded in country-level activities, what processes are in place to promote and achieve good VfM, and provide contextual information to support analysis of reported quantitative metrics.

Sustainability analysis

In 2019, we conducted a literature review to identify elements of good practice in delivering sustainability in development programmes. This review highlighted the importance of four factors in achieving sustainability; resources, capacity, motivation and planning. These provide a framework for making a judgement about the plausibility that Fleming Fund outputs will be sustained.

Which EQs does this method help answer?

Sustainability Analysis has been used to answer the following EQ:

EQ3 How likely are the Fleming Fund’s country-level results to be sustained?

Through a combination of document review and KIIs we gathered evidence on the extent to which these key pillars of sustainability were a) currently in place and b) expected or planned to be in place.

Table 5 Expected and planned pillars of sustainability

| Expected changes | Indicator | Source |
| --- | --- | --- |
| Resources exist to maintain the production of quality AMR surveillance data | Extent and source of non-Fleming Fund funding vs needed funding Adequacy of available resources | NAP Checklist (Annex 3) in Sustainability Assessment (SA) / Comprehensive Stakeholder Analysis (CSA) KIIs |
| Capacity exists to maintain the production of quality AMR surveillance data | Extent to which Fleming Fund supported sites have reached core level across The London School of Hygiene and Tropical Medicine (LSHTM) capacities | MA quarterly reporting KIIs |
| Systems: Incentives/ motivation to maintain and apply capacity | Institutional/organisational systems and structures recognise, value and reward the acquisition of relevant skills | KIIs |
| Planning | Exit or sustainability plans are developed by grantees, implemented, and reviewed | Document review KIIs |

We applied the following rubrics to generate a visual overview using Red, Amber, and Green (RAG) ratings for each of the key sustainability pillars.

Table 6 Rubrics applied to generate RAG ratings for each key sustainability pillar

| Rubric | Red | Amber | Green |
| --- | --- | --- | --- |
| Current | insufficient | Partially sufficient | Sufficient |
| Plans | No plans in place | Plans are in place but partially cover issues | Relevant/adequate plans in place and being implemented |
| Fleming Fund contribution | Not an area of focus | Some work was planned, but no significant implementation | Work planned and ongoing (specify which grants/interventions) |

We used the template below to capture a summary of evidence and RAG ratings. One template was completed for each sector in each of our 16 focus countries.

| Human Health | Current | Plans | Fleming Fund contribution |
| --- | --- | --- | --- |
| Summary statement |  |  |  |
| Resources |  |  |  |
| Capacity |  |  |  |
| Motivation |  |  |  |
| Planning |  |  |  |

Cross-case synthesis

Synthesis of evidence derived from the methods above is our main way to answer all six EQs. However, our approach to synthesis is influenced by two main factors:

1. The imperative to deliver evaluation outputs ahead of key decision points for the MA and the DHSC. This means the evaluation team had to deliver findings, conclusions, and recommendations for adaptive learning purposes in 2018, in the first half of 2019; while the findings, conclusions and recommendations from 2020 have supported a decision by the DHSC/HMG on a further phase of support to AMR through the Fleming Fund.

2. We needed to manage the fact that the implementation approach for grants being used by the MA was staggered. This affects what was available for evaluation in 2021-2022.

Focus of synthesis and methods to be used for each deliverable

At the country level, our analysis will provide four sources of analysis:

- Contribution analyses around the HH and AH surveillance systems;

- Alignment and Coherence Analysis;

- National policy agenda analysis;

- Data Use analysis;

- Quantity and quality analysis;

- Sustainability analyses; and,

- VfM analyses, looking at efficiency, economy and effectiveness.

For each form of analysis, evidence and conclusions are presented in the same format across each case. The focus in the evaluation design on ensuring that all analysis is presented in a standardised way was deliberate and the key to our approach to synthesis. The use of consistent frameworks across both countries and analytical methods allowed us to easily provide overviews of what is found across cases or analytical methods, using presentational methods such as RAG ratings.

Such an approach has the advantage of being both systematic and transparent whilst at the same time being feasible to implement within the resources and time available. Consistency across the evidence tells us that our understanding of what happens is supported by the empirical evidence. Divergence in patterns beyond what is expected, on the other hand, indicates areas into which we need to look further to try to understand how and why we are finding something unexpected and consider the implications for either what we can conclude or recommend.

Figure 7 below is an example of how a necessary and sufficient synthesis across three countries helps to explain the approach. In the example below, we identified that in three of the countries, the AMRCC has identified a particular outcome as important to achieve, say reform of legislation. In phase 1 of our analysis, based on our review of existing theoretical literature, we identified eight conditions (see phase 1) that need to be in place for that outcome to be achieved.

Figure 7 An indicative example of cross-case synthesis

Data collection at the country level then, in phase 2 of our analysis, allowed us to verify which of the conditions was already in place and which were not. In Phase 3 of our analysis, we then identified which of the conditions the grants had contributed towards. Conclusions from synthesis, and answering EQ4, would from the above include:

- The conditions needed to trigger the desired outcome were not in place in any of the countries, so it is not plausible to conclude that the outcome will be achieved in the near future;

- On the other hand, the Fleming Fund grants have, in this case contributed to ensuring that some of the necessary conditions are in place;

- The Fleming Fund grants have contributed to different conditions in different countries, so we would need to explain whether this shows that the grant design and targeting process is effective at identifying the right things to support or whether this was due to something else.

- We would need to explain why the Fleming Fund did not contribute to ensuring all the right conditions are in place. An explanation could be that it was assumed that either the country partners or another development partner was dealing with those conditions or it was not possible for any of the partners to affect those conditions.

Because the same analysis is presented in the same way across the cases throughout our design, the important point is that it allows the rapid inspection, across cases, to see if the same pattern is repeated across the relevant cases and/or differing analytical methods or whether there is divergence from either what we expected to observe or between what was found using different analytical methods.

- Annex 4: Data collection and analysis

This section briefly describes our approach to the key data collection methods that facilitated the application of the evaluation methods described above. Four sources of evidence were used within the evaluation: Interviews with stakeholders, within the MA, at country and regional level and with a small selection of DPs; evidence from the MA’s monitoring and other reports, secondary evidence drawn from the documentation of other stakeholders and DPs, and finally from site visits conducted during the country visits.

Through a combination of extensive reviews of secondary evidence contained in a range of documentation, and a focused period of primary data collection in each of the 16 focus countries, we gathered relevant data to enable the completion of a set of analytic tools. The approach across all three rounds of data collection has been broadly consistent.

In line with best practices, we have piloted our tools and processes in two countries (Nepal and Uganda for Country Visit 2, Pakistan and Zambia for Country Visit 3) and we have revised them before full implementation across all 16 countries.

Country visits

During the evaluation, the evaluation team completed three rounds of country visits (2018, 2019-2020 and 2021-2022). The third and final round of country visits were conducted to inform the Summative Evaluation. The country visit consisted of document reviews, KIIs and site visits.

    - Country document review

Document reviews were carried out for each country case study. The evaluation team reviewed over 729 documents as part of the country level document review. This included quarterly reports, annual reviews, sustainability assessments, VfM reports, country coordinating meeting minutes, GLASS reports, laboratory assessments and project documents that detailed the activities of other DPs involved in strengthening laboratories or, more broadly in AMR at country level. The documents were used to prepare the team for country visits, they were also coded, and the relevant information was extracted and used to complete analytical tools.

The table below outlines the number of documents reviewed per country.

Table 7 Documents reviewed per country

| Country | Number of documents reviewed |
| --- | --- |
| Bangladesh | 45 |
| Bhutan | 30 |
| Ghana | 50 |
| Indonesia | 90 |
| Kenya | 23 |
| Laos | 65 |
| Nepal | 60 |
| Nigeria | 80 |
| Pakistan | 25 |
| Senegal | 50 |
| Sierra Leone | 70 |
| Tanzania | 18 |
| Timor-Leste | 60 |
| Uganda | 30 |
| Vietnam | 53 |
| Zambia | 25 |
| Total | 729 |

The desk review helped focus and shape subsequent data collection during KIIs to reduce transaction costs for interviewees and collect the best possible information during the short time available. The document review yielded the following:

- Coding workbook filled in with excerpts of relevant documents against the codes that have been developed on the basis of our six EQs and the information needs of each thematic approach.

- Prefilled tools filled in with findings from the desk review, this outlined key gaps that the country visit needed to address.

- Prompts/hypothesis for the country team to follow up on during primary data collection.

Besides the documents listed earlier, the country teams also reviewed additional documents giving a good understanding of Fleming Fund investments in the country. In particular, this included:

- Request for Proposals (RfPs) for CG1, CG2 and any extensions

- Quarterly and annual reports

- Sustainability assessments

- VfM reports

- Debriefs/outputs from previous evaluation rounds.

Country teams also received inputs generated centrally:

- KII notes/findings from centrally conducted KIIs with RGs, host institutions (HIs) and global projects

- VfM related prompts/questions based on the central document review

- Global Database for Tracking AMR Country Self- Assessment Survey (TrACSS) summary for each country (for analysis on USE, EQ4)

- MSA analysis thematic document review.

Thematic leads conducted document reviews for each workstream analysis. The table below outlines the additional documents reviewed by thematic leads.

Table 8 Number of documents reviewed by theme

| Workstreams | Number of additional documents reviewed |
| --- | --- |
| One Health Analysis | Included in the country document review |
| Quantitative Analysis | Included in the country document review |
| Qualitative Analysis | Included in the country document review |
| MSA Analysis | 501 |
| Use Analysis | 120 |
| Coherence Analysis | Included in the country document review |
| Contribution Analysis | 5 |
| Sustainability Analysis | Included in the country document review |
| VfM Analysis | 364 |

    - Key informant interviews

KIIs were conducted to enhance and complement the data, especially for areas that are were not well covered by existing documentation and/or that require more qualitative information. KIIs were carried out using a semi-structured interview protocol, recorded with the interviewee’s permission before being written up and coded.

The approach to sampling was flexible and aimed at ensuring maximum coverage and representation of key stakeholders to cover the EQs. Standard interviewing techniques for qualitative work were used, starting with an agreed list of KIs and then snowballing until we had reached saturation. To ensure equitable and appropriate representation in our list of KIs, and wider engagement in this evaluation, we categorised KIs before sampling to ensure we captured an appropriate balance of views.

A stakeholder mapping exercise was conducted to identify a range of categories of KIs, (as outlined in Table 9 below) that we wanted to interview to help finalise our analytical tools – e.g. to help triangulate and provide nuance to evidence from document review. The country teams worked with the regional coordinator (RC and CG for each country, to identify specific, relevant individuals for each category – drawing on KI lists from previous rounds of data collection – and ensuring we complied with General Data Protection Regulation. We also used our networks to identify other relevant KIs.

Table 9 Key Informant Categories and their estimated numbers

| Category | Indicative number of KIIs | Estimated number of questions | Estimated number/ duration of KIIs |
| --- | --- | --- | --- |
| CG team | 1 (but more team members might be involved at different stages; and the CG may want to split this into several calls accordingly) | 53 | 3+ hours divided up in multiple interactions if needed |
| AMR Focal Point | 1 for HH 1 for AH | 20 | 1.5 hours |
| WOAH/GLASS Focal Point | 1 for HH 1 for AH (if different from above) | 24 | 1.5 hours |
| National Reference Laboratory (NRL) | 1 for HH 1 for AH (but more team members might be involved – typically the director and the AMR/microbiology lead). Also note that the NRL may be the same person as the AMR Focal Point | 13 | 1.5 hours |
| Fellows | Minimum 4 (at least one surveyor and one laboratory fellow for both sectors) or perhaps a focus group discussion with more. Note not active in Sierra Leone. | 16 | 1.5 hours |
| Policy Fellows | 2 (i.e. all). Note not active in all countries. | 18 | 1.5 hours |
| AMRCC members | 2-3 split between HH and AH | 18 | 1-1.5 hours |
| Other decision makers | 2-3 | 17 | 1-1.5 hours |
| DPs/ academia | WHO, FAO + other 1-2 depending on the country | 10 (20 for WHO) | 1 hour |
| Sites | 4 split between HH & AH | 13 | 2.5 hours |
| Total target | 15*-20 + site visits *Depending on whether we conducted a focus group discussion or separate interviews with the Fellows |  |  |

Interviews were semi-structured and based on interview guides. Best practice in research is to record and then transcribe the interview for analysis. This has advantages in that it produces greater transparency in what is said and allows the interviewer to focus on the interview and doing it well and guarding against bias. However, time and cost limitations mean that transcribing all interviews was not an option. The common strategy in evaluations in such situations is for the interviewer to write notes during the interview, and then use these to write up the interview. But there are considerable risks to validity in this strategy, especially for rich, semi-structured interviews. There is also no scope for transparency and review of what has been recorded, so its accuracy depends on how well the interviewer can simultaneously engage in an interview and take notes, the accuracy of their understanding of what is being said and their ability to overcome cognitive biases, such as finding it easier to remember things that fit with one's own views. To overcome this we adopted two strategies:

- Recording interviews (where permission from the KI was provided) and then writing up notes afterwards based on the recording. Written notes were also taken during this process as a backup in case of technical issues.

- Notes were made of important points and quotes made during the interview, but at the end of the interview, we took a few moments to go back through the notes with key informants, validating and confirming the correct understanding of the points raised.

KIIs lasted between 60 and 90 minutes, following verbal consent obtained at the start of each interview. We produced tailored KII guides that could be covered within this time, and which we reviewed and revised based on experience in the two pilot countries. However, as some KI categories were of such central importance to our data collection, it was necessary at times to ask for more of their time (either at once, or through repeated interactions). These categories included – CGs, MA RTs, Fleming Fellows. A shortlist of questions was developed according to each stakeholder prior to the interview, based on the allocation of country teams tweaked questions, and asked relevant probes based on existing gaps and needs of different thematic approaches.

    - Site visits

The country-level data collection incorporated a limited number of site visits (where COVID-19 restrictions did not prevent travel within a country or face-to-face meetings). The country teams worked with the CG in each country to identify the most appropriate sites to visit during country-level data collection, drawing on the criteria outlined below. The site visit included a tour of the facility, KIIs and photography of equipment, laboratory space and renovation work (including of equipment that is yet to be installed/does not fit specifications, if that was the case). The photos were included in the country visit debriefs.

Table 10 Criteria for selecting sites to be visited

Criteria for site visit selection

At least one HH and one AH surveillance site should be visited; ideally two or three for each sector. It may be preferable therefore to focus on sites where HH and AH are supported in the same location and sites that are easy to reach.

Sites that have received investment in either physical infrastructure/renovation or equipment; and or training.

Sites that have a Quality Manager in place

Sites that can be expected to have implemented Standard Operating Procedures (SOP)s developed through Fleming Fund support

Sites that have given examples of use at facility level

Global and Regional Grants analysis

Global and Regional Grants Document review

In addition to the country visits, data collection was also carried out at a global and regional grant level. Regional and global data collection consisted of document reviews and KIIs.

Documents were collated by Itad, working with the MA team. Research analysts (RAs) assigned to specific grants reviewed these documents and filled the coding workbook, according to the set codes.

The table below presents the grants that each review focused on.

Table 11 Direct and regional grants reviewed

| Direct Grants Review | Regional Grants Review |
| --- | --- |
| Commonwealth Pharmacists Association (CwPAMS) | Capturing Data on AMR Patterns and Trends in Use in Regions of Asia (CAPTURA) FF10 SA |
| WHO | CAPTURA FF11 SEA |
| Foundation of Innovative and New Diagnostics (FIND) | MAAP FF8 |
| WOAH | MAAP FF9 |
| Tropical Health & Education Trust (THET) | DTU Africa FF25 (WGS) |
| South Centre | DTU Asia FF64 (External Quality Assurance (EQA)) |
| FAO | Regional Antimicrobial resistance Data Analysis for Advocacy, Response and Policy (RADAAR) FF54 |
| Multi-Partner Trust Fund | Ending Pandemics FF49 |
| Overseas Development Institute | African Society for Laboratory Medicine (ASLM) Global FF60 (training) |
| Global Research on Antimicrobial Resistance (GRAM) | International Procurement Agent (IPA) FF70 |

The evaluation team reviewed over 104 documents as part of the global and regional grant document reviews. This included quarterly reports, annual reports and grant summaries as well as any synthesis done by the MA at the global level. The documents were coded, and relevant information extracted and used to complete analytical tools.

The table below shows the breakdown the number of documents reviewed per type of document.

Table 12 Number of documents reviewed per document type

| Type of document | Global grant documents reviewed | Regional Grants Review documents reviewed |
| --- | --- | --- |
| Quarterly Reports/Progress Reports | 31 | 52 |
| Annual Reports/Final Reports | 2 | 10 |
| Grant one-pagers | 7 | - |
| Six-monthly reports | 5 | - |
| Grant Agreements | 3 | - |
| Other/Miscellaneous (Grant Activity Summary, Meeting Minutes, …) | 16 | - |
| VfM | - | 75 |
| Total | 66 | 62 |

    - Global, Regional and Direct Grants KIIs

KIIs were conducted with key stakeholders at the DHSC and the MA as well as with RCs, HIs and a small number of DPs. The KIIs were conducted as per the country level KIIs, using a semi-structured interview protocol, recorded with the interviewee’s permission before being written up and coded.

Ensuring quality in the evaluation

Itad is a values-based organisation, and our Quality Assurance (QA) regime that monitors, measures and assures quality outcomes, which has evolved over the course of many evaluations is at the kernel of our core values of ‘making a difference’ and ‘technical excellence’. It has four stages: a) establishing quality ex-ante – engaging the right team, b) quality of the evaluation process – selecting and implementing the best evaluation design, c) quality of the end product – ensuring the timeliness and quality of all deliverables, and d) improving quality ex-post - securing feedback on the quality of the evaluation. This process also includes the assignment of an Itad Director to provide QA to the assignment, in this case Jon Cooper. QA will assure that the evaluation adheres to relevant standards.

Throughout the evaluation, we have called on key stakeholders, such as the evaluation’s own Evaluation Expert Advisory Group (EAG), the DHSC’s own Technical Advisory Group (TAG) and the DHSC project team to help assure and guide key elements of our work. We understand that the DHSC intends to utilise Evaluation QA and Learning Service (EQuALS), an external service established to deliver independent QA of certain Fleming Fund evaluation products. Itad is used to working within the EQuALS framework and welcomes this assessment process. To that end, the report has also been quality assured (QA’d) by senior advisor Paul Balogun, an EQuALS consultant.

Our evaluation design complies with established standards on ensuring quality in evaluations. The terms of reference (ToR) states that it is expected that the evaluation implementation and reporting will comply with the Organisation for Economic Co-operation and Development - Development Assistance Committee (OECD-DAC) quality standards for development evaluation. Our evaluation design is based on the use of qualitative evaluation methods. To ensure quality, we have therefore drawn on the approach to QA for qualitative evaluation developed by the Cabinet Office (2003) and cited in Stern et al (2012: 22). This framework is not substantively at odds with the OECD-DAC quality standards but is better tailored to use with evaluations using qualitative methods.

Table 13 Framework for ensuring quality in the evaluation

| Underlying concern | Ways of ensuring quality (examples) | What we have done |
| --- | --- | --- |
| The defensibility of the approach | A clear logic of enquiry | See Volume II Annex 3, and inception report |  |
|  | Clarity of questions posed | See Volume II Annex 3 and 4 (EQs) |  |
|  | Rationale for questions | See inception report |  |
|  | Responsiveness to real life context | See Volume I section 1 |  |
|  | Fitness for purpose | See Volume II Annex 17 |  |
| The rigour of conduct | Collection of in-depth data | See Volume II Annex 4 |  |
|  | Careful recording of data | See Volume II Annex 4 |  |
|  | Contextual documentation | See Volume II Annex 4 |  |
|  | Systematic and thorough analysis | See Volume II Annex 3 and Annex 4 |  |
|  | Explication of conceptual and analytic process | See Volume II Annex 3 and Annex 4 |  |
|  | Auditable documentation | See Volume II Annex 4 |  |
| The relationship of the researcher to the researched | Ethical behaviour (e.g. gaining consent) | See Volume II Annex 4 and Volume II Annex 12 |  |
|  | Involvement of participants in study | See Volume II Annex 4, Annex 12 and Annex 16 |  |
|  | Reflexive awareness of investigators’ role | The team has been selected for its skills and experience, as set out in Annex 14. Comprehensive training will be provided as required. |  |
|  | Open and empathetic fieldwork skills | See Volume II Annex 4 and Volume II Annex 12. |  |
|  | Recognition of different subjective perspectives. | See Volume II Annex 4 and Volume I section 1.3. |  |
| The credibility of claims | Triangulation | Findings presented have been fully triangulated at different levels. Findings from country visits have been generated by triangulating evidence across documents reviewed, and different categories of stakeholders interviewed. They have also been refined and validated through country level debriefings involving the DHSC and the MA. Evidence from country visits have then been triangulated with information from global and regional level document reviews and KIIs through multiple analysis workshops with the wider team. |  |
|  | Validation by informants/respondents | See Volume II Annex 4 |  |
|  | Peer review | See Volume II Annex 16 |  |
|  | Consideration of alternative explanations and negative cases | See Volume I section 2 |  |
|  | Balanced presentation of evidence | See Volume I section 2 |  |
|  | Demonstrating links between data and conclusions | See Volume II Annex 21 |  |
| The broader contribution of the study | Relevance and utility to policy | The entire evaluation has been conducted with a utilisation focus, meaning that primary intended users have been involved at key stages to maximise their ownership of the process and the results of this evaluation. Conclusions and recommendations have been formulated with relevance and utility in mind. |  |
|  | Ongoing involvement of potential users in planning and discussing recommendations | See Volume II Annex 17 |  |
|  | Timeliness | See Volume I section 1 and Volume II Annex 17 |  |
|  | Clear reporting and active dissemination | See Volume II Annex 17 |  |
|  | Linking findings to broader research and theory | See Volume II Annex 7, Annex 8, Annex 9, Annex 10 and Inception report. |  |

We note that the above framework is not explicit on requirements for disaggregation. This is of relevance to understanding differences between countries and between sectors, and we have ensured that implementation and results are collected separately for human, animal, and other sectors where relevant.

- Annex 5: Mapping of evaluation questions to report sections

| Evaluation Question | Report Section/s |
| --- | --- |
| EQ1 What has been the increase in the quantity and/or quality of data on AMR at country level and to what extent has the Fleming Fund contributed to this increase? | Executive Summary and sections: 2.1, 2.1.2, 2.1.3 |
| EQ2 To what extent have the Fleming Fund's investments been aligned and coherent with other relevant investments at country level? | Executive Summary and section: 2.3.2 |
| EQ3 How likely are the Fleming Fund's country level results to be sustained? | Executive Summary and section: 2.3.1 |
| EQ4 Has, or is it likely that, the increase in AMR data influenced: (a) changes in national policies/regulations?; and/or (b) changes in practice and attitudes in country? | Executive Summary and sections: 2.2, 2.2.2, 2.2.3, 2.2.4, 2.2.5, 2.2.6, 2.2.7, 2.2.8 |
| EQ5 What has been the increase in quality data shared and reported internationally and has the Fleming Fund contributed to this? | Executive Summary and sections: 2.1, 2.2, 2.2.4 |
| EQ6 Did the Fleming Fund's investments at country level offer VfM? | Executive Summary and section: 2.3.2 |

- Annex 6: Value for money

Background

Investing in AMR Surveillance is one of 10 cost-effective solutions recommended to tackle drug-resistant infections globally. As part of a broader response to the global health threat of AMR, the Fleming Fund Grants Programme is the UK investment in strengthening surveillance systems. Although there is a clear return on investment for reducing AMR, the benefits of investing in strengthening AMR surveillance systems are less easily quantified and valued. This is in part due to the type of intervention and when and where benefits are realised. Benefits from investing in stronger systems result over a longer timeframe and contribute to health outcomes through service delivery. Benefits from investing in health systems’ resilience and response to global health threats are also realised globally as well as locally. Therefore, our approach to evaluating the VfM of the Fleming Fund is not based on a cost-benefit analysis (one was not included in the economic case for investing in this programme). We have applied the UK NAO 3E framework to review VfM. Our approach looks at what the Fleming Fund has delivered in terms of VfM (measurement) as well as how well resources have been managed to achieve impact (management).

Findings

DHSC and MA’s approach to VfM

The DHSC and the MA considered VfM from the outset of the programme. RfPs included a requirement for grantees to include their approach to VfM in the grant proposal. The MA also developed an approach to VfM, which was revised twice during implementation and rolled out across the grants. A literature review of common practice in VfM in grant management, as part of our first evaluation deliverable (January 2019), enabled us to benchmark the MA approach to VfM with best practice. During the grant period, the MA continued to refine their approach to VfM (updating their Approach document twice) and implement the approach at the grant level.

Grantee quarterly reporting templates included a section on VfM (and Sustainability) in which grantees give examples of VfM. Over the implementation period, there has been a shift away from reporting economy examples to including efficiency and effectiveness, though almost all the examples remained qualitative. Whilst training was conducted with RTs and cascaded to the country level, there has been an evolution of grantees’ understanding of VfM, reflected in more examples of efficiency and effectiveness in the quarterly reports. However, this was not seen in the HIs for Fleming Fellows where VfM was equated with cost savings. At the same time, there was a high level of buy-in to the Fleming Fellows by HIs demonstrated by their willingness to invest their own resources in the scheme, indicating their recognition of its value.

During implementation, VfM Grant Reviews were undertaken. These combined VfM metrics (e.g. tracking unit costs of inputs; budget and activity implementation rates; overhead; gender split of grantee team) with narratives (explanations of performance against metrics; examples of adaptive management) and presented a RAG rating against the 4E’s together with recommendations for the Grantee, the MA and the DHSC. Whilst the reviews enabled the tracking of VfM against a standard set of indicators, the reviews were limited in scope and did not go into detail about what was being delivered in terms of outputs, the quality of the outputs, or the value of outputs and outcomes compared with the investment. The Fleming Fellows did not have VfM Reviews and the quarterly reporting template did not include VfM.

Reporting on VfM by the MA to the DHSC included a summary of the RAG rating across all grants. This provided a snapshot rather than continuous tracking of VfM given that the grant reviews were usually conducted twice (once during implementation then updated at the end of the grant). 14 out of 16 CGs and all the RGs undertook at least one VfM Grant review, based on the VfM reports available. The Fleming Fellows have not established VfM measures and reporting. The processes they had in place to manage VfM did not focus on the input and work plan completion level, and there has not been any analysis of common indicators such as unit cost per fellowship, as seen in other similar programmes. There is a risk therefore that the Fleming Fellows focus too much on economy, at the risk of efficiency and effectiveness. For example, the VfM discussion focuses on capped rates for per diems, rather than how the fellowships can contribute more cost-effectively to improving the quantity, quality, and use of AMR surveillance data in a sustainable way.

Have DHSC and MA managed for VfM at country level?

Economy

At the grant proposal stage, and during the no-cost extension process, there is evidence across CGs and RGs that unit costs were reviewed and, in some cases, challenged and revised. This was as a result of the MA reviews as well as feedback from the DHSC. For example, the DHSC provided input and feedback on overhead costs  and costs of personnel  at the grant proposal stage. Once budgets were agreed and in place, unit costs were reviewed during VfM grant reviews (i.e. once during implementation). See Table 15 for the summary of performance against tracked unit costs. There is less evidence that unit costs were benchmarked systematically across the grants; and there is evidence that, during the grant review process, unit costs were compared across the submitted proposals .

In some cases, tracking unit costs of inputs (not including procurement of laboratory equipment and consumables) revealed that budget unit costs were much higher than actual costs e.g. RG FF10/11. (See Table 14 below for example from a RG). Budgeted costs for most inputs were higher than actual costs in most countries. Whilst this may demonstrate economy in terms of lower costs of inputs, it had an impact on budget absorption rates. There were also examples  where a few unit costs were higher than had been budgeted (see Table 15Table 15 VfM Measures of Economy achieved across country grants for analysis of tracked unit costs).

Table 14 Example of overbudgeting in RG FF10/11

| Tracked cost items | Budgeted cost | Actual cost | % Variation |
| --- | --- | --- | --- |
| Epidemiologist, M&E specialist (Public Health Surveillance Group (PHSG)) FF10 | £2,504/month | £1,787/month | +28% |
| Software engineer/Interface developer (WHONET) FF10 | £3,126/month | £1,648/month | +47% |
| BWH PI, John Stelling (WHONET) FF11 | £2,624/month | £1,683/month | +36% |
| BDI Primary Investigator FF11 | £2,335/month | £560/month | +76% |
| PHSG Administrative Support FF11 | £850/month | £656/month | +23% |
| Laptop BDI FF11 | £748 each | £646 each | +14% |
| IVI Office supplies FF11 | £37/month | £60/month | -62% |

Financial management processes have been used to control costs and allowable expenditures. Examples of such financial processes included a review of quarterly work plans and budgets with the MA to approve allowable expenses and assess alignment with the overall work plan. At the end of each quarter, expenditure review and variance analyses were also conducted by the finance team for each CG using already-developed templates. Some grantees reported templates as initially difficult to use but most grantees received training and support to use over the period of the grant. An exception to this was Laos where the CG was WHO and had different financial reporting systems and therefore did not provide quarterly reports using the MA’s financial reporting templates. In general, it is harder for United Nations (UN) agency grants to report in the templates due to the lower level of detail provided in their financial reporting. This means limited grantee data on Sierra Leone HH (WHO), Sierra Leone AH (FAO), Senegal AH (FAO), Laos CG1 (United Nations Office for Project Services (UNOPS)) was available for VfM analyses.

The quarterly monitoring led to well-managed grants where expenditure was aligned to the work plan, which itself was based on the country NAP. Phase 2 plans to continue and strengthen reviews of allowable expenses. However, focusing the quarterly work plan and budget reviews reporting (both implementation and financial) at activity level mostly risks funds being spent on inputs and activities without linking these to the grant outputs and outcomes. Some grantees agree with this level of control, others find it too restrictive. It also focuses the level of adaptive management at the work plan activity level to maintain budget absorption rates rather than adapting activities to course correct at the outcome level.

Each CG had a procurement budget for purchasing equipment and consumables for laboratories and laboratory renovations. There were two streams for procurement – central procurement by IPA as the international procurement across the CGs and RGs, as well as local procurement led by the CGs in partnership with the government. For the local procurement, many countries set up processes such as prequalification of local vendors, and competitive bidding/tendering for the selection of best prices and quality. For central procurement, each CG conducted site visits to identify the required renovations and develop procurement catalogues detailed with the required specifications for each site.

Due to the COVID-19 pandemic, among other factors, site reports indicated delays in procurement and installation of equipment across most sites. Trainings and capacity building sessions were also put on hold at first during the pandemic but later conducted virtually. This introduced some lag in implementation in many countries. Other than the delays (which have impacted the pace of programme implementation – see Efficiency or other sections in report) there is general satisfaction with procurement. However, there are cases of potentially unsuitable equipment and concerns about the quality and suitability of supplied equipment. These have been raised in some sites, notably Kenya, Nepal and Uganda. Concerns were also raised in some sites on the availability of comprehensive insurance cover for maintenance and sustainability.

Opportunities to benefit from economies of scale were not always taken, for example resulting in Fleming Fellows purchasing their own reagents rather than benefitting from access to supplies purchased through the CG arrangements or other pooled procurement with lower negotiated prices. This is an opportunity for greater coordination and coherence being considered in phase 2.

Efficiency

The MA put in place processes to support grantees to deliver planned activities on time and within budget. All CGs and RGs were set up with comprehensive work plans, which themselves were based on RfPs. CGs reported rigorous activity tracking systems in place consisting of quarterly reports based on templates provided by the MA as well as quarterly review meetings with the global team, weekly or biweekly review meetings at RT level , and monthly at CG level .

There was also evidence of flexibility in work plan implementation where quarterly work plan review with the RT led to fund reallocation and deprioritisation of unnecessary activities. Where the initial RFP work plan did not fit with the needs and current situation in the country, work plans and budgets were adapted during implementation. This often happened to ensure the work plans and budgets were well-suited to the current realities in the country, and to eliminate unnecessary activities . In addition, between May 2021 and September 2022, 45 CGs and RGs were extended. Most of these (39) were no-cost extensions, demonstrating how unutilised budgets were reprogrammed and delays in implementing activities were addressed.

Cost-savings were identified and reallocated to other activities during implementation. This happened on a quarterly basis for many CGs, and in the cases of some RGs, as part of the implementation of recommendations from the VfM review. A strict caveat was noted for the quarterly reallocation and use of cost-savings – operational costs could not be reallocated to management costs.

Delays occurred at various points during the grant lifecycle but there were notable delays that seemed common to most grantees – first, many CGs reported delays in the commencement of grant implementation. This was often due to lengthy grant kick-off processes. Secondly, there were also delays during implementation specifically for laboratory-dependent activities where COVID-19 slowed down the procurement of necessary equipment. In addition to the pandemic, slow buy-in from government stakeholders also delayed kick-off activities.

Monitoring and tracking of output level results took place during the annual review process, although this was largely a qualitative exercise. In addition, due in part to the delays in implementation and also due to resource constraints, annual reviews were usually conducted only once during grant implementation.

Risk management processes are in place. A risk matrix was updated on a quarterly basis and RTs worked with CGs to review and mitigate the risks each quarter. Some of the risks identified on a quarterly basis included issues around buy-in from government stakeholders and bureaucracy, as well as challenges with the poor capacity of staff at the laboratories. Many of these risks were managed via multiple advocacy activities and training events. Whilst most grants seem to be managed well in terms of risk, it was notable that some grant risk registers did not identify and track key risks such as the procurement (of laboratory equipment and consumables) delays which were a significant factor in implementation delays and slowed progress towards achieving improved quantitative and qualitative AMR data.

A key driver of VfM was the grantees’ or HIs’ existing processes and policies. For example, we saw examples of stronger efficiency where grantees had less bureaucratic processes, stronger relationships with the government and non-government stakeholders as well as stronger institutional AMR technical capacity. For economy however, CGs with already existing programmes and alliances such as WHO could achieve greater leverage of already existing resources. This was similar for Bhutan where the grantee was the Royal Government of Bhutan and this led to use of government resources during implementation. A balance was recommended during annual reviews where more technical (and nimble) partners were included to support the implementation of the grants. For HIs, the cost of mentors depended on the costing regime or the established rates of the institution e.g. whether a mentor was paid a stipend or as an independent consultant.

It is not clear (November 2022) to what extent these issues are addressed by the MA for phase 2 as we have not yet seen the implementation plan for phase 2.

VfM Measures

Economy

CGs have demonstrated good VfM in terms of economy. This is based on the assessment of two VfM measures: (1) Cost-savings achieved and (2) Selected tracked unit cost of inputs (actual vs. budget). These measures are sourced from the VfM Grant reviews, apart from Senegal and Sierra Leone where VfM savings are sourced from quarterly reports and there is no evidence (NE) of routinely tracked unit costs.

Table 15 VfM Measures of Economy achieved across country grants

| VfM Savings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Unit cost of inputs tracked |  |  |  |  |  |  |  |  |  |  |  |  | NE | NE |  |

Table 16 VfM Measures of Economy achieved across regional grants

| VfM measures Economy | FF8 FF9 | FF10 FF11 | FF49 | FF55 | FF64 | FF54 | FF25 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| VfM Savings |  |  |  |  |  |  |  |
| Unit cost of inputs tracked |  |  |  |  |  |  |  |

Table 17 Rubric for VfM Measures of Economy

| RUBRIC | Green | Amber/Green | Amber/Red | Red |
| --- | --- | --- | --- | --- |
| VfM Savings | Savings documented and value estimated. Estimated value equates to >3% of programme expenditure | Savings documented and value estimated. Estimated value equates to <3% of programme expenditure | Savings documented but not valued. | No savings made (NB if not documented note as NE rather than Red rated |
| Unit costs | All tracked unit costs within 10% of plan (or below) | >50% of tracked unit costs within 10% of plan | <50% of tracked unit costs within 10% of plan | All tracked costs above 10% of plan |

Six out of 15 CGs achieved and reported cost-savings from planned expenditure that were equivalent to at least 3% of the grant value while five other countries recorded cost savings but less than 3% of the total cost. For RGs, all seven RGs reported significant cost-savings ranging from £53,531 to £239,916 with the proportion of expenditure saved ranging from 4.3% to 46.9%. Cost savings were achieved through various strategies such as sharing costs for training activities, meetings and other events with other partners, and use of government-owned spaces for teaching and training events and as offices, the unintended COVID-19 effects where grantees switched to virtual meetings and training thus reducing travel costs, the use of local trainers rather than international ones; requesting waivers on import duty for procured equipment.

In terms of the comparison of unit costs to budgeted costs, eight of the 16 CGs had all tracked unit costs within 10% of planned costs or below. In many cases, the actual cost of the input (e.g. staff salary, travel costs) were significantly below budgeted costs thus indicating the unit costs were not realistic or sufficiently benchmarked during the budget and proposal review process. (See

Table 16) These resulted in cost savings that were reprogrammed from quarter to quarter, where required.

Savings were identified through central procurement negotiations. Overall the estimated savings through central procurement reported by the MA were €2.73 million. Of which, €2.06 million is through the central procurement of mass spectrometry instruments.

Efficiency

In a few countries, overheads (budget and actual) are higher than in similar grant programmes. The value of actual overhead costs ranged from as low as 6% to as high as 62% . (See Table 18). The range can be due to the way the definition is applied and also the differences in the way the grants were structured and their financial systems. Overheads are defined as ‘IDC’ indirect costs which cover the grantees’ overhead costs i.e. a portion of their operating costs, and ‘management and overhead expense’ (M&OH) that is directly attributable to the grant such as personnel (Project Managers/administrators/finance staff/etc) and expenses (office costs, rent, etc). For RGs, overheads range from 7% (FF8/FF9) to 19% (FF10/FF11). During the proposal review and grant processes, selected grantees received feedback on high overhead costs from the DHSC and MA. In terms of actual overheads, these became higher than expected due to implementation delays. For example, salary costs for programme staff even though the implementation of laboratory-related activities and engagements with government stakeholders were on hold due to the COVID-19 pandemic.

Table 18 Budgeted and Actual Overhead costs in CGs

| Proportion of overhead costs | Bangladesh | Bhutan | Indonesia | Laos | Nepal | Pakistan | Timor-Leste | Vietnam | Ghana | Kenya | Tanzania | Nigeria | Senegal | Uganda | Zambia |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Budgeted (%) | # 9.2 | # 6.3 | # 14 | # 12 | # 6 | # 34 | # 27 | # 16 | # 27 | # 12 | # 49 | # 10 | # NA | # NA | # 27 |
| Actual (%) | # 62 | # 6.3 | # 21 | # 8 | # 20 | # 32 | # 34 | # 33 | # 16 | # 7 | # 61 | # 11 | # NA | # NA | # 14 |

Activity and budget implementation rates reveal the greatest variation across CGs, and within countries, variations also existed among activity implementation, budget use, and output seen. For example, some countries achieved increased quantity and quality of data even though activity and budget implementation rates were off track (see  Table 19 below). It is therefore more of an indicator of how well grantees are planning and managing resources at the input and activity level, rather than a measure of efficiency defined as how well inputs are converted to outputs.

There is some evidence that the value of leveraged resources is reasonably significant (£7,310 – £398,195 ), although these have not been reported or consistently tracked across all grants. This occurred when CGs leveraged already ongoing activities within the health system, either government-led or partner-supported, to complete programme activities. This indicator helps to demonstrate alignment with existing resources and whether grants are set up taking account of other programmes operating in the same area. It may also indicate sustainability if resources leveraged are from the country’s existing health budgets and could be included as indicators to track at the CG level in a systematic way, during phase 2.

Table 19 VfM measures of efficiency

| VfM measures Efficiency | Bangladesh | Bhutan | Indonesia | Laos | Nepal | Pakistan | Timor-Leste | Vietnam | Ghana | Kenya | Tanzania | Nigeria | Senegal | Uganda | Zambia |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Percentage of overhead |  |  |  |  |  |  |  |  |  |  |  |  | NE | NE |  |
| Activity/budget implementation rates |  |  |  |  |  |  |  |  |  |  |  |  | NE | NE |  |
| Value of leveraged resources | NE | NE | NE |  | NE |  |  |  |  |  | NE | NE | NE | NE | NE |

Table 20 VfM Measures of Efficiency achieved across regional grants

| VfM measures Economy | FF8 FF9 | FF10 FF11 | FF49 | FF55 | FF64 | FF54 | FF25 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Percentage of overhead |  |  |  |  |  |  |  |
| Activity/budget implementation rates |  |  |  |  |  |  |  |

Table 21 Rubric for VfM Measures of Efficiency

| RUBRIC | Green | Amber/Green | Amber/Red | Red |
| --- | --- | --- | --- | --- |
| Percentage overhead | Budget and actual overhead costs are below 12.5% | Actual overhead between 12.5% and 25% and budget is at or below 25% | Actual overhead between 25% and 50% and/or budget is over 25% | Actual overhead above 50% and budget is over 12.5% |
| Activity and budget implementation rates | Activity implementation rate above 60% and budget implementation rate above 60% | Activity implementation rate between 40-60% and budget implementation not higher than 60% | Activity implementation rate between 40-60% and/or budget implementation higher than 60% | Activity implementation rate below 40% and/or budget implementation rate higher 40% |
| Value of leveraged resources | Resources leveraged have been estimated and equates to >5% of programme expenditure | Resources leveraged have been estimated and equate to <5% of programme expenditure | Resources leveraged have been documented but not valued | No resources leveraged (NB if not documented note as NE, rather than Red rated) |
| Outputs have been achieved as expected: Evidence of increased quantity and quality of AMR data | Increased quantity and quality of AMR data for AH and HH (where Fleming Fund has made a contribution) | Increased quantity and/or quality in AH and/or HH (where Fleming Fund has made a contribution) | No or modest increase in quantity and/or quality in AH and/or HH (where non-programme related factors explain) | No or modest increase in quantity and/or quality in AH and/or HH (where programme related factors explain) |
| Percentage overhead | Budget and actual overhead costs are below 12.5% | Actual overhead between 12.5% and 25% and budget is at or below 25% | Actual overhead between 25% and 50% and/or budget is over 25% | Actual overhead above 50% and budget is over 12.5% |

A fifth indicator was planned to examine the unit cost per Fleming Fellow, but data is not available either on the total number of Fleming Fellowships completed or the expenditure. VfM reporting was not set up for Fleming Fellows. A key indicator used by similar fellowship programmes is the leveraging of resources, but systems were not set up to track this though there was evidence from KIIs that HIs were contributing resources, and this was seen as an indication of the value they placed on the scheme.

Due to the way the MA tracks and reports efficiency (at the activity level), it is hard to establish how well the grants at the county level have achieved VfM in terms of efficiency. We have also reviewed qualitative evidence of efficiency to summarise some key findings here (Box 1).

- Box 1 Key findings on Efficiency - Cost-savings could be and were reallocated and reprogrammed on a quarterly basis. This became a lot more important during COVID-19 when funds were freed up from training and travel. - The RT and, to an extent, the global team provided guidance, training and close oversight for efficient activity implementation in many of the countries. There is evidence of weekly, biweekly, or monthly problem-solving sessions and programme update meetings to support the CGs to get on track with their implementation targets. - Risks were identified at the start of the contract and were updated every quarter in reports to the RT and the MA.

Effectiveness

There is evidence of the involvement of country-level stakeholders in the design and implementation of grants (CGs and RGs) and alignment with NAPs in some of the countries. Also, needs assessments were completed before the onset of the grant. In Ghana and Vietnam, a multidisciplinary team made of policy, academic experts, and chief scientific officers participated in the grant design.

Countries have made varying progress with data sharing – HH AMR data to GLASS and AMU data to WOAH, with more countries having achieved improved sharing of HH AMR data to GLASS rather than AMU to WOAH.

Table 22 VfM measures of effectiveness

| VfM measure Effectiveness | Bangladesh | Bhutan | Indonesia | Laos | Nepal | Pakistan | Timor-Leste | Vietnam | Ghana | Kenya | Nigeria | Senegal | Sierra Leone | Tanzania | Uganda | Zambia |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evidence of increased quantity and quality of AMR data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evidence of data use/ in GLASS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| RUBRIC | Green | Amber/Green | Amber/Red | Red |
| --- | --- | --- | --- | --- |
| (intermediate) Outcomes have been achieved as expected: Evidence of data use/in GLASS | HH AMR data to GLASS has advanced and AMU data sharing with WOAH has advanced | HH AMR data to GLASS has advanced or AMU data sharing with WOAH has advanced | HH AMR data to GLASS and AMU data sharing with WOAH have not advanced (where non-programme-related factors explain) | HH AMR data to GLASS and AMU data sharing with WOAH have not advanced (where programme-related factors explain) |

Managing for effectiveness. During the early stages of implementation, the evaluation highlighted issues related to how the programme had been set up to manage results at the (intermediate) outcome level. This has been a recurring theme throughout the evaluation and has formed a key part of learning and adaptation in relation to VfM. Several steps have been taken during implementation to address these issues. The MA undertook a VfM Deep Dive into Managing for Effectiveness in 2020 which identified the mechanisms in place (formal and informal) to manage results. Whilst many of the findings and recommendations have not been addressed during phase 1, some are being considered for implementation in phase 2. For example, agreeing on output level indicators and focusing monitoring at the output (rather than activity) level and formalising a Monitoring, Evaluation and Learning strategy. There are other recommendations which have not yet been implemented and would strengthen the MA’s approach to tracking and delivering VfM such as an output quality review framework to ensure a standard approach across grants; and including outputs within the grants for government commitments/budgeting for procurement of reagents, consumables and maintenance and implementing. The Managing for Effectiveness VfM Review also included a review of progress through the ToC in four case study countries which presented performance on outputs and quality of outputs in a level of detail not seen in the quarterly and annual reviews.

The evaluation used available data to form a summary overview of effectiveness based on contribution analysis, as an input to the VfM analysis. Headlines from this analysis are presented in Volume I. Supporting data is presented below:

Overall there is evidence across the 16 countries in our sample that the Fleming Fund has contributed to improvements in establishing surveillance systems and data use.

| VfM Sub-Question | VfM measurement | Tanzania | Kenya | Nepal | Bhutan | Uganda | Timor-Leste | Zambia | Bangladesh | Pakistan | Laos | Vietnam | Ghana | Indonesia | Nigeria | Senegal | Sierra Leone |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evidence of increased quantity and quality of AMR data | Increased quantity HH with Fleming Fund contribution | 8 | 8 | 8 | - | 8 | 2 | 8 | 4 | 4 | 4 | 4 | 2 | 4 | 1 | 1 | 2 |
|  | Increased quality HH with Fleming Fund contribution | 8 | 8 | 6 | 8 | 4 | 8 | 3 | 4 | 6 | 3 | 6 | 6 | 3 | 4 | 2 | 1 |
|  | Increased quantity AH with Fleming Fund contribution | 4 | 8 | 8 | 3 | 4 | 3 | 4 | 6 | 4 | 8 | 4 | 4 | 4 | 1 | 6 | 1 |
|  | Increased quality AH with Fleming Fund contribution | 8 | 8 | 4 | 8 | 6 | 8 | 3 | 6 | 3 | 2 | 4 | 2 | 0 | 4 | 1 | 0 |
| Evidence of data use/ in GLASS | HH AMR data to GLASS advanced with Fleming Fund contribution | 8 | 3 | 8 | 8 | 4 | 4 | 3 | 0 | 4 | 3 | 1 | 0 | 4 | 2 | 1 | 1 |
|  | AMU data sharing with WOAH advanced with Fleming Fund contribution | 8 | 8 | 4 | 6 | 3 | 0 | 4 | 4 | 2 | 2 | 2 | 2 | 0 | 1 | 0 | 2 |

Table 23 Country grant rating based on the change from baseline and contribution analysis rubric scoring matrix

|  | Contribution | 3 or more | 2 or less | None |
| --- | --- | --- | --- | --- |
| Change from baseline |  | 2 | 1 | 0 |
| Considerable | 4 | 8 | 4 | 0 |
| Some | 3 | 6 | 3 | 0 |
| Limited/Not Clear | 2 | 4 | 2 | 0 |
| Not yet | 1 | 2 | 1 | 0 |
| Negative | 0 | 0 | 0 | 0 |

In principle, we can look at investments compared with change (as per contribution analysis) given the MA or grantee financial reporting is set up to record costs under investment areas and these can be mapped to contribution analysis results and drivers.

Table 24 Mapping of investment areas to contribution analysis drivers

| Investment areas | Contribution Analysis result areas | Main Contribution Analysis drivers | Other Contribution Analysis drivers that may be linked but not included in analysis due to n |
| --- | --- | --- | --- |
| Foundation building – AMR surveillance data use | C3, C4, C5 |  |  |
| Human resource strengthening + work force reforms | C1a, C1b, C2a, C2b | Human capacity | (Supervision) |
| Laboratory infrastructure enhancement | C1a, C1b, C2a, C2b | Renovation and Equipment | (Consumables) |
| Systems development (surveillance) | C1a, C1b, C2a, C2b | Governance (data sharing) | (SOPs QA) |
| Rational use of antimicrobial medicines | Not mapped | Not mapped |  |

In practice, there are some limitations to this analysis.

- The high proportion (45%) of CG investments recorded as cross-cutting and not assigned to a specific investment area (ranges from 10% to 70% across CGs). Cross-cutting investments are programme delivery costs which cannot be allocated to an investment area, e.g. positions such as One Health Specialist. Overheads range from 3% in Bhutan to 44% in Nigeria (see Figure 8 below).

- Not all contribution drivers can be mapped to an investment area, so we look only at the main drivers; Human capacity, Renovation and Equipment, and Governance which can be mapped to investment areas. Therefore, we only assess the overall alignment of investment in areas with contribution analysis drivers and identify and explore outliers (e.g. where the level of resources invested is high compared to how the contribution driver was perceived or where the contribution perceived is high compared with the resources invested). Figure 9 displays expenditure by investment area from the start of implementation to the end of June 2022. It excludes all cross-cutting costs and only shows expenditure in the five investment areas.

Figure 8 Fleming Fund Country Grants Expenditure September 2019 to June 2022 by budget category (Source: Management Agent)

Figure 9 Fleming Fund Country Grants Expenditure September 2019 to June 2022 by investment area (Source: Management Agent)

In general, we found that there was a high degree of alignment between the level of investment and the strength of drivers for change in data availability. We compared the levels of expenditure by investment area with the contribution drivers reported. In general, we found alignment between the level of investments and the strength of drivers: for example, in countries where there was a higher level of investment in laboratory infrastructure, renovation was one of the stronger drivers.

In general, investments are also aligned with performance in terms of data sharing and use.  We compared the level of investments under Foundation building – AMR surveillance data use with performance assessed through contribution analysis. We found that there was lower investment in countries that reported less progress/Fleming Fund contributions and higher performing countries had relatively higher investment in this area.

Investments in the rational use of antibiotics were very low overall in most countries except Pakistan and Vietnam.

- Annex 7: One Health

Background

One Health is an approach to develop a multisector response to infectious disease challenges such as AMR, zoonoses and emerging infections that involve multiple species groups and sectors. Given the role of animal, environment as well as HH sectors in controlling the problems of AMR, global health agencies had labelled AMR as an ‘entry point’ for demonstrating the effectiveness of One Health approaches from the early days of the One Health movement. Accordingly, Fleming Fund had identified One Health as one of the four principles (phase 1) for its operationalisation in its Implementation plan.

As this document describes below, even though there was a strong impetus for fostering multisector One Health partnerships around AMR at the time the Fleming Fund started, there was limited practical guidance around how to successfully operationalise One Health in different country contexts – something that the international agencies have only now started to address, as demonstrated in the objectives of the recent world Health Assembly resolution on One Health.

The last five years have witnessed a changing landscape of global partnerships around One Health governance globally. For instance, the WOAH-FAO-WHO tripartite has now expanded its leadership to include the United Nations Environment Programme and a stronger acknowledgement of the environment sector. This has been accompanied by the development of a more structured approach to implementing One Health across different country contexts, as evidenced by the development of the Tripartite Zoonoses Guide and related tools.

The landscape of One Health discourse was changing externally, accompanied by a parallel set of reflections on the importance of the country context within the Fleming Fund. The practical experience of operationalising One Health across 23 different countries that spanned a wide range of technical capacities and administrative cultures helped refine its understanding of and expectations from a One Health approach, as described in Figure 10 and Figure 11 below.

The changes in expectations from a One Health approach were also reflected in the focus of the evaluation. The evaluation scope changed from mapping existing institutional modes of One Health in Country Visit 1 (2019) to characterising the diversity of partnerships in Country Visit 2 (2020-21) to identifying spaces for multisector dialogues that could improve cross-sector decision making in Country Visit 3 (2022) (see Figure 14).

The main findings from the different phases of the evaluation, as well as their relevance for the next phase of Fleming Fund activities, are discussed below. To give a quick overview of the structure of this Annex, we discuss the EQs posed across the three sets of country visits. We then describe the key findings, including the situation in 2018 as well as the progress made across 16 countries. Lastly, we identify the variations in country performances and the possible reasons.

Evaluation question

Starting position: What is One Health

The first set of clear statements on One Health in the context of the Fleming Fund were included as an Annex in the Fleming Fund implementation plan (June 2017). According to the implementation plan, One Health was centred around three principles. The first two, leadership and collaborative structures and integrated surveillance, were expected to lead to the third principle – evidence-based policies.

This approach to One Health was, in turn, informed by a 2008 WHO guidance on establishing One Health in member countries as well as the GLASS roadmap paper. The notable features of the WHO guidance and the roadmap paper – also replicated in the Fleming Fund statement – were twofold. First, One Health was understood as a single standardised model of collaboration, which envisioned One Health discussions taking place between representatives of different government agencies around a common goal of health protection. Secondly, this understanding of One Health assumed the presence of One Health to be binary; either it was present in a country or it was not (see Figure 10 below).

Figure 10 One Health partnerships in Fleming Fund- Implementation Plan (June 2017)

Evolving approach to One Health and its evaluation

The experience of operationalising the Fleming Fund’s One Health strategy across a wide range of countries and institutions somewhat altered the rigid approach to One Health that was in place at the start of phase 1. The experiences from different Fleming Fund countries, as reflected in Country Visit 1 findings, helped the Fleming Fund determine that a standardised one-sized approach to One Health partnerships would not account for local political and bureaucratic realities and so was not likely to work in different countries.

While Country Visit 1 took place at a very early stage in the programme cycle even as many of the contractual processes were being finalised, the difficulties in the countries’ adoption of the AMRCC-style institutional mode of collaboration showed that there is no single formulation of the One Health approach – different countries are likely to reconfigure their own modes of fostering institutional collaboration. It could take the form of super-ministries to broker partnerships – as in the case of Indonesia, or the use of existing social networks to promote discussions across agencies, as in the case of Timor-Leste. Alternatively, the head of government’s office could be the one to call meetings – as in the case of Tanzania.

These different forms of institutional partnerships emerging in different countries led the Fleming Fund MA to develop a graded approach to One Health, first advanced in a 2019 position paper (depicted in Figure 11 below). This approach conceptualises multisector collaborations along a gradient where successive stages of One Health lead to closer working which, in turn, is assumed to lead to better exchange of information and increased evidence-informed decision making.

Figure 11 MA Position paper on assessing One Health Implementation (September 2019)

While this approach was useful in developing a more nuanced understanding of the different levels of data sharing (and use) taking place, for the purpose of the evaluation, we wanted to identify some of the underlying dynamics which would have influenced the different levels of performance of One Health partnerships in different countries.

As noted above, because of the relative novelty of the One Health concept, there was limited literature around evaluating multisector One Health partnerships and or even characterising different kinds of One Health partnerships. Therefore, the Itad team conducted a literature review which helped us think about how to define, characterise multisector partnerships, and identify ‘success’ in One Health.

We found that multisector One Health partnerships can be characterised based on different qualities, such as scale, scope of functioning, degree of formality practised as well as strength of integration (Figure 12 and Figure 13). Incorporating these additional ways of classifying One Health helped us find additional information about the diversity and functioning of One Health partnerships in Country Visit 2 and Country Visit 3, discussed below.

Figure 12 Other ways of characterising One Health partnerships (Itad literature review)

Figure 13 Characterising One Health partnerships, by strength of integration (Itad literature review)

Evaluation questions and approach

As depicted in Figure 14 below and explained earlier in Annex 3 our approach to the evaluation changed over time. During Country Visit 1, One Health was first integrated with Use questions and we aimed to examine the presence and absence of institutional One Health mechanisms (such as the AMRCC and the Technical Working Group (TWG), etc.) across different countries based upon the framings of GAP and LSHTM GLASS frameworks.

Country Visit 2 took place in 2020-21 and we used it to apply the MA and Itad categorisations to assess the different stages of One Health in different countries. Importantly, our questions were framed around the likely trajectory of the Fleming Fund and One Health, and we asked national actors where they predicted the Fleming Fund to be headed by the end of the project.

During Country Visit 3, we revised the EQs slightly. Instead of merely probing the presence or absence of One Health (Country Visit 1), or stages/levels of One Health (Country Visit 2), we started exploring the different ways and spaces within which One Health partnerships were active. This included probes on non-formal spaces. The purpose of these questions was supposed not only to make a summative judgment on One Health, but also to identify potential areas for One Health efforts to develop in a second iteration of One Health.

Figure 14 Approach to evaluating One Health across different country visits

Key findings

Situation in 2018

The WHO guidance on One Health, WHO GAP report as well as the GLASS roadmap paper all provided the essential templates for countries to develop a coordinated national One Health response to AMR. However, despite the detailed structures provided in this framework, questions remained about the clarity of roles, leadership, as well as the funding of these institutional partnerships.

As reflected in Country Visit 1 findings (2019) different Fleming Fund countries had different starting points in terms of the recognition afforded to AMR in the political agenda across health as well as non-health sectors. The countries also varied in terms of the presence of pre-existing understandings, capacities, and relationships across the HH and AH sectors.

Progress made across 16 countries

While Country Visit 2 assessed country One Health ambitions, Country Visit 3 provided a more current assessment of One Health. Using the gradient approach to One Health (Figure 15), we found decreased achievement across different functions of One Health related to joint data sharing and analysis. This is because Country Visit 3 was more realistic than the ambitions set out in Country Visit 2.

Secondly, this framework assumes that all One Health discussions take place within formal institutional committees, and that good decision making is contingent on the sharing of data and joint epidemiologic analysis. Therefore, it is also possible that some cross-sectoral discussions are taking place outside the formal One Health committees which the framework would not have been able to account for, as we see next.

Figure 15 Functional status of One Health partnerships (expectations and findings)

The next chart (Figure 16) uses additional categories for multisector partnerships identified in the Itad literature review. The overriding message from this chart is that it captures a wide range of One Health mechanisms that appear to exist in different countries. However, using this categorisation there appears to be little difference between Country Visit 2 and Country Visit 3. This is likely because these categorisations reflect longer-term characteristics of institutional arrangements in the health sector across different countries. Some countries have more decentralised governance with the presence of subnational institutions, while others encourage informality – either owing to small sizes or different administrative cultures.

Figure 16 Nature of One Health partnerships, Country Visit 2 and Country Visit 3

Similarly, Figure 17 shows not so much of the difference between Country Visit 2 and Country Visit 3 findings. It demonstrates the fact that there are a wide range of partnership arrangements in place in all countries. An important trend is that integration (seeking exchange of physical space and personnel) and even collaboration (joint activities in the field) remain very difficult to achieve across almost all the countries. The ambition of cross-sectoral activities remains limited to conducting joint meetings and limited sharing of experience and insights. These are, consequently, more likely to be feasible than joint data analysis across most countries.

Figure 17 Strength of One Health partnerships, Country Visit 2 and Country Visit 3

Variation and possible explanations

- Box 2 Key messages from the Itad literature review [here]

There is a rich body of literature around multisector collaborations in other contexts that can inform One Health. The review demonstrates that multisector collaborations are complex enterprises whose structures and success are rooted in local political and administrative contexts. Collaborations come in all shapes and sizes, and can be described in the following ways:

Informality, relationships and local political dynamics are important drivers

Most collaborations will have elements that are formal AND informal.

One is not necessarily better than the other. The degree of formality is likely to be a response to the administrative cultures in a country, and likely to represent what is most feasible at the current stage.

Actors come to collaborations in pursuit of their (different) institutional agendas – no shared vision

Fractured contexts: Collaborating partners have different aims, agendas and approaches. They do not come together willingly but come together only when the situation at hand is beyond their individual sector’s control.

Interdependence: Instead of a common vision, individual partners are more likely to be pursuing institutional agendas. Collaborations consist of complementary aims and strengths. This allows each to pursue their individual organisational aims while drawing upon each other’s strengths.

Often not easy to identify – therefore likely to require a flexible approach

Adaptation takes place when boundaries are fluid: To allow sustainable partnerships or collaborations, there should be some room for them to manoeuvre, adapt to and respond to partner needs or changing circumstances.

Successful partnerships = Sustainable collaborations: What is a successful collaboration? One that delivers on immediate project aims, or one that sustains over a longer timeframe and is responsive to local needs?

Country Visit 2

The MA approach to One Health includes at least two sets of assumptions about what is One Health (a formal, institutional mechanism), and the purpose of One Health (development of joint datasets and joint analysis to address common resistant pathogens) which need to be made explicit. In addition, we found that even in the most optimistic countries, joint analysis from integrated surveillance databases appears to be too ambitious a goal for the end of 2022.

However, on the positive side, we found interesting insights emerge from KIIs.

While the focus of the MA and AMR Focal Points was on national-level, formal (e.g. AMRCC) collaborative mechanisms, many of the KIs were able to help us identify other platforms where cross-sectoral interactions and discussions were taking place. When probed we found evidence of multiple collaborative networks – often informal – that were active around AMR. In many places, this included professional networks and academic collaborations. This presents an opportunity to use additional resources to further advance the AMR agenda.

Country Visit 3

We found that despite COVID-19 disruptions, the larger architecture of the AMR apparatus at the country level remained unchanged. One Health remains challenging to conceptualise as well as operationalise across most countries, especially if relying exclusively upon the NAP-style template of institutional partnerships. Therefore, taking a broader approach to One Health might be more productive.

Additional avenues to explore further would be subnational and informal spaces for One Health discussions. Though we were able to find limited references to sub-national examples, it is also possible that those relationships are more informal in nature and therefore not captured with the use of formal One Health style labels.

Informality took various forms and was mostly seeded by academic networks, especially by the presence of well-networked academic experts who also acted as policy advisors. In addition, as AMR surveillance is linked closely with technical institutions (and experts), there is a potential to explore the role of academics further. There were references to a Community of Practice in Nigeria. On the other hand, in smaller countries like Timor-Leste and Bhutan, many officers know each other, and it is easier for them to interact at a personal level. On the other hand, some countries such as Senegal have a top-down and formalised approach to governance. Most One Health coordination in these countries is therefore conducted at the Presidential level.

Box 3 Observations from countries – Two different ways in which One Health has been operationalised:

Bhutan

- Bhutan is a small country, where One Health is a government-led initiative with multiple tiers of One Health Multisector Partnerships (MSP) (NMTAC, TWG. Secretariat, and ministerial One Health committee.

- These MSP mechanisms are underpinned by social networks where most people know each other or know of each other.

- There is a background of work on other zoonoses and cross-border zoonoses – notably rabies.

- Strong social networks mean there might not be a need or space for other platforms.

- it is interesting to note the absence of research or university activities in One Health. This is possibly the result of the country’s small size.

Senegal

- Senegal is francophone, echoing French administrative traditions of centralised bureaucracy.

- The President’s office is the lead on One Health which could be a sign of presidential commitment, but also be interpreted as indicative of strong sectoral silos in which individual departments can not break through without resorting to a higher authority.

- One KII said the “senior One Health structure is a ‘fiction’ behind which all sectors just return to their corners and do not speak.”

- In reality, ‘highly informal’ modes of MSP are sustained between individual officers over long periods. (How were these helped by ‘formal signals’?) (From the debriefing slide).

Headline messages

- The Fleming Fund has been at the cutting edge of thinking when it comes to promoting One Health and the AMR agenda across so many different contexts.

- However, it has also been limited by an instrumentalist approach to One Health, which is focused almost entirely on shared epidemiologic analysis to the exclusion of other possible modes and outcomes of partnering.

- The One Health approach itself needs rethinking in different country contexts.

Suggestions to the DHSC for Fleming Fund 1: be Pragmatic and Flexible

- Information sharing and joint planning through meetings between AH, HH, and others might be a realistic ambition for the short term.

- The Fleming Fund is seen as a major voice in countries. So, use the opportunity to identify different networks and convene discussions across sectors and institutions to mobilise support for AMR and the One Health approach.

Suggestions to the DHSC for Fleming Fund 2: be Responsive, Innovative and Ambitious

- To make One Health partnerships sustainable, allow countries to develop their version of One Health partnerships.

- Ringfencing of One Health for AMR is likely to limit its usefulness, desirability, and sustainability in country contexts. Perhaps allow countries to explore One Health options outside AMRCC – (e.g. One Health partnership in Vietnam?).

- The importance of informal networks should be recognised.

- Annex 8: Quality and quantity

8.1 Changes in quantity of AMR data

In this section we present supporting evidence for the findings on the changes in the quantity of AMR data are based on starting with 1) figures on the situation in 2018, followed by 2) data collected by the evaluation team from document review and KIIs.

Situation in 2018

Table 25 NAPs in place in 2018

| Country | NAP in place | Budget for NAP on government budget | Government funding disbursed |
| --- | --- | --- | --- |
| West Africa |  |  |  |
| Ghana | 2017-21 |  |  |
| Nigeria | 2017-22 |  |  |
| Senegal | 2018-22 |  |  |
| Sierra Leone |  |  |  |
| East and Southern Africa |  |  |  |
| Kenya | 2017-22 |  |  |
| Tanzania | 2017-22 |  |  |
| Uganda | 2018-2023 |  | ? |
| Zambia | 2017-24 |  |  |
| South Asia |  |  |  |
| Bangladesh | 2017-22 |  |  |
| Bhutan | 2018-22 |  |  |
| Indonesia | 2020-2024 |  |  |
| Nepal | 2020-25 |  |  |
| South East Asia |  |  |  |
| Laos | 2019-23 |  |  |
| Pakistan | 2017-22 |  |  |
| Timor-Leste | 2017-20 |  |  |
| Vietnam | 2013-20 (HH) 2017-20 (AH) |  |  |

| Yes |  |
| --- | --- |
| Under-development or applied for |  |
| No |  |

Table 26 Availability of AMR data in 2018

| Country | HH AMR survey data (Itad) | AH AMR survey data (Itad) | Global Antibiotic Resistance Partnership (GARP) | CAPTURA/ MAAP | Research |
| --- | --- | --- | --- | --- | --- |
| Bangladesh |  |  | x | Substantial data available in 2017 and 2018 | HH: c.20 relevant studies preceding 2018 referenced AH: several studies preceding 2018 referenced |
| Bhutan |  |  |  | Over 126,000 samples from 2017 through 2019 from four laboratories |  |
| Indonesia |  |  |  | Of 36 surveyed facilities. 10 have 1-3 years of data, 12 have 3-10 years of data, and 6 have 10+ years of data. |  |
| Nigeria |  |  | X | Data from 2016 to 2018 was collected from 25 laboratories. 85,127 cultures, of which 84,548 were valid and 27,135 were positive. | HH: c.30 studies referenced AH: multiple studies referred |
| Senegal |  |  |  | Data from 2016 to 2018 was collected from 16 laboratories. 78,304 total cultures, of which 51,771 were valid and 15,845 were positive. |  |
| Sierra Leone |  |  |  | Data for 2016 to 2018 were collected from seven laboratories/facilities. 4,333 total cultures, of which 4,192 were valid and 744 were positive |  |
| Timor-Leste |  |  |  | Data available in 2017 and 2018 |  |
| Vietnam |  |  | x | No data shared but evidence that system and data exist | HH: SIDA supported MoH surveillance project for 10 years (1996-2006) known as Antimicrobial Susceptibility Tests (ASTs); AH: report includes data on resistance and references multiple studies |
| Ghana |  |  |  | Data from 2016 to 2018 was collected from 16 laboratories. 24,427 total cultures, of which 17,096 were valid and 5,928 were positive | e.g. Laboratory-based nationwide surveillance of antimicrobial resistance in Ghana |
| Kenya |  |  | x | Data from 2016 to 2018 was collected from 16 laboratories. 66,835 total cultures, of which 64,328 were valid and 23,578 were positive. | HH: efforts to provide resistance trends: CDC, Kenya Medical Research Institute (KEMRI), Agha Khan University hospital AH: KEMRI surveillance study on antibiotic resistance rates in poultry |
| Laos |  |  | ? | Over 5,500 samples from 2016 to 2018, including from over 15 sites which contribute over 100 samples each during the three-year period. |  |
| Nepal |  |  | x | 11/39 facilities have 3+years of AMR data | HH: individual studies documented AH: very few studies carried out but some do exist |
| Pakistan |  |  | x | 8 of the facilities used Local Information Management Systems (LIMS) for recording AST data and had 3-10 years of e-records on AST available | HH: data from journals (2006-16) and from Karachi laboratories (2013-15) by Pakistan Antimicrobial Resistance Network (PARN) AH: multiple studies listed |
| Tanzania |  |  | x | Data available for 2016 to 2018 | HH: 58 studies listed in 2015 GARP report from 1999 to 2015 AH: 3 studies listed in 2015 GARP report from 2004 to 2012 |
| Uganda |  |  | x | Data from 2016 to 2018 was collected from 16 laboratories. 88,116 total cultures, of which 85,096 were valid and 28,849 were positive. | HH and AH: various studies (c.30+) |
| Zambia |  |  |  | Data for 2016 to 2018 were available from 14 of 16 laboratories. 36,968 total cultures, of which 33,790 were valid and 23,318 were positive |  |

| Available |  |
| --- | --- |
| Not available |  |
| Unclear |  |

Data on changes in quantity of AMR at national level

The following table (Table 27) presents the data for HH AMR collected during country visits and from document reviews which form the basis for findings in Volume I of this report. This requires careful interpretation; increases in HH data could be driven by increases in the number of sites reporting which is often (but not always) linked to the size of the country, also to presence (or absence) of disease outbreaks from year to year, which mean that the Fleming Fund is not in complete control of this metric. Increases in AH reporting is linked to the extent and focus of active surveillance – i.e. the number of provinces data is collected from, for how many species and how many pathogens.

To mitigate this, we looked at a number of data points to give a broad perspective on changes in the quantity of data. These include number of sites (including total within the system, and number of these supported by the Fleming Fund); number of patients tested; number of samples; and number of isolates. For each data point we collected baseline data (2018 or earliest available) and the latest available at the time of data collection in 2022. Comparisons were made between baseline and latest year data, and given RAG ratings using transparent criteria (see Table 27 below).

Given a degree of uncertainty around specific numbers, we include Table 26 for illustrative purposes. In Vol I, section 2.1.2 we note that it has not been feasible to quantify actual amounts of new data.

Table 27 Human Health AMR data from country visits

| Country | Total sites (Base Line) | Total sites (latest) | Fleming Fund sites supported | % | Baseline (BL) | Latest Year (LY) | Pathogen (PT)/ Sample (S)/ Isolate (I) | % change |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bangladesh | 8 | 9 | 6 | 66% | 553 (S, 2017/18) | 678 (S, 2019) | S | 22% |
| Bhutan | 3 | 4 | 5 | 100% | 38,897 (S, 2018) | 31,816 (S, 2021) | S | -18.30% |
| Indonesia | 11 | 20 | 13 | 65% | 0 (S, 2018) | 52,454 (S, 2021) | S | + |
| Nigeria | 29 | 35 | 11 | 38% | 3,638 (PT, 2017) | 4,585 (PT, 2020) | PT | 26% |
| Senegal | N/A | 50 | 5 | ? | ? | ? | - | ? |
| Sierra Leone | 0 | 0 | 3 | ? | 0 | 0 | - | - |
| Timor-Leste | 0 | 5 | 6 | 100% | ? | 114 | S | ? |
| Vietnam | 16 | 19 | 20 | ? | 100,000 (I, 2019) | >200,000 (I, 2021) | I | 100% |
| Ghana | 8 | 8 | 8 | 100% | 0 | ? | S | ? |
| Kenya | 2 | 13 reporting to NRL | 8 | 62% | 0 | 1,892 | S | + |
| Laos | 2 | 9 | 9 | 100% | 17,126 | 19,060 | S | 11% |
| Nepal | 21 | 24 | 15 | 63% | 87867 | 147,150 | S | 67% |
| Pakistan | 9 | 40 | 11 | 28% | ? | ? | - | ? |
| Tanzania | 0 | 10 | 6 | 60% | ? | 27,154 | S | ? |
| Uganda | 22 | 30 | 12 | 40% | 405 | 4,852 | S | >100% |
| Zambia | 1 | 8 | 7 | 88% | 19,248 (2020) | 34,576 (2021) | I | 80% |

Criteria for rating

| RAG colour | Criteria |
| --- | --- |
|  | Positive trend compared to baseline |
|  | Positive trend apparent from qualitative data but absence of specific numbers |
|  | Unclear |
|  | No change compared to baseline |
|  | Negative trend compared to baseline |

We also present data from GLASS reports on the number of GLASS pathogens reported by focus countries in 2018 and 2019 (the latest year (LY) for which quality assured GLASS reporting is available), supplemented by data from KIIs to check for changes since 2019. Data was taken directly from published GLASS reports, up to and including the GLASS 2021 report (the GLASS 2022 report was published too late to fully incorporate in our anlaysis, although reference is made to trends in Volume I section 2.2.4).

Figure 18 GLASS pathogens tested in national systems

The following table presents the data for AH AMR collected during country visits and from document review which forms the basis of the findings in Volume I of this report. A similar approach to HH was taken to capture a broad understanding of changes in data availability, with one distinct difference relating to also seeking to understand the extent of active surveillance data collection efforts that had taken place.

Table 28 Data for AH AMR collected during country visits and from document review

| Country | Sampling rounds (BL) | Sampling rounds (latest) | Rounds supported by Fleming Fund | # sites supported by Fleming Fund - including reference laboratory (RL) (LY) | Baseline | Latest Year |
| --- | --- | --- | --- | --- | --- | --- |
| Bangladesh | 5 | 5 | Partial | 6 | 0 | 528 |
| Bhutan | 0 | 1 | Completely | 4 | 0 | 469 |
| Ghana | 0 | 2 | Partial | 3 | 0 | 3000 |
| Indonesia | not available | not available | Partial (focus on AMU) | 6 | 0 | 1000 |
| Kenya | 0 | 1 | Completely | 6 | 2462 | 40632 |
| Laos | 0 | 2 | Completely | 2 | 772 | 2238 |
| Nepal | 0 | 4 | Completely | 7 | 3097 | 6110 |
| Nigeria | 0 | 0 | N/A | 7 | 0 | 0 |
| Pakistan | 0 | ? | unclear | 10 | 470 | ? |
| Senegal | 1 | 1 | Completely | 2 | 0 | 650 |
| Sierra Leone | 0 | 0 | N/A | 0 | 0 | 0 |
| Tanzania | 0 | 1 | Completely | 4 | 314 | 1270 |
| Timor-Leste | 0 | 3 | Completely | 1 | 0 | 429 |
| Uganda | 0 | 4 | Completely | 3 | 0 | 108 |
| Vietnam | 2 | 1 | Partial | 3 | 1050 | 3339 |
| Zambia | 0 | 8 | Partial | 5 | 0 | 44 |

Criteria for rating

| RAG colour | Criteria |
| --- | --- |
|  | Positive trend compared to baseline |
|  | Unclear |
|  | No change compared to baseline |
|  | Negative trend compared to baseline |

Data on changes in quantity of AMR at international level

In the following table (Table 29) we present data from GLASS reports which has informed findings on the sharing of data at the international level. The year of publication for each GLASS report is shown, covering data two years older than the date of publication (due to time elapsed for submission and quality checks) - e.g. 2021 GLASS report covers 2019 data from countries (submitted by countries in 2020 and published by WHO in 2021).

Table 29 GLASS Data

| Country | Enrolled GLASS AMR (2021 report) | Enrolled GLASS AMC (2021 report) | Participated in WHO PPS (BL) | Participated in WHO PPS (LY – 2021 report) | 2018* GLASS report | 2019* GLASS report | 2020* GLASS report | 2021* GLASS report | 2022 GLASS report | Sites BL | Sites LY | Pathogens BL (2021 report) | Pathogens LY (2021 report) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bangladesh | 2016 | No | N | Y | N | N | Y | Y | Y | 8 | 9 | 7 | 7 |
| Bhutan | 2018 | 2019 | N | N | N | N | N | Y | Y | 0 | 1 | 0 | 6 |
| Ghana | 2021 | N | N | N | N | N | N | N | Y | 0 | 5 | 0 | - |
| Indonesia | 2019 | 2020 | N | N | N | N | Y | Y | Y | 9 | 16 | 6 | 7 |
| Kenya | 2016 | 2021 | N | Y | N | N | N | N | Y | 0 | 7 | 0 | 8 |
| Laos | 2018 | N | N | Y | N | N | N | N | Y | 1 | 3 | 8 | 8 |
| Nepal | 2018 | 2019 | N | Y | N | Y | Y | Y | Y | 15 | 17 | 7 | 8 |
| Nigeria | 2017 | No | N | Y | N | Y | Y | N | Y | 5 | 6 | 8 | 6 |
| Pakistan | 2018 | N | N | Y | N | Y | Y | Y | Y | 6 | 22 | 8 | 8 |
| Senegal | No | No | N | Y | N | N | N | N | N | - | - | - | - |
| Sierra Leone | 2020 | No | N | Y | N | N | N | N | N | - | - | - | - |
| Tanzania | 2019 | 2021 | N | Y | N | N | N | N | Y | 0 | 10 | 0 | 8 |
| Timor-Leste | 2020/2021 | Y | N | Y | N | N | N | N | Y | - | 1 | - | 5 |
| Uganda | 2016 | N | N | N | N | Y | Y | Y | Y | 2 | 30 | 8 | 8 |
| Vietnam | 2019 | No | N | N | N | N | N | N | N | - | - | - | - |
| Zambia | 2016 | N | N | N | Y | Y | N | Y | Y | 1 | 5 | 8 | 5 |

Criteria for rating

| RAG colour | Criteria |
| --- | --- |
|  | Positive trend compared to baseline |
| For all columns except GLASS reporting | Unclear |
| For GLASS reporting columns | reporting to GLASS but qualitative information on nature of surveillance system, not reporting actual AMR surveillance data |
|  | No change compared to baseline |
|  | Negative trend compared to baseline |

Data from the 2022 GLASS report objectively corroborates the positive trends that we have identified through our country specific data collection efforts and as reported by the MA. GLASS reporting shows increases in the proportion of our focus countries that are reporting more sample types (see Figure 20), and that more of our focus countries are reporting more data compared to 2018 (see Figure 19).

Figure 19 Number of countries reporting

Figure 20 Percentage of countries reporting more data

In the following table (Table 30) we present data from country-level KIIs on their reporting on AMU to WOAH. Data for 2018 (baseline) and latest available data (latest year) were collected using the ’reporting options’ categories that are available to countries when they participate in the WOAH annual survey on AMU. We were unable to corroborate this for specific countries with WOAH because data is submitted on a confidential basis. However, we have benchmarked this against aggregates of country reporting (see Volume I, section 2.2.4). We used these data to inform findings on sharing of data at the international level.

Table 30 Country data on AMU reporting to WOAH (from KIIs)

|  | WOAH reporting |  |  |
| --- | --- | --- | --- |
| Country | BL: 2018 | Latest year | Change within |
| Bangladesh | None | 2 | Y |
| Bhutan | 1 | 3 | N/A |
| Ghana | 1 | no info | N/A |
| Indonesia | no info | no info | N/A |
| Kenya | 1 | 1 | Y - Starting to capture imports via informal routes, not just government data on imports. Work in progress |
| Laos | ? | 3 | N |
| Nepal | 1 | 3 | N/A |
| Nigeria | 1 | 2 | N/A |
| Pakistan | ? | ? | No info |
| Senegal | 1 | 3 | No Info |
| Sierra Leone | None | none | N/A |
| Tanzania | None | 1 | Y |
| Timor-Leste | None | 3 | N/A- N/A |
| Uganda | 1 | 1 | Y |
| Vietnam | 1 | 1 | N |
| Zambia | 1 | 3 | N/A |

Criteria for rating

| RAG colour | Criteria |
| --- | --- |
|  | Positive trend compared to baseline |
|  | Unclear |
|  | No change compared to baseline |
|  | Negative trend compared to baseline |

Performance compared to the MA implementation plan targets

Table 31 shows the number of countries in which the MA expected to see progress in generating and using AMR data at different stages of phase 1 implementation; these targets were set out in the MA’s implementation plan (v2.5), prior to substantial implementation.  Table 32 shows what the status of implementation was by December ‘22 (in terms of duration of Fleming Fund support) and progress in terms of data generation and international sharing; the intention is to enable comparisons with original MA implementation plan targets as set out in Table 31.

Table 31 MA implementation plan targets (v2.5)

| Target/FF Grant programme length | 12 | 24 | 36 | 48 |
| --- | --- | --- | --- | --- |
| Primary data* generated and used for policy and improving guidelines | 3 | 8 | 16 | 18 |

*“Primary data” in this table refers to data from surveillance systems that are the subject of Fleming Fund investments and are intended to be a measure of the outputs of those specific investments.

Table 32 Mapping duration of support with available evidence on whether data is being generated

|  | Duration of FF support by: |  | Reporting AMR data to GLASS | Data collated by evaluation team |  |
| --- | --- | --- | --- | --- | --- |
|  | Jun-22 | Dec-22 | 2022 report data | Baseline | Latest Year |
| Senegal | 20 | 26 | not enrolled | 0 | ? |
| Sierra Leone | 21 | 27 | N | 0 | 0 |
| Bangladesh | 30 | 36 | Y | 553 | 678 |
| Indonesia | 31 | 37 | Y | 1 | 52454 |
| Kenya | 34 | 40 | Y | 1 | 1892 |
| Zambia | 35 | 41 | Y | 8270 | 30000 |
| Nigeria | 37 | 43 | Y | 3638 | 4585 |
| Pakistan | 38 | 44 | Y | ? | ? |
| Vietnam | 38 | 44 | N | 100000 | 200000 |
| Timor-Leste | 38 | 44 | Y | 1 | 114 |
| Laos | 39 | 45 | Y | 17126 | 19060 |
| Bhutan | 39 | 45 | Y | 38897 | 31816 |
| Tanzania | 40 | 46 | Y | 1 | 27154 |
| Ghana | 42 | 48 | Y | 0 | ? |
| Uganda | 45 | 51 | Y | 405 | 4852 |
| Nepal | 47 | 53 | Y | 87867 | 147150 |
| India | 12 | 18 | Y | not a focus country |  |
| Eswatini | 27 | 33 | N | not a focus country |  |
| Malawi | 27 | 33 | Y | not a focus country |  |
| Zimbabwe | 27 | 33 | N | not a focus country |  |
| PNG | 30 | 36 | N | not a focus country |  |
| Myanmar | 34 | 40 | Y | not a focus country |  |
| Sri Lanka | 35 | 41 | Y | not a focus country |  |

8.2 Changes in quality of AMR data

The following table was used as a template for the collation of data from the MA quarterly site reports to make an assessment of changes in key markers of quality processes. Separate templates were completed for the baseline (drawing on the earliest available site report) and latest year (drawing on the most recent quarterly report). Separate templates were also completed for HH and AH laboratories. A score of 1 was given where the category was reported to be in place. Total scores across all sites were averaged.

Table 33 Quality of AMR data - data collection template

| BASELINE quarter/year: Q3 - Oct 2019 - used as baseline (some data tracked in Q2, but in a different format and not consistent ability to answer/compare below questions) | Source (refers to cell in 'site report' section of the quarterly report) | Site 1 | Site 2 | Site 3 | Site 4 | Site 5 | Site 6 | Site 7 | Site 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. All sample types and organisms are processed according to SOPs | QR SR 2c (need 'yes according to SOP' for all sample types and organisms in this section to gain "1") |  |  |  |  |  |  |  |  |
| 2. Working blood culture instrument in place and under a service contract | QR SR 2c |  |  |  |  |  |  |  |  |
| 3. Is the laboratory enrolled in approved EQA for identification and AST | QR SR 1d |  |  |  |  |  |  |  |  |
| 4. Are SOPs for AST methods in use based on Clinical and Laboratory Standards Institute (CLSI) or European Committee on Antimicrobial Susceptibility Testing (EUCAST) guidelines that are < 3 years old | QR SR 2d |  |  |  |  |  |  |  |  |
| 5. Are sites using a unique alphanumeric identifier (ID number) assigned to patients | QR SR 1b |  |  |  |  |  |  |  |  |
| 6. All relevant laboratory staff trained in internal quality control procedures | QR SR 1d (if only "some staff" mark as "0") |  |  |  |  |  |  |  |  |
| 7. All relevant staff trained in identification SOPs | QR SR 2 |  |  |  |  |  |  |  |  |
| 8. All relevant laboratory staff trained in AST SOPs | QR SR 2 |  |  |  |  |  |  |  |  |
| Total score |  |  |  |  |  |  |  |  |  |
| Average score |  |  |  |  |  |  |  |  |  |
| # Sites (update as required) 8 |  | insert "1" where parameter in place/met, "0" where not in place |  |  |  |  |  |  |  |

A summary of the data collated from the above template is included in the following tables (Table 34 and Table 35).

Table 34 Changes in quality of AMR data (Human Health)

| Country Name | Human Health |  |  |  |
| --- | --- | --- | --- | --- |
|  | Average Quality Score |  | Number (%) of sites improving from baseline to endline | RAG |
|  | 2018 | 2021 |  |  |
| Bangladesh | 3.8 (2020) | 4.6 (2021) | 2 sites (67%) improved. 1 (NRL) remained the same. |  |
| Bhutan | 2 (2020) | 6 (2021) | 4 sites (80%) improved, 1 remained the same |  |
| Ghana | 3.5 (Oct 2019) | 6.5 (July 2020) | 8 (100%) |  |
| Indonesia | 4.07 (2020) | 4.23 (2021) | 2 (18%) improved, 9 sites remained the same |  |
| Kenya | 2.12 (Jan - March 2020) | 5.5 (Apr - Jun 2021) | 8 (100%) |  |
| Laos | 2.75 (Oct-Dec 19) | 3.4 (Jan-Mar 2022) | During endline, 3 sites improved from BL and 1 site remained the same but the average score from 10 million sites. (additional 6 sites added). So score from BL (4) & endline (10) sites |  |
| Nepal | 3.83 (Aug 2019) | 7.13 | 12 (100%) |  |
| Nigeria | 4.45 | 4.63 (2021) | 5 (45%) sites improved from 11, 2 remained the same, 4 dropped |  |
| Pakistan | 1.18 (NRL: Oct-Dec 19) (Surveillance Sites: Jan to March 2021) | 2.45 (Jan-Mar 22) | 8 improved (73). 3 remained the same |  |
| Senegal | 3.4 | 4.4 | 4 (80%) sites improved, 1 remained the same |  |
| Sierra Leone | 2 (2020) | 0 (2022) | 3 sites dropped, 1 site remained the same |  |
| Tanzania | 4 (Q3_CG1 Jan 2020) | 6.66 (CG 2 Q2-Oct 2021) | 6 (100%) |  |
| Timor-Leste | 0 (2019) | 7.14 (2022) | 7(100%) improved |  |
| Uganda | 6.43 (2019 Q4_QR) | 5 (2022 QR_Q6) | Among 7, 1 site improved, 2 remained same and 4 sites’ score declined |  |
| Vietnam | 4.4 (2019) | 6.65 (2021) | 19 (95%) improved, one remained same |  |
| Zambia | 4.71 (Q2_ Jan-March 2020) | 5.42 (Q8_ April-June 2021) | 3 (42.85%) improved. Among 7, only three sites improved and four sites’ score decreased |  |

Table 35 Changes in quality of AMR data (Animal Health)

| Country Name | Animal Health |  |  |  |
| --- | --- | --- | --- | --- |
|  | Average Quality Score |  | Number (%) of sites improving from baseline to endline | RAG |
|  | 2018 | 2021 | RAG |  |
| Bangladesh | 2 | 4 | 2 site (100%) |  |
| Bhutan | 0 (2020) | 6.75 (2021) | 4 (100%) improved |  |
| Ghana | 2 (Oct 2019) | 2.33 (July 2020) | 1 (33%) improved, 2 remained the same |  |
| Indonesia | 2.5 (2020) 6 sites | 2.72 (2021) 11 sites | 9 (%) |  |
| Kenya | 0.67 (Jan - March 2020) | 3.83 (Apr - Jun 2021) | 6 (100%) |  |
| Laos | 0.33 (Jan-Mar 2020) | 1 (Jan-Mar 2022) | None (0%) of the 2 sites improved. Both remained the same |  |
| Nepal | 2 (Aug 2019) | 4.42 | 4 (100%) |  |
| Nigeria | 0 | 3 | 3 (100%) improved |  |
| Pakistan | 1 (NRL) 0 (SS) | 4.5 (NRL) 0.11 (SS) | 3 (27%) improved, 8 remained the same |  |
| Senegal | 1.5 | 2 | 1 site (50%) improved, 1 remained the same |  |
| Sierra Leone | 1 (2020) | 0 (2022) | The only site dropped |  |
| Tanzania | 0 (Q3_CG1 Jan 2020) | 4.75 (CG 2 Q2 - Oct 2021) | 4 (100%) |  |
| Timor-Leste | 0 | 7 | 1 (100%) improved |  |
| Uganda | 3.33 (2019 Q4_QR) | 5 (2022 QR_Q6) | All 3 (100%) sites scores increased from baseline, but during endline four more sites were included (score “0” all of them) which lowered the average score. |  |
| Vietnam | 0.3 | 4 | 3 (100%) |  |
| Zambia | 1.5 (Q2_ Jan-March 2020) | 5.4 (Q8_ April-June 2021) | 2 sites match with baseline. And those two improved from baseline to endline. The additional 3 sites were added during endline and two were absent from baseline. |  |

The MA’s KPI data on changes in laboratory capacity (Figure 21 and Figure 22) show that, in both HH and AH sectors, there has been a progressive increase in both the number of sites supported by the Fleming Fund and in the number of sites that are progressing in two or more components of the LSHTM roadmap. Note that data shown for 2022 is not complete, it only shows data up to June 2022. This equates to meeting agreed targets in HH in two of three completed years, with 2020 being off-track – most likely due to COVID-19. Similar performance is shown in AH. In both sectors, at the time of writing it was too early to tell whether targets would be met in 2022.

Figure 21 Number of Fleming Fund supported HH sites showing progress through the LSHTM roadmap

Figure 22 Number of Fleming Fund supported AH sites showing progress through the LSHTM roadmap

- Annex 9: Data Use

9.1 Observed data use at the national level

This section summarises the headline national-level data use observations. These observations are based on information from KIIs as well as relevant documentation (including underlying data, and/or evidence of data sharing, or use provided by KIIs where available).

Data use was assessed to have taken place where there was evidence that relevant AMR surveillance data had contributed to decision making by responsible participants (policymakers) in the appropriate governance structures (AMRCC or equivalent), linked with verifiable national action in the form of policy being implemented or regulation enacted since 2018.

Data use is different from data sharing, although the two are related. Data sharing was assessed to have taken place where there was evidence of shared relevant AMR surveillance data with appropriate governance structures (AMRCC or equivalent) for surveillance purposes (ongoing, systematic, purposeful data processing by those responsible for decision making on AMR-related action).

Countries were grouped into clusters. Note that these groups were developed for evaluation analysis purposes focused on the question of how surveillance data sharing relates to national action on AMR. These observations are not a general assessment of national AMR actions, nor do they claim to be a comprehensive summary of relevant actions. National decisions over whether to implement policy or enact regulation on AMR (or not) involve a broad range of issues and refer to various forms of information beyond AMR surveillance data. Observations in this section focus on processes of cross-sector AMR surveillance data sharing and use which is just a part of that overall picture.

Table 36 Examples of use of relevant data for decision-making

| Country | Example national action | Role of AMR surveillance data | Assessment of the use of AMR surveillance data |
| --- | --- | --- | --- |
| Bangladesh | HH: work ongoing to update National Drugs Act | Surveillance input is reported as being at an early stage. Research is leading at present. | No AMR data influence yet (research) |
|  | AH: regulation - product bans & drug quality controls | Lack of specific information on the details of the decision process but a KII reported that surveillance information as well as research, informed regulatory initiatives. | AMR data influence (details unclear) |
| Nepal | HH: policy – changes to national (List of essential medicines) EML (Dec 2021); ongoing work on national STG and IPC guidelines | EML changes were based on national AMC surveillance data; a KII was explicit that they are not yet informed by AMR surveillance. But work on national standard treatment guidelines (STG) and IPC guidelines plus drug packaging regulation was reported to have drawn on AMR data. | AMR data (AMC only so far) |
|  | AH: regulation – feed restrictions (2020) | Reportedly based on research (results from cross-sectional studies), explicitly not informed by surveillance data. | No AMR data influence yet (research) |
| Kenya | HH: policy – revision to national AMS guidelines and EML over 2019-20 | Wider data inputs from general national M&E activities under NAP, including e.g. knowledge from research. Specific examples of surveillance data inputs, especially AMU Point Prevalence Survey (PPS) but also AMR. | AMR data influence confirmed |
|  | AH: policy – farm biosafety guidelines (IPC) | AMU surveillance data reported as input to draft regulation development. Further/AMR contribution is at an early stage. | AMR data influence (unclear, AMU only so far) |
| Tanzania | HH: policy – revision to national STG and EML over 2019-20 | STG and EML updates, reportedly, use both AMR and AMU surveillance data. | AMR data influence confirmed |
|  | AH: no action completed yet | Ongoing work on policy (STG and livestock policy) and regulation (disease and perimortem rules) informed by AMR research, is not yet surveillance based. | No action yet and no AMR data influence yet (research) |

Table 37 Examples where use in decision making looks promising but is not confirmed

| Country | National action | Role of surveillance data | Assessment |
| --- | --- | --- | --- |
| Bhutan | HH: policy - national STGs revised at the start of the period (2018); regulation - Medicines Rules and Regulations (MRR) – last updated 2019 | STGs are reportedly based on ‘the limited AMR data available in 2016’, there were plans to repeat this using post-2018 data but they were delayed due to COVID-19. | AMR data influence (but interrupted by COVID-19) |
|  | AH: regulation - MRR – last updated 2019 | MRR data inputs not specified. There were plans to update again in 2022. Meanwhile, KIIs reported AMR data being used for informal advice. | AMR data influence (formative stage) |
| Uganda | HH: No action completed yet | Reported in progress draft of new Pharmaceutical Plan for 21-25, but link to AMR data not specified. | No clear AMR data influence |
|  | AH: policy - Essential Veterinary Medicines List; guidelines for infection prevention and appropriate AMU in various AH sectors (2020) | No evidence of surveillance data as an input yet, but research was used and current efforts explicitly set out to use AMR data for policy updates. | AMR data influence (formative stage) |

Table 38 Data sharing not yet connected with action/current systematic collation and analysis leading towards data use

| Country | National action | Role of surveillance data | Assessment |
| --- | --- | --- | --- |
| Pakistan | HH: No action completed yet (although notable subnational actions) | Data ‘so far been used only for awareness-raising/sensitisation of policymakers and discussion among technical people’ at a national level. | No AMR data influence yet (awareness stage) |
|  | AH: regulation - Ciprofloxacin was banned in poultry (2018) | ‘Based on certain observations and research’ | Unclear (research lead) |
| Vietnam | HH: No action completed yet | Site data is reported monthly, with annual analysis & feedback workshops. Focus on awareness-raising so far. Current work on input to situation analysis/national strategy development. | No AMR data influence yet (awareness stage) |
|  | AH: regulation – growth promotion ban 2018 | Surveillance data were not available, based on research, informal reporting, and international recommendations. | Unclear (research/ international lead) |
| Laos | HH: No action completed yet | Data is now more available but no connection to processes for national action. | No AMR data influence yet |
|  | AH: policy initiatives | Data is now more available but perceived problems in using it to inform national policy. | Unclear (export standards lead) |
| Zambia | HH: No action completed yet | There is some use of AMR data, amongst other inputs, to policy briefs being deliberated by the AMRCC. | No action yet |
|  | AH: No action completed yet | Some use of AMR data amongst other inputs to the development of draft regulations on poultry feed. | No action yet |

Table 39 Progress towards data sharing/developments increasing potential for future data use

| Country | National action | Role of surveillance data | Assessment |
| --- | --- | --- | --- |
| Ghana | None yet, mainly awareness | Issues assembling AMR data for influence on national policy – no reporting of AMR surveillance, lack of systematic view across PPS. | Data (AMU), no action |
| Sierra Leone | None yet | PPS and situational awareness discussions | Initial data, no action |
| Timor-Leste | Uncertain – towards HH policy (guidelines) | Data is now more available but the perceived problem is using it to inform national policy. | Data (AMR), no action |

Table 40 No substantial progress towards data sharing/unclear prospects for future data use

| Country | National action | Role of surveillance data | Assessment |
| --- | --- | --- | --- |
| Indonesia | None yet | AMR surveillance data goes to GLASS but not national data; national processes are more concerned with other information inputs | Data (AMR), no action |
| Nigeria | HH: no action completed yet (some IPC guidelines mentioned but not linked to AMR) | Developments are restricted to the early stages of awareness and enthusiasm building. Policy document revision is not currently based on AMR data. | No AMR data influence yet (early stages) |
|  | AH: regulation - ban on the use of antibiotics as growth promoters and mould inhibitors in animal feed (2022) | NAFDAC’s action to enact this ban was reportedly influenced mainly by the mandate to decrease counterfeits and improve the quality of medicines available. Some AMC data was collected, and international were standards consulted. | Data (AMC), action not for national AMR/through AMRCC |
| Senegal | AH policy initiatives | Current AH policy initiatives are mainly motivated by regional trade standards. | No data, initial action (AH) |

9.2 National policy agenda analysis (Kingdon Multiple Streams Analysis MSA)

John Kingdon developed the MSA in the 1980s based on an investigation of policy processes in the USA. MSA identifies three processes ‘streams’ that influence how policy agendas are set and how policy alternatives are specified. These streams are:

- Problems: the way in which social conditions come to be defined as a problem to policymakers, e.g. through indicators, focusing events, and feedback;

- Policies: the solutions generated to address problems, which are influenced by technical feasibility, value acceptability, the anticipation of future constraints, policy communities, and policy entrepreneurs; and

- Politics: political factors, including the influence of interest groups, the ‘national mood’ and turnover of elected officials.

- Box 4 Kingdon's Multiple Streams Analysis Kingdon’s MSA suggests that the three streams must come together at the same time, during a ‘window of opportunity,’ in which people pay high attention to a problem, a viable solution exists, and policymakers have the motive and opportunity to select it. [MSA] expresses work on agenda setting, which revolves around the basic insight that problems do not receive attention simply because we think they are important, and policymakers do not select solutions simply because they are the most effective. Rather, actors exercise power to raise attention to some issues at the expense of others, drawing on a combination of facts and emotional appeals. They use persuasion and argument, alongside the use of material and other resources, to challenge or reinforce often deeply held beliefs about the nature of policy problems and appropriate solutions. Actors often described as ‘policy entrepreneurs’ become crucial to the process of linking solutions to problems. These are the people, such as elected politicians or leaders of interest groups, with the knowledge, power, tenacity, and luck to be able to exploit windows of opportunity and heightened levels of attention to policy problems to promote their ‘pet solutions’ to policymakers.

National policy agendas. It remains unclear how NAPs can be prioritised in resource-constrained contexts. Prioritisation of an agenda happens when policymakers concurrently understand the problem, have a viable solution available, and are convinced of the need to act. When this happens is unpredictable (not linear, more chaotic) and it is sometimes facilitated by a policy entrepreneur. However, evidence from published literature and KIIs suggests that the necessary conditions for the prioritisation of NAPs are generally not in place.

Figure 23 Diagram of the Multiple Streams Approach

Table 41 Notes on changes in analysis, 2020-2022 (reflections on Fleming Fund contribution in wider policy context)

| Stream | Headline | Subcomponents | Observations |
| --- | --- | --- | --- |
| Policy | Most changed – technical networks, in search of solutions to problem | Positive: value acceptability, policy community, technical feasibility | Focus of Fleming Fund contribution, facilitating international-national-local interactions, building networks of interest and ability, funding work on national laboratory systems |
|  |  | Neutral: network integration | See One Health observations |
|  |  | Negative: resource adequacy | Resourcing issues in national surveillance & NAP context, including Fleming Fund sustainability & VfM challenges, emerging as a significant brake |
| Problem | Change in some countries only – advocacy not just analysis, headwinds | Positive: Indicators | Focus of Fleming Fund contribution, through surveillance system (although progress here is much broader, especially using research and international inputs – see use headlines) |
|  |  | Neutral: Focusing events |  |
|  |  | Negative: Load (though there is some feedback mitigation) | COVID-19 distraction & priority as a public health crisis |
| Politics | No real change – outside control but emerging as a leading challenge | Positive: Party ideology | Leadership interest in some countries (global engagement opportunity) |
|  |  | Neutral: National Mood, Balance of Interests | Awareness not hitting the public yet, starting to think about professional engagement but not much yet on economics (e.g. pharmaceutical food production) |
| Policy entrepreneurs (PE) | Rare to see progress | Neutral | See Policy Fellow comments. Champions still understood only within the policy stream, with some interest in the problem stream |
| Window of opportunity | May emerge | Weak Positive | Opportunities are more likely to emerge if the focus is on fostering progress in the problem and policy stream and targeting policy entrepreneurs on the politics stream. Fleming Fund phase 2 needs to stay responsive to country specific opportunities given the low ability to impact politics. |

Over the course of phase 1, the clearest indication of improved prospects for the AMR agenda prioritisation has come in the Policy stream, through gradual accumulation of knowledge and perspectives among technical specialists and the generation of policy proposals by said specialists. The Fleming Fund Professional Fellowship scheme proved especially valuable in developing networks of expertise around national AMR agendas.

It has proved harder to make headway in the Problem stream, establishing clear recognition by senior decision makers that AMR constitutes a serious problem that needs addressing urgently. Determined national action has only been taken in countries in which KIs reported that national policymakers regard AMR as a serious and urgent problem . One clear issue in this respect has been the COVID-19 pandemic since 2020, which has (amongst other influences) tended to diminish the capacity for decision makers to devote attention to other issues including AMR (see Box 5).

- Box 5 COVID-19 and national AMR agendas, 2020-22 The global COVID-19 pandemic over 2020-22 has had a significant impact on the way that AMR is perceived as a problem in the national policy agendas of Fleming Fund countries. Literature reviews and KII conversations with stakeholders indicated different kinds of effects within the subcomponents of the ‘Problem’ stream in MSA. The strongest effect tended to undermine perceptions of AMR as a serious and urgent policy problem. The ‘Load’ subcomponent of the MSA Problem stream refers to the capacity of institutions to deal with problems; if policymakers are dealing with all-consuming or numerous problems, then a new problem’s ability to nudge its way into the purview of policymakers is negligible. COVID-19 certainly challenged the AMR agenda in many countries from a Load perspective. Policymakers were understandably distracted with developing responses to the immediate threat, and officials were preoccupied with service provision and regulatory measures. There were priority claims on public health budgets and in many places AMR initiatives and meetings were deferred or directed to seek ways to contribute to the COVID-19 response. COVID-19's prominence as an issue over 2020-22 made it difficult for other public health issues like AMR to claim attention. But there were also other ways, although fainter and less consistent across countries, in which COVID-19 was reported to have strengthened the position of MSA in policy agendas. The ‘Indicators’ subcomponent of the MSA Problem stream speaks to the way in which actors identify and monitor potential problems, including metrics measuring the relative severity of a given problem. In some cases, stakeholders suggested that the recent experience with COVID-19 had helped reinforce awareness and regard for the seriousness of public health issues in policymakers’ minds generally, making it easier to draw attention to AMR. The ‘Feedback’ subcomponent, similar conceptually to Indicators, accounts for information provided by analogous programmes related to the problem of interest; basically, evidence from addressing one policy problem strongly flags problems in another area. In some countries, increased attention to Infection Prevention and Control (IPC) and also to Global Health Security (GHS) as a result of the COVID-19 pandemic experience was reported to have created opportunities for AMR policy by association because of shared concerns. So most countries cited COVID-19 as a factor impeding progress with the AMR agenda, consistent with TrACSS 2021 reporting that the pandemic has had negative administrative and operational impacts. However, KIs also commonly reported that COVID-19 has tended to raise general awareness of the importance of taking public health threats seriously. Increased attention to IPC was cited as a positive opportunity for national AMR agendas going forward. Associated policy initiatives in dimensions such as health security were said to tend to reinforce AMR governance structures in some countries.

Above all, there is no clear sign of any headway in the Politics stream in any country, with a lack of mainstream public demands for government action on AMR and persistent ‘balance of interest’ issues involving important but poorly understood factors such as the imperative of concentrating on improved access to high-quality medicines and effective treatment, plus powerful incentives to prefer nutrition (vs food safety) or economic objectives (vs regulatory burden). These are issues firmly outside of Fleming Fund’s control, not least as a programme that emphasises country ownership principles in its theory of change. However political change is still relevant to programme implementation as a contextual dimension in which opportunities or constraints arise.

This is not unexpected when it comes to the broader experience with agenda setting. To date, the Fleming Fund has not focused on establishing the full range of conditions that are necessary and sufficient for the use of AMR surveillance data or verifying whether these conditions are in place, primarily because it has emphasised the production of the data during this phase of the Fleming Fund.

9.3 Examples of Use at facility level

The potential for and significance of data use changes at the facility level has grown over phase 1. Over the course of phase 1, there has been increased Fleming Fund attention to the potential to develop a local or facility-based change in parallel or as an alternative to national action. As part of data gathering for this summative evaluation, country stakeholders including the MA, CG, Fellows, counterparts and laboratory visit contacts were encouraged to identify and provide information on local or facility-based EoU using a simple template based on ‘stories of change’ qualitative methods.

At the facility level, there is emergent evidence that Fleming Fund interventions are stimulating isolated positive changes to practices and attitudes as clinicians and other stakeholders start to interact differently with improved laboratories. A substantial number of examples were confirmed across the majority of focus countries (35 examples from 13 out of 16 countries). Despite extensive efforts, it was not possible to identify any examples in three countries , and only a limited number of examples were available in most countries. The data collection objective was three to six examples per country, but the median number of examples obtained was two (six countries). The maximum number of examples obtained for a country was four .

HH examples were more abundant than AH ones, see Figure 24 below. Globally, more examples were drawn from the HH sector (nearly two-thirds of the total, 22/35 or ~63%). The remainder (13/35 or ~37%) were drawn from AH. No examples were offered from the plant health or environmental sectors.

Examples in both HH and AH were offered in most, but not all countries. Most countries in which examples were available offered instances of use across both HH and AH sectors (8/13). In some countries, only HH examples were offered . There was an exclusive focus on AH examples in only one country . No examples offered adopted a One Health/multisectoral perspective. There were no examples of use based on plant health or environmental data.

The goal of data use in most examples was to promote AMS. The majority of examples offered focused on AMS as the objective of relevant data use (20/35 or ~57%). Otherwise, a significant proportion targeted awareness-raising objectives (8/35 or ~23%). A further significant proportion pursued IPC objectives (7/35 or 20%), mostly in combination with AMS goals (4/35 or ~11%).

Examples mainly described practice changes resulting from data use. The results of relevant data use specified in the examples were mainly in practice (24/35 or ~69%). There were some examples resulting in changes to attitudes (4/35 or ~11%), although attitudes were also implicitly involved in many practice-related and other examples. Examples of policy changes were less common (6/35 or ~17%), and only one example ended with regulatory change .

Figure 24 Local/facility level Examples of Use across Fleming Fund countries evaluated (EoU)

Examples of Use in HH suggest a pattern of facility-based clinical engagement over AMS in practice. Examples of Use in the HH sector concentrated on changes in terms of AMS (21/22), sometimes but not typically including explicit IPC (5/22). The objective was most often change to clinical practice (18/22).

HH Examples of Use were often based on uses of AMU data rather than AMR data generated from laboratory AST. Most HH Examples of Use involved uses of AMR data derived from laboratory AST linked to Fleming Fund investments (16/22). But a significant number of others involved AMU data from applications of the Point Prevalence Survey (PPS) methodology (8/22). It was rare for an example to describe changes resulting in the use of these data types in combination (2/22).

HH Examples of Use typically described changes at a single site, although some also detailed site networks and ultimately broader connections. Most examples concerned change in a single site (16/22). However, others described uses of data from networks of sites (6/22), of which about half involved broader policy change (3/22) – two associated with national initiatives  and one at the provincial level .

Figure 25 Human Health Examples of Use

Examples of Use in AH described a wider variety of objectives, data types and categories of change. AH examples demonstrated a greater emphasis on awareness (6/13) relative to AMS (4/13); in contrast to the HH examples, some AH examples focused exclusively on IPC objectives (3/13). The exact nature of the data used was less clearly specified in AH than in HH examples but included AMC data, AMU data (3/13) as well as AMR data from ASTs (6/13). Although practice was again prominent, AH results were also described in more varied terms, covering the full range of attitudes (2/13), practice (6/13), policy (4/13), and regulation (1/13).

AH Examples of Use involved engagement with commercial stakeholders more than professional groups, especially involving the poultry industry. AH examples frequently included and/or addressed industry stakeholders, with a significant proportion of the examples offered relating to AMR in the poultry industry (6/13). There was only one example in aquaculture . More examples than expected, given phase 1 investment in active surveillance, related to uses of data generated passively (4/13).

AH Examples of Use suggested greater potential for facility-level AH data to be used for direct influence on national policy and regulatory change. A significant proportion of AH examples described change resulting in national policy or regulatory change (5/13 – or ~38%). This was higher than the equivalent proportion in HH (3/22 – or ~14%).

Some unexpected variation in examples was observed across countries. We expected to find examples of use connected to and arising from the Fleming Fund phase 1 CGs, especially where use-focused CG2 are in place. While this held true in some countries , it was much less evident in others .

The number of facility-level Examples of Use available did not correlate neatly with the assessed data use at national levels. Mostly this was a question of relatively abundant facility-level examples contrasting with relative lack of progress with national data sharing . In a smaller number of countries, the lack of facility-level examples was surprising given observed national changes .

Annex 10: Sustainability

The following tables provide an overview of data collected through country visits and corresponding judgements about the prospects for sustainability, using the four pillars of sustainability described in Annex 3. Table 43 includes an explanation of the ratings shown in Table 41andTable 42.

Table 42 Sustainability Data – Animal Health

| Country/criteria | Animal Health |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Resources |  | Capacity |  | Motivation |  | Plans |  |
|  | Current | Planned | Current | Planned | Current | Planned | Current | Planned |
| Bangladesh |  |  |  |  |  |  |  |  |
| Bhutan |  |  |  |  |  |  |  |  |
| Ghana |  |  |  |  |  |  |  |  |
| Indonesia |  |  |  |  |  |  |  |  |
| Kenya |  |  |  |  |  |  |  |  |
| Laos |  |  |  |  |  |  |  |  |
| Nigeria |  |  |  |  |  |  |  |  |
| Nepal |  |  |  |  |  |  |  |  |
| Pakistan |  |  |  |  |  |  |  |  |
| Senegal |  |  |  |  |  |  |  |  |
| Sierra Leone |  |  |  |  |  |  |  |  |
| Tanzania |  |  |  |  |  |  |  |  |
| Timor Leste |  |  |  |  |  |  |  |  |
| Uganda |  |  |  |  |  |  |  |  |
| Vietnam |  |  |  |  |  |  |  |  |
| Zambia |  |  |  |  |  |  |  |  |

Table 43 Sustainability Data – Human Health

| Country/criteria | Human Health |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Resources |  | Capacity |  | Motivation |  | Plans |  |
|  | Current | Planned | Current | Planned | Current | Planned | Current | Planned |
| Bangladesh |  |  |  |  |  |  |  |  |
| Bhutan |  |  |  |  |  |  |  |  |
| Ghana |  |  |  |  |  |  |  |  |
| Indonesia |  |  |  |  |  |  |  |  |
| Kenya |  |  |  |  |  |  |  |  |
| Laos |  |  |  |  |  |  |  |  |
| Nepal |  |  |  |  |  |  |  |  |
| Nigeria |  |  |  |  |  |  |  |  |
| Pakistan |  |  |  |  |  |  |  |  |
| Senegal |  |  |  |  |  |  |  |  |
| Sierra Leone |  |  |  |  |  |  |  |  |
| Tanzania |  |  |  |  |  |  |  |  |
| Timor-Leste |  |  |  |  |  |  |  |  |
| Uganda |  |  |  |  |  |  |  |  |
| Vietnam |  |  |  |  |  |  |  |  |
| Zambia |  |  |  |  |  |  |  |  |

Table 44 Sustainability Data Rubric

|  | Green | Amber | Red |
| --- | --- | --- | --- |
| Current: To what extent are current resources, capacity, motivation and planning sufficient to sustain AMR surveillance outputs beyond the end of 2022? | Sufficient | Partly sufficient | Insufficient |
| Planned: to what extent are country-level plans (i.e. not specific to Fleming Fund) in place to address any sustainability constraints? | Relevant/adequate plans in place and being implemented | Plans in place but partially cover issues | No plans in place |

- Annex 11: Departures from the ToRs

Given the time that has elapsed since the original ToRs (Annex 1) were written, and the somewhat evolving nature of the Fleming Fund design and implementation arrangements, the evaluation design has identified a number of areas in which the evaluation’s purpose, scope and objectives have been altered during the inception phase. These are detailed in the following table.

Changes in what is proposed against what is stated in the original ToR for the Evaluation Supplier

| Point from the original Evaluation ToR | Modification to the scope of the implementation plan | Implications |
| --- | --- | --- |
| A detailed methodology for data collection, analysis, and regular reporting, including proposals for verifying the baseline information for each project granted funding by the MA. | We did not have the resources available to validate baseline information for each and every grant while also delivering against the primary objectives of the evaluation. Each of our 16 sample countries was our unit of analysis. | The evaluation, to the extent possible, has been able to comment upon whether claimed outputs of the grants are delivered and then whether these outputs are likely to have contributed to change both in the status of surveillance systems and enhanced sharing of surveillance data. The quality of the evaluation was not adversely affected by this approach. |
| Proposals for the capability-building activities to be undertaken with grantees in understanding the M&E and the theory of change laid out in Annex B of the Specification. | As above, our focus has not been on individual grants, and we did not have the necessary resources to put in place a systematic process to build grantees’ capacity on using the M&E frameworks or ToCs. | The MA supported grantees with monitoring (a monitoring officer was present in each of the four RTs) and took the decision not to put in place country-level ToCs for monitoring purposes. |
| Proposals for the provision of a mid-point review report which answers the EQs indicatively and supplies formative recommendations for the remainder of the Fleming Fund. | At the time of writing our inception report in December 2017, we did not think that a mid-term formative report delivered in late 2019 would meet the DHSC needs as our understanding at that time was that a formative report produced in late 2019 would be too late to influence the overall strategy of the Fund, since nearly all grants would have been approved at that point and so the room for change would be limited. | Implementation timelines have subsequently evolved, and we did submit a formative deliverable in January 2020. |
| Proposals for the provision of a final summative evaluation report that answers the EQs agreed in accordance with Milestone/Deliverable 3. | At the time of writing our inception report in December 2017, we did not think that a summative report in early 2022 would meet the DHSC needs. Given the evolving implementation timelines, we have revised the timing for the summative report in order to maximise its usefulness to the DHSC. | This summative report was submitted in draft form in December 2022 and in its final form during Q1 2023. |
| Governance arrangements for the evaluation | The DHSC decided that its Project Board will primarily be responsible for the governance of Fleming Fund decisions, and that there was not going to be a Steering Committee as indicated in the ToR. The DHSC expectations were that both the MA and the Evaluation Supplier attended the Project Board on an ad hoc basis when there are key agenda items that would benefit from their direct involvement. This has not been the case. Instead, the Evaluation Supplier has had multiple interactions with the DHSC Technical Advisory Group (TAG). | No material implications were noted from this decision. |
| Evaluation Question and Indicative Evaluation Sub-Questions | The ToRs include proposed EQs and indicative sub-questions, these were used to guide the development of the final EQs that were used throughout the evaluation. | As noted, EQs formed the basis for evaluation design, data collection, analysis, and reporting. |
| Production of evidence briefs (formative report) | Evidence briefs were not produced following the formative report | Instead learning products were created for key stakeholders and public use including dissemination of findings to the DHSC, MA, and TAG, learning products such as blog posts, contributions to thematic workshops, and peer reviewed journal papers. |
| Contracting Phases and Outputs | The evaluation period was extended until March 2023, in line with an overall no cost extension to the programme. - Phase 1 | There was a deviation from the deliverables and timings outlined in the ToRs. The final deliverables and timings were as follows: - Report 1: January 2019 Formative report including judgements for the DHSC, MA, and HMT to support a decision on future Fleming Fund funding. - Report 2: Formative deliverable for the DHSC, MA to support adaptive learning in key windows of opportunity, submitted January 2020. - Report 3: Formative deliverable requested by the DHSC to inform the design of the second phase of the Fleming Fund (specifically focusing on Fleming Fellows, RGs and Use of data) and identify any potential adaptations for the remaining time of phase 1, submitted March 2021. - Report 4: Summative report for the DHSC on whether the grants programme is likely to meet its overall objectives (covering all the six EQs), submitted December 2022. |

The above departures had no material impact on the credibility and robustness of evaluation findings. All mitigation strategies were designed to ensure the evaluation was able to deliver timely, high-quality outputs, and to maximise their utility for the DHSC and other key audiences.

Annex 12: Ethics and Safeguarding

Ethics

The design of this evaluation complies with the established principles and guidelines on ethical standards. Our initial evaluation design was informed by the DFID’s 2011 Ethics Principles for Research and Evaluation and the Review of Ethics Principles and Guidance in Evaluation and Research commissioned by DFID and delivered in 2015. It was subsequently informed by FCDO Ethical Guidance for Research, Evaluation and Monitoring Activities. We have set out below how our evaluation design complies with these principles and guidelines.

| Ethical principle | How we addressed them in our evaluation |
| --- | --- |
| 1. Researchers and evaluators are responsible for identifying the need for and securing any necessary ethics approval for the study they are undertaking. This may be from national or local ethics committees in countries in which the study will be undertaken, or other stakeholder institutions with formal ethics approval systems. | The evaluation did not require the collection of primary data from key populations or reviews of such data. Therefore, it was not necessary to use an institutional review board to review the evaluation design and protocols at either the global or national level within the 16 countries. |
| 2. Research and evaluation must be relevant and high quality with clear developmental and practical value. It must be undertaken to a sufficiently high standard that the findings can be reliably used for their intended purpose. Research should only be undertaken where there is a clear gap in knowledge. Evaluations might also be undertaken to learn lessons to improve future impact, or to meet DFID’s requirements for accountability. | Relevance was ensured through the use of an evaluation framework based on clear EQs designed to meet the evaluation objectives. Quality was ensured through a number of mechanisms, including internal QA review by the Senior Advisor and a senior Itad staff member, and support from an independent technical panel of experts (EAG). The evaluation team utilised opportunities to feed in findings from the evaluation to key Fleming Fund governance structures, including the DHSC Project team and TAG which supported the evaluation’s utility focus. The formative focus of the early evaluation outputs (2018 and 2019), and the mechanisms to support adaptive management enabled lessons to be fed into the implementation of the Fleming Fund by the MA. And the increased focus on accountability from 2020 brought evidence to support decision making by the DHSC and HMG more broadly, specifically around investment into a second phase of the Fleming Fund. |
| 3. Researchers and evaluators should avoid harm to participants in studies. They should ensure that the basic human rights of individuals and groups with whom they interact are protected. This is particularly important with regard to vulnerable people. The well-being of researchers/evaluators working in the field should also be considered and harm minimised. | The evaluation did not require the collection of primary data from key populations or reviews of such data. Participants in this evaluation were engaged in KIIs only which minimised the risk of harm to participants. This was constantly reviewed throughout the evaluation. The evaluation team also followed clear guidelines on confidentiality and consent, and feedback of evaluation findings to participants was promoted. Itad takes the safety and security of staff and contractors extremely seriously. Itad has a Risk Management Framework that helps to provide a safer and more secure working environment and minimises and manages risk. Itad has a Travel and Security committee, made up of senior management, who provides board-level engagement and oversight. To ensure that Itad’s duty of care is integrated into the activities of every department of the company, the TSC conducts independent reviews and audits of our processes. |
| 4. Participation in research and evaluation should be voluntary and free from external pressure. Information should not be withheld from prospective participants that might affect their willingness to participate. All participants should have a right to withdraw from research/evaluation and withdraw any data concerning them at any point without fear of penalty. | Participants of KIIs were informed in advance about the aim of the exercise and their involvement, so they can decide whether or not they would like to participate. Before interviews were conducted informants were informed about the background and focus of the evaluation and the objective of the interview, they were also informed that participation was voluntary and they had the right to withdraw from research/evaluation and withdraw any data concerning them at any point. During the KIIs all respondents were asked for verbal consent as well as consent to take notes during the interview or for the interview to be recorded. There was no reward or compensation structure provided for participation in the KII. |
| 5. Researchers and evaluators should ensure the confidentiality of information, and privacy and anonymity of study participants. They should communicate clearly to prospective participants any limits to confidentiality. In cases where unexpected evidence of serious wrongdoing is uncovered (e.g. corruption or abuse), there may be a need to consider whether the normal commitment to confidentiality might be outweighed by the ethical need to prevent harm to vulnerable people. DFID’s fraud policy will apply if relevant. | The study involved primary data collection from some key stakeholders, mostly in the form of KIIs For all participants, informed consent procedures were followed. This was done verbally using a formal script to ensure consistency by evaluators. Where necessary this was translated into the appropriate language. Informants were asked for consent to conduct the interview, consent to take notes, and consent to record the interview. During the process of consenting, the respondents were asked if they would prefer anonymity while reporting the information, and all personal identifiers were removed before the wider circulation of the interview notes. Quotes or respondents used in the Summative reports were anonymised and checked to ensure they were a fair and accurate summary of what the respondent said. Participants were free to cease their participation at any point. Full details of our consent procedures (used on other similar evaluations), including draft recruitment scripts, consent and assessment forms, and a Code of Conduct for Itad evaluators, were made available on request. The evaluation used a large amount of secondary data, much of which was not open access and some of which was confidential. All primary and secondary data was managed carefully and in line with the following: - Interview notes and recordings were stored in a secure system and never shared via email or any other means. - At no stage were interviewees’ personal details, or any information which could identify the respondent, shared with anyone outside the research team. - The evaluation team did not share audio recordings with the DHSC, MA or anyone outside of the core evaluation team, due to our obligation to preserve respondent anonymity. - Recordings and data were stored securely and will be destroyed once the Summative report has been submitted and approved. |
| 6. Researchers and evaluators should operate in accordance with international human rights conventions and covenants to which the United Kingdom is a signatory, regardless of local country standards. They should also take account of local and national laws. | The evaluation team followed international human rights conventions and covenants at all times. |
| 7. DFID-funded research and evaluation should respect cultural sensitivities. This means researchers need to take account of differences in culture, local behaviour and norms, religious beliefs and practices, sexual orientation, gender roles, disability, age and ethnicity, and other social differences such as class when planning studies and communicating findings. DFID should avoid imposing a burden of over-researching particular groups. | All the team members had experience of working in a diverse range of contexts and were cognisant of issues around cultural sensitivity. To prevent language from being a barrier for participants, translators were recruited to assist with the KIIs and the country-level debriefs were translated and shared with those who participated in the evaluation |
| 8. DFID is committed to the publication and communication of all evaluations and research studies. Full methodological details and information on who has undertaken a study should be given and messages transmitted should fully and fairly reflect the findings. Where possible, and respecting confidentiality requirements, primary data should be made public to allow secondary analyses. | Paragraph 6 of the Joint strategy on ways of working between the MA and Itad (Inception report Annex 6) states that: ‘All data collected by the MA and Evaluation Supplier will be owned by DHSC. Datasets will be made publicly available as per the agreed M&E Communication Plan between the parties and approved by the DHSC.’ The evaluation's Communications Plan reflected the following principles: DHSC, MA, and ES must be notified in advance of any external communication from any of the three parties regarding the independent evaluation. All proposed external communications need to be circulated at least two weeks before they are published, wherever feasible, and earlier if possible. Deliverables and publication: Respecting the independence of the ES, the disclosure of evaluation reports and any communication of parts of a formal report is a matter between the DHSC and ES. The ES will publish all deliverables independently, with full acknowledgement of the contributions of MA and others as appropriate. The MA has had the opportunity to comment on any draft evaluation reports before their release in the public domain. We also developed an Information Transfer Agreement regarding the use of data coming out of the programme. This was updated in 2022. Whilst this was covered by the contracts that the MA and ES have with the DHSC, it was considered useful to have something explicit and direct between the two parties. It was the responsibility of the organisations to ensure that all individuals within their teams are compliant with this document. In the event of any conflict between the terms of this agreement and the terms and conditions of the agreements between the ES and DHSC or between the MA and DHSC, the terms and conditions of the latter agreements took precedence. |
| 9. Research and evaluation should usually be independent of those implementing an intervention or programme under study. | The evaluation team consortium has had no conflict of interest (CoI) in undertaking this work, and we have set out below how the evaluation will be managed and governed to protect the independence of the evaluation process. |

Safeguarding

The evaluation was conducted according to Itad’s safeguarding policy which all members of the evaluation team are expected to comply with. Itad recognises that the care and well-being of those that we work with, and of our staff, is paramount and that everyone has the right to be protected from all types of harm. Itad espouses a broad definition of safeguarding, which is to prevent, protect and respond to harm caused by sexual exploitation, abuse, harassment and bullying.

Itad’s principles in relation to safeguarding are:

- Do no harm;

- Promote equality;

- Act with integrity, ensuring transparency and accountability;

- Respect confidentiality when required;

- Take individual responsibility for promoting safeguarding;

- Take a survivor-centred approach.

As an organisation, Itad’s leadership is committed to:

- Prioritising the approach to, and seriousness of dealing with safeguarding issues, ensuring that appropriate steps are taken in a transparent and accountable way;

- Providing a safe and supportive culture so that staff, consultants and partners are able to raise issues and concerns related to safeguarding appropriately;

- Sharing information and training about policies and good practice with all who work for us;

- Sharing information and reporting any concerns or issues with relevant agencies;

- Ensuring checks are made when recruiting staff, subcontractors and consultants.

Behaviours that are expected from those covered under the scope of this policy are outlined below, these are reinforced by our Safeguarding Code of Conduct:

- Accountability – If you have a concern then respond to or report it, never assume someone else has or will.

- Advocacy – Help others to put forward their own point of view. Promote a culture of listening to ensure that staff and others feel able to raise issues in confidence, knowing that they will be listened to and responded to.

- Inclusion and equality – every individual is equally important and valuable and should be treated in that way. Everyone has an equal right to protection from harm and abuse.

- Act quickly – take action and provide support as soon as a problem emerges before it gets any worse.

- Vigilance and understanding – it is important to take the time to understand situations and be alert so we can notice when something is not right and respond appropriately.

- Confidentiality – depending on the nature of the situation it may be appropriate to act with a high degree of confidence to protect the anonymity of individuals involved.

This Code of Conduct sets out a minimum standard in terms of behavioural expectations of the evaluation team. The Code was and is applicable at all times. This not only involves respect for the rights and feelings of others but also demands that individuals refrain from any behaviour that might be harmful to themselves, co-workers, and/or Itad, or that might be viewed as such by the public at large.

Whilst recognising that local laws and cultures differ considerably from one country to another, Itad works internationally, and therefore the Code of Conduct is developed from international standards. The evaluation team is expected to act within local law as a minimum wherever they operate, except where the Code of Conduct is more stringent, in which case the Code applies.

COVID-19

Due to COVID-19, KIIs for the summative evaluation were a mix of remote and in-person interviews. At all times, national and local COVID-19 guidelines and regulations were followed by the evaluation team as were Itad’s duty of care policies and our commitment to uphold Itad’s ‘Do No Harm’ approach. Where in-person interviews were possible, interviewees were offered a choice of in-person or remote interviews. If a KII was conducted in person a risk assessment was completed with Itad’s travel and security team and steps were taken to reduce the risk of transmission, these included guidance on conducting KIIs in open spaces where possible, maintaining distance where possible and the wearing of personal protective equipment.

Ensuring independence and managing conflict of interest

In Annex 14, we highlight that our organisational structure and accountabilities and responsibilities are designed to promote inter alia the independence of the evaluation. Here we provide further detail on our approaches to ensuring independence, and managing CoIs.

Organisational independence ensures that the evaluators are not under the influence or control of those who have decision-making responsibility for the activities being evaluated, and that evaluators have full access to the information they need to fulfil their mandate. This evaluation design includes:

- Ensuring the evaluators had clear and frequent reporting lines directly to the relevant DHSC Fleming Fund Project Team members.

- Ensuring that the design and programming of evaluation activities were kept distinct from management interference or budget restrictions.

- Liaising with the Itad Project Management and QA Team, which can independently verify that there were adequate resources to conduct the evaluation to a high standard.

Behavioural independence relates to the ability of the individual evaluators to issue candid, uncompromising, and high-quality reports, and report their findings to the highest levels without management-imposed restrictions. The approach to guaranteeing behavioural independence included:

- Ensuring the Team Leader and other senior evaluators were of an appropriate grade and title. We selected the team carefully to ensure they had appropriate experience and seniority; CVs for all team members were shared within the inception report and the CVs of additional team members were made available. Any junior staff involved in the fieldwork were specifically briefed on ensuring independence or accompanied by a more experienced evaluator.

- Focusing the evaluation on issues of materiality that have substantial relevance to the evaluation and development effectiveness.

- Recording and reporting any instances where the evaluators were denied unrestricted access to staff and records.

- Having clear ethical guidelines for staff that set out the importance of evidence-based judgements and conclusions.

Protection from outside interference was facilitated by organisational independence and relates to managing all stakeholder relationships to ensure the independence of the evaluation. The approach to mitigating outside influence included the following:

- Ensuring that all key stakeholders had an opportunity to comment on drafts and material relating directly to their activities and record their disagreements or comments if relevant.

- Reporting significant delays if it was suspected that they are intended to deliberately hinder the evaluation.

- Clarity that if any undue pressure was put on any member of the evaluation team by a DHSC official, it would be immediately reported to the appropriate office in the DHSC.

We recognise that, particularly with M&E services, it is very important to proactively engage with the issue of potential CoI. We take the issue seriously, and we have given it significant consideration. A CoI policy and management principles strategy was developed for this assignment as follows:

Policy Statement: Itad will minimise and avoid the potential for CoI by managing the contract according to the following principles:

- Our first principle is to avoid CoI. We will apply a precautionary principle, erring on the side of caution where there appears to be conflict.

- Declaration of interest: All team members will be expected to self-declare any known actual or potential CoIs at the earliest possible opportunity.

- Responsibility rests with Itad to satisfy itself regarding team member eligibility.

- The principle of transparency will apply in all cases, particularly where there is doubt about the existence of CoI. We will consult with the Fleming Fund Project Team and Steering Committee where there is uncertainty.

- Itad will undertake CoI assessments as a primary activity on all evaluation activities that arise under the contract.

The Itad Project Management and QA Team have a mandate to review the performance of the evaluation against these standards, and if necessary, report any concerns both to the Itad Board, and to the DHSC. The Fleming Fund Project Team and Project Board were able to have the final say in adjudicating assessments of potential CoI.

Interaction with the MA was governed through a Working Protocol Agreement between the MA and Itad. An initial version of this protocol was jointly developed by the MA and Itad and laid out ways of working throughout the life of the project, roles and responsibilities, and the process for resolving disputes.

- Annex 13: Risks, challenges and mitigating strategies

Through the quarterly reporting process and as and when requested by the DHSC, Itad has identified risks and opportunities, instigated and monitored mitigation actions through living risk registers. The risk register includes relevant information for the DHSC, including detailed descriptions of the risk, its causes, effects, and impact. The risks are identified and scored based on the DHSC RAG rating tool. Mitigating actions are detailed and followed up, with risk RAG rating reviewed quarterly. Risks are discussed with the DHSC at the quarterly review meetings, mitigating actions are taken as appropriate and residual risks are understood and managed. The current full risk register used throughout the evaluation is shown in Table 45 below.

Table 45 Risks and mitigating strategies

| Risk Type | Risk Description | Mitigating Actions | Risk Rating |
| --- | --- | --- | --- |
| Technical | Risk: Outcomes are not evident within the timeframe of the evaluation Cause: Transformation may take several years to occur, and evidence may not be seen until some time after that. This project will report within a much shorter timescale. Limited time to get beyond outputs in ToC/conceptual framework Effect: Unable to answer outcome aligned EQs, we will be reliant, in many cases, on early or interim indicators/predictors of transformation by the end of the five-year phase. Impact: Deliverables not meeting contract specification | Mitigating Actions: 1. The evaluation team (evaluation team) uses Contribution Analysis to explore whether outcomes that have not become apparent yet are likely to be delivered - so the design of the evaluation is predictive in nature. 2. Inception period meetings educate partners on the nature of the evaluation and what is evaluable. | G |
| Technical | Risk: Bias in the selection of KIs and other sources of evidence, either publication bias (where negative or unwelcome findings from evaluations have not been published) or selection bias. Cause: The evidence base will be incomplete and all evidence will not be included in evaluations. Effect: Lack of awareness of gaps in evidence/findings. The lack of evidence may introduce bias. Impact: Reduction in the quality of findings. This impacts the Fleming Fund’s effectiveness if they act upon these incomplete findings. | Mitigating Actions: This will mainly be a challenge for evaluating the Fleming Fund’s contribution to the delivery of country outputs. We will manage the risk of selection (confirmation) bias within analyses of experience in individual countries through: 1. A rigorous process of assessing whether there are alternative explanations (theories of causality) for what is observed. 2. A transparent and systematic process of internal QA that will focus on whether or not, credible data is available and has been well triangulated to support claims made on the contributions of the Fleming Fund. 3. Presentation and discussion of the evidence and contribution story developed with key country-level stakeholders to allow them to assess whether the evidence is supported by their experience, and if not, why. We will manage the risk of confirmation bias in presenting findings across the countries in which the Fleming Fund works through: 4. Using a systematic and transparent process of cross-case analysis, supported by internal QA. 5. In cases where we do not have evidence across the whole portfolio, generalising through theory and only generalising to the degree that qualitative good practice allows us to. | G |
| Technical | Risk: Not possible to get sufficient evidence to answer priority EQs. This risk has increased due to COVID-19 and the need to move from in-country data collection to remote data collection and the increased difficulty of accessing stakeholders, some of whom are refocusing on COVID-19. Cause: Data unavailable, question unclear in scope, activities dependent on further work Effect: The budget runs out and work has to be reduced or the budget reallocated. Can not deliver quality products. Evaluation does not meet its purpose. Impact: Breach of contract. Trade off with other areas of evaluation. Reputational damage. | Mitigating Actions: 1. Careful refining and prioritisation for each EQ and relevant indicators. 2. A clear, resourced plan for gathering data against each EQ, signed off by DHSC and approved by the MA. 3. Management of monitoring system to deliver data - following M&E framework. Regular interaction with the MA and the DHSC to identify data availability and respond to changes in reporting systems. Adaptation of evaluation approach and data collection tools to mitigate anticipated paucity of data from routine reporting. 4. Reformatting of evaluation approach to ensure data can be collected remotely in 2021 and 2022, working with the MA to support access to stakeholders and enable answering of EQs. Contingency Plan: Itad to keep under close review during 2022. The MA’s plans for within the country (contribution of all grants into a single results framework) and cross-country analysis become clearer. We expect to be able to gather sufficient supplementary information through document review and KIIs to produce a quality deliverable at that time. The third country visits completed in 2022 have drawn more heavily on the MA’s reporting. | A |
| Data | Risk: Implementing partners/MA grantees in the country do not share information Cause: Due to the protection of intellectual property and the competitive nature of contracts Effect: Incomplete evidence base Impact: Poorer deliverables | Mitigating Actions: 1. Creating buy-in from implementing partners during the planning process by checking plans with them and keeping them informed. 2. Country leads provide regular (weekly) updates to Team Lead and Project Manager and highlight where there is a lack of engagement. 3. Inclusion of quality of M&E framework, M&E plans, and capacity of implementing partner staff in the selection of projects which will contribute to the evaluation (The MA’s M&E team is confident that the selected projects have the capacity to provide high quality work). 4. Support for Implementing Partners with methodologies through guidance, M&E clinics and (where necessary) 1:1 support to incentivise engagement. 5. Drawing on DHSC support where MA/implementing partners are not meeting contractual obligations for evaluation quality. | A |
| Data | Risk: Monitoring data provided by the MA not of sufficient quantity or quality Cause: grantee failure in country, not complying with M&E framework and monitoring plans, poor M&E capacity in MA or grantees Effect: reduced quality of deliverables, delayed delivery Impact: findings not as robust, breach of contract | Mitigating Actions: 1. Provision of support during early implementation to ensure Implementing Partners have a minimum standard of M&E against the Itad and MA M&E Framework 2. Regular coordination (as required) with the MA to ensure ongoing QA of project monitoring and results reporting data including meetings with the MA in April 2019, and September 2019 and discussing plans for aggregate/cross-country reporting (ongoing discussion). 3.Agreed M&E Guidance aims to create a clear and comprehensive programme-level M&E framework within which all projects will sit and contribute, helping to ensure the protocols for data collection are clear and robust. 4. Ways of working protocol which set our respective responsibilities in section 4 including a QA and sampling system 5. Implementation plan which sets out expectations and agreement regarding data gathering and responsibilities 6. Maintaining a close working relationship with the MA through regular meetings 7. Supporting monitoring work through effective agreed terms of agreement. 8. Ongoing conversation about tracking KPI performance (relating to EQ1 and EQ5), VfM and sustainability - as VfM approach is firmed up and exit plans start to be finalised. Also to keep under review the extent to which CG2s and RG2s start to trigger standard indicators from the indicator compendium. We continue to hold regular meetings with the MA M&E team to understand plans, in particular for cross-country analysis. 9. Pilot of summative data collection approach, and revisions for full sample based on experience. Contingency Plan: The MA will be responsible for the design, collection, quality control, and delivery of monitoring data relating to the Fleming Fund grants programme in accordance with the agreed M&E Framework. Where feasible and realistic the nature and type of these data will need to be synergistic with the requirements of the ES, as it will be used in the delivery of the evaluation of the Fleming Fund grants. The MA and the ES will instigate and agree on a QA mechanism so that monitoring data delivered by the MA can be sampled and checked by the ES on a periodic basis. This will be included in the implementation plan. Any issues arising regarding data quality will be jointly assessed by the parties, and agreed measures are taken as soon as possible to resolve the quality issues. Assessment and measures of data quality standards will be pre-agreed between the MA and ES and described in the M&E Framework. In the event of a disagreement or dispute between the MA and ES regarding data quality that cannot be resolved between the parties, they agree to engage the DHSC (if they are not already engaged) at the earliest opportunity. Itad to keep under close review on an ongoing basis as the MA plans for cross-country analysis become clearer. Based on data received for Nepal (2019) it is clear that a) October reporting would include a number of important changes and increase in volume; b) KPI reporting supplements quarterly reporting in important ways we will need to engage with the DHSC on the plans for this in 2021 and 2022 (including to see whether mid-term KPI reporting is feasible for mid-2022); c) reporting on VfM and sustainability, and for the Fellowship scheme continues to evolve. We expect to be able to gather sufficient supplementary information through document review and KIs to produce a quality deliverable at that time. | A/R |
| Data | Risk: Data security compromised Cause: Itad’s system is hacked by a malignant source, or there is a failure to ensure safe information management results in a loss or corruption of data. Effect: Confidential data, is corrupted and/or lost. Impact: cost of recollection, undermines product quality | Mitigating Actions: 1. “Cyber essentials” precautions, incl. secure offsite backups 2. Use of M-files as knowledge sharing platform – moved to TEAMS in 2020. Impact of COVID-19: COVID-19 creates new compliance-related risks. An increase in remote working increases the chance of non-compliance and the risk of confidential data leaks. Internal changes as a result of altered working practices potentially limit the effectiveness of their IT Security tools. Contingency Plan: 1: Working practices and IT security tools are reviewed on an ongoing basis by the IT department. 2: Evaluation team refreshed in compliance and safety procedures. 3) Ongoing guidance to ensure compliance and best working practices. 4) Regular update of passwords. | G |  |
| Relationship | Risk: Independence of evaluation undermined Cause: undue influence by the MA or DHSC on the process of collection, analysis, and reporting to influence findings and recommendations Effect: bias in evaluation findings and recommendations Impact: The independence of the evaluation is compromised meaning findings have less weight to external eyes and deliverables of poorer quality. Loss of confidence and reputation | Mitigating Actions: 1. Way of working protocol and information sharing agreement with MA: the evaluation team engaged closely with MA to ensure that they understand our role. This has included a presentation of the objectives, methodology, and scope including the boundaries of the assignment. 2. Further work to orientate grantees and other stakeholders to the role of the evaluation team and its approach and methodology. 3. M&E framework to develop and agree on a clear division of responsibilities in M&E functions. However further work is required early in the implementation phase to agree on ongoing detailed data collection responsibilities. 4. The Summative Evaluation Report will include a summary of evaluation findings in clear and accessible language which may be used for the wider dissemination of Itad independent findings by DHSC and external stakeholders. 5. There is an established and ongoing development of governance structure, designed to mitigate influence from any one party on the independence of the evaluator 6. Inception Report details planned activities and methods for the implementation period, this has been led by Itad as an independent evaluator 7. The EAG includes independent actors who will discuss the progress of the evaluation, asking "why" actions are taken with a remit including ensuring the independence of the evaluator. 8. Evaluation QA and Learning Service (EQuALS) - reports will be assessed using the equivalent of EQuALS framework as part of Itad's QA, which is external to the project and professionally independent. 9. In our first evaluation deliverable we were very careful not to make recommendations so that we cannot be accused of subsequently evaluating our own prescriptions. The MA and DHSC were given information in that report to enable them to reflect and decide on the best course of action to address any concerns raised. | G |  |
| Relationship | Risk: The DHSC requesting a high level of interaction or tasks that are beyond the original ToR Cause: As the programme is utilisation focused and about co-creation, the level of interaction between the DHSC and Itad is likely to be high. Poor communication between the DHSC, Itad and the MA. Too many unplanned demands. Effect: High transactional cost. Resources taken away from required deliverables; work undertaken not then accepted by the DHSC. Breach of contract. Impact: Time wasted; progress slowed. Deliverables delayed or quality not as high as expected. Unable to deliver to specification and within budget. Damage to relationship with DHSC and MA | Mitigating Actions: 1. Agreed ways of working with DHSC 2. Clearly defined and understood work plans, clearly signed off by the DHSC and understood by the MA prior to inception/implementation. 3. Appropriate resources allocated to project management 4. Not all payments linked to deliverables 5. Close and good working relationship with DHSC maintained 6. Good communication (including regular meetings) and ways of working protocol agreed with the MA 7. Sound budget and contract management by Itad Project Manager and Project Officer to ensure that there is a good change control procedure for agreeing on key changes in the scope and trajectory of the evaluation. | A |  |
| Relationship | Risk: Difficulty brokering knowledge or organising meetings in priority countries where we have no regional partners or local knowledge Cause: no infrastructure or contacts on the ground. Additional risk due to COVID-19 means stakeholders in the country and members of the DHSC may be unavailable for a protracted period of time. Effect: insufficient quality data gathered Impact: poorer quality of findings and deliverables | Mitigating Actions: 1. MA support to logistics 2. MA support to access KIs and utilise convening power 3. Country visits are planned to ensure consistency in at least one team member per country where possible 4. The evaluation team has a revised approach, working with in-country consultants, this supports developing relationships with key stakeholders and supported remote/hybrid data collection as required. | A |  |
| Relationship | Risk: The MA is not open to the formative nature of the evaluation Cause: The MA is too busy or otherwise opposed to an ongoing, close formative relationship with the evaluation team Effect: evaluation team struggles to gather the right data at the right time, and findings are not considered for the adaptive management of the programme. Conflict with the MA. Impact: Wasted resources, breach of contract | Mitigating Actions: 1. Way of working protocol sets out details of the formative nature of relationships and agreement that evaluation considerations are ‘embedded’ in the programmes across the project cycle. This means clear assessments of the evidence for what does or does not work in the initial stages of programme design, analysis of baseline data, and effective evaluation over the life of the programme and beyond. 2. The evaluation Implementation plan will further elaborate the adaptive management focus of the evaluation as a joint deliverable 3. Strong relationships developed and maintained across the matrix of relationships 4. We have a strong learning and dissemination plan to create opportunities for learning and reflection for both the MA and the DHSC. | A/G |  |
| Relationship | Risk: DHSC/HMG priorities may change, and new issues may emerge over time rendering existing plans less useful or even inappropriate. Cause: Change of government priorities, change of government Effect: Work already completed is no longer of great value. Resource and budget implications for continuation. Reduced buy-in affects access to KIs Impact: Evaluation less relevant and useful. Waste of resources. Reputational damage. | Mitigating Actions: 1. The Evaluation will need to be agile in responding to emerging issues and changing priorities. 2. EQs are articulated so that they are likely to remain useful and relevant regardless of changes 3. EQs are refined with senior stakeholders in the DHSC and HMG 4. We are providing support with the business case for continued funding for the Fleming Fund through a Nepal case study. Contingency Plan: As the evaluation has progressed, we have discussed with DHSC any changes to their requirements, in terms of particular areas of emphasis or new/emerging questions and have responded to these where possible - e.g. ICAI questions, supporting ToC workshop to contribute to a 10-year strategy. We will continue to do this, including as we plan for the Summative evaluation deliverable. If the DHSC/HMG priorities change we will agree, with the DHSC, on the best way to deliver what is needed from the evaluation based on the most up-to-date understanding of what is/will be available at the time of the summative Deliverable. | A |  |
| Relationship | Risk: Delays in project implementation coupled with unpredictable/reduced funding for the evaluation limits the quality and scope of the evaluation Cause: poor management, approvals, national circumstances, political events Effect: reduces the evaluation team's ability to produce evidence A no-cost extension for the MA without a costed extension for the evaluation team would result in a similar risk as the core costs of running the evaluation for an extra year would reduce the budget available for evidence generation and uptake activities Impact: reduction in the responsiveness of evaluation/quality of deliverables | Mitigating Actions: 1. A no-cost extension to implementing partners has been agreed upon. The next steps are to include a costed extension for the evaluation team (submitted), which would allow time for the projects to finish their implementation and for the evaluation team to complete research and evaluations based on a more advanced set of results. Contingency Plan: As the evaluation has progressed we have discussed with DHSC any changes to their requirements, in terms of particular areas of emphasis or new/emerging questions, and have responded to these where possible - e.g. ICAI questions, supporting ToC workshop to contribute to a 10-year strategy. We will continue to do this, including as we plan for the Summative Evaluation. If it transpires that project implementation has been substantially delayed - which is outside the control of the evaluation - we will agree with the DHSC on the best way to deliver what is needed from the evaluation based on the most up-to-date understanding of what is/will be available at the time of the summative deliverable. | A/R |  |
| Financial management | Risk: Overspending /Underspending against the budget Cause: As it is a complex programme with multiple budget streams and currently undefined work areas, there is a risk of overspending/underspending through different phases. Effect: - The programme runs out of money and has to reduce work/vary delivery in certain areas. Deliverables not optimised in terms of delivering quality on time. Breach of contract. -The programme returns unspent funding at the end of the project; with the implication that evaluation activities were not fully executed to deliver optimal products. Impact: Damage to reputation with HMG. The project becomes non-commercial. Lack of confidence in Itad's resource planning and management. | Mitigating Actions: 1. Dedicated Project Officer and Project Manager supporting the Team Leader and Project Director with regular, accurate and easy-to-understand budget and utilisation reports 2. Regular and tight budget monitoring for all outputs. 3. Monthly (internally) and quarterly (with DHSC) review of budgets and clear forecasting. 4. Regular accurate invoicing of subcontractors 5. Discussion to be tentatively had with the DHSC about the shifts in the budget to cover the additional time required within the revised evaluation approach and the decrease in expenses, subject to COVID-19-related restrictions on travel. 6. Impact of budget decreases/shifts to be outlined to the DHSC. Changes to the delivery/deliverables are to be agreed. | A |  |
| Financial management | Risk: Payment delay from the DHSC if deliverables are not agreed Cause: Failure to communicate progress with the DHSC between deliverables, slow feedback process in the DHSC, and poor quality deliverables which are not responsive to requirements. Effect: Cash flow insufficient, breach of contract Impact: Cannot pay suppliers/subs, lose suppliers, damage reputation, conflict with the DHSC. | Mitigating Actions: 1. Ensure that the deliverables have check-in points, so we are always in agreement with DHSC on what we are delivering, and the rounds of feedback expected. 2. Allow space in the budget for delayed payment of invoices. 3. Deliverables proofread and QA'd by an external person with experience in EQuALS QA with final approval from Jon Cooper, Itad Director 4. Continuing cognisance of contract requirements | G |  |
| Financial management | Risk: Fraud/corruption results in loss of funding Cause: Insufficient controls and financial management lead to fraud. Effect: Loss of funds, inadequate resources to complete the work Impact: Reduction in the quality of deliverables, damage to the relationship with the DHSC and the MA | Mitigating Actions: 1. Strong project management processes, Project Manager, Project Officer, and accountant 2. Itad have robust contracting and accountability processes with subcontractors Impact of COVID-19: COVID-19 creates new compliance-related risks. An increase in remote working increases the chance of non-compliance fraud and the urgent nature of COVID-19 responses increases the risk of external fraud. Risks include: 1) Organisation misrepresenting the impact of the pandemic on their financial records. 2) Opportunities to hide mismanagement or misappropriation of assets. 3) Urgent nature of COVID-19 responses increases the risk of external fraud (Phishing, fraudulent products, and services) | G |  |
| Team | Risk: Core team changes within the consortium ('Key personnel'). Cause: staff move on to other work, and conflicts of interest emerge Effect: Gaps in resources and institutional knowledge. Impact: Reputation with partners may be damaged. Loss of knowledge during handovers, affecting the quality of the evaluation. | Mitigating Actions: 1. Ensure sharing of knowledge so no gaps are left 2. Develop a system of inducting new evaluation team members to the programme 3. Maintain a pool of experts to call on to help assure and guide key elements of our work. 4. Make the programme an enjoyable piece of work 5. Orient all evaluation team members to the expected code of conduct, expected behaviours and Itad values 6. Utilise informal and formal dispute resolution mechanisms through the Project Director to deal efficiently with disputes Contingency Plan: 1) Strong project management processes, Project Manager, Project Officer and accountant 2) Robust contracting and accountability processes with subcontractors 3) To prevent external fraud all project-related financial and purchasing decisions are limited to the Project Director/Project Manager. Financial processes are managed by finance team. 4) All invoices and receipts are logged digitally and the Project Director/Project Manager approves all invoices and receipts being logged. 5) Organisation continues to provide transparent financial reporting. 6) Discussions with DHSC on budget lines to ensure transparency and accountability. | G |  |
| Team | Risk: evaluation team members fail to deliver against the work plan and specification Cause: Consultants are offered other work/have clashes with other priorities, or become disinterested Effect: Gaps in resources may take a while to fill. Impact: Loss of knowledge during handovers, affecting the quality of the programme | Mitigating Actions: 1. Good communication with partners 2. QA processes to pick up on poor performance 3. Good induction and orientation to work, including clear instructions 4. Judgement by the Team Leader to match tasks with the demonstrable capacities of team members 5. Clear escalation procedure for addressing quality/conduct concerns and resolving them | G |  |
| Team | Risk: High staff turnover within the DHSC and gaps in key positions Cause: internal DHSC mechanisms Effect: Lack of continuity in our relationships, reduced momentum and buy-in. Impact: Time wasted, and progress slowed down | Mitigating Actions: 1. Regular communication with HMG. 2. Clear and easy-to-use background documentation completed by the DHSC to bring new staff up to speed easily with programme and evaluation approach and progress. 3. Develop a system of inducting new staff to the programme - by June 2017. 4. Encourage wider DHSC participation in evaluation key moments as they arise from time to time, and as elaborated in the implementation plan Contingency Plan: Itad has produced a one-pager for the new TAG. This can be supplemented with a presentation/workshop if further onboarding support is required. | A/G |  |
| Context | Risk: Crisis/disaster affects business continuity Cause: catastrophic event/act of God Effect: interruption/cessation of activities Impact: unable to deliver to specification/additional cost to recover | Mitigating Actions: 1. Business Continuity and Disaster Recovery Plan 2. Insurance | G |  |
| Context | Risk: Volatility in conflict-prone Fleming Fund countries, extreme events and/or health risks. Cause: prohibiting or limiting travel to undertake evaluation teamwork Effect: lost opportunity to gather data/lost resources, death or personal injury, partners unable to engage. Impact: unable to deliver on time or at the required quality, lost budget, impact on family and friends of death or permanent injury. | Mitigating Actions: 1. Continued monitoring of security and other threats in Fleming Fund countries and regions in liaison with the DHSC and MA. If security concerns are identified (as in Mali and Sri Lanka) we will look to switch to an alternative country (if there is flexibility to do so). 2. Itad maintains security procedures in place in accordance with its own duty of care and reserves the right not to assign its consultants to the field where the threat level is too high in its sole discretion 3. Risk assessments, security suppliers, liaison with the MA/DHSC 4. Country visits will be kept under review in 2022 due to COVID-19. Subject to discussion with the DHSC a combination of in-person and remote data collection may be required. 5. Continued monitoring of the situation and impact on country visits in liaison with the DHSC and MA. Intelligence from the DHSC and Foreign, Commonwealth & Development Office (FCDO) regarding COVID-19 and approvals for travel from ministries to be added into planning. Contingency Plan: 1. Given how the evaluation process and reporting has evolved, if there were to be a security situation in one of our final set of 16 countries (i.e. after all 16 first country visits had happened), we do not see this as a massive problem in terms of having meaningful evidence as the basis for evaluation findings (providing this applies to a limited number of our sample countries). We will explore three options: 1) look to see whether alternative countries could be included to maintain the sample at 16 (e.g. through organising a preparatory visit to establish baselines, key contacts etc but either shorter than first country visits and/or closer to second country visits); 2) discuss with the MA/DHSC whether the original country could be included in some through desk review/based on remote KIs and data from MA reporting; 3) proceed with a reduced sample and discuss implications with the MA and DHSC as well as noting any limitations in our reporting. 2. Continue working with In-Country Consultants to complete data collection in person and site visits, where it is safe to do so. | A/G |  |
| Technical | Risk: The theory-based approach may be misunderstood in some quarters; particularly among those who would prefer to see experimental evidence used to evaluate the Fleming Fund Cause: Theory-based evaluation does not provide proof of the cause of an outcome or the success or impact of an intervention. Rather, it generates contextualised learning to inform future decisions. Effect: this approach will not be suitable to address some questions asked of the programme, such as the actual outcomes resulting from it. Impact: Relevance and value of the EQs and confidence reduced. | Mitigating Actions: 1. Utilisation-focused approach adopted. The rationale for selecting this methodology will be communicated clearly through meetings during inception and in country and in the Implementation Plan. 2. It will be important to continue to explain the purpose of the Evaluation to stakeholders and why the theory-based approach is the best way to achieve that purpose. | Closed |  |
| Relationship | Risk: The DHSC's/MA's requirements for planning around the collection of monitoring data are too rigid and prevent Itad from being opportunistic in the field to gather data arising from unplanned sources such as user feedback or field-based learning. Cause: Lack of flexibility to take advantage of field-testing opportunities. Caution regarding allowing the evaluation team to engage with project-level users. Effect: Opportunities lost. Lack of VfM. Impact: Reduced evidence, quality of findings, reduced rigour | Mitigating Actions: 1. Develop an implementation plan and living work plan that builds flexibility into the process and review points to allow change of approach. 2. DHSC to provide flexibility to approach in order to allow the project to respond quickly to emergent opportunities. Itad to suggest any perceived inflexibility of obligations during the contracting for the implementation phase. | Closed |  |
| Technical | Risk: Wrong combination of data collection tools for evaluating the programme as a whole Cause: The evaluation needs to have the right mix of tools for data collection and analysis, including targeted impact evaluation methodologies for selected interventions and also tools to evaluate the MA’s overall approach. Effect: Given that the programme will support a number of interventions across several countries, there is a risk that data collection will be of variable quality depending on the different levels of complexity of different interventions and regional and geographical differences, which may complicate the evaluation of the overall approach. Impact: poorer quality data and less useful deliverables, reduced budget through overspending in the wrong areas | Mitigating Action: 1. Data collection tools and methodologies will be designed, piloted, refined and revised to ensure continued relevance. These will be developed during the scoping mission to Early Investment Countries. Theories as well as the validity of assumptions will be partly tested by the visit to the pilot country, Vietnam. 2. Plans will be detailed in the implementation plan following agreement on the M&E framework regarding data sources and collection methods, as well as roles and responsibilities. | Closed |  |
| Technical | Risk: The Implementation plan (evaluation component) will not meet expectations Cause: Lack of clarity on the content of the implementation plan developed by Itad. Effect: Product does not meet expectations Consequences: More extensive feedback on products/delay to approvals, and breakdown of trust. | Mitigating Action: 1. Regular communication with DHSC and MA 2. Scheduled collaborative Q&A sessions with lead staff on project 3. External and internal QA of implementation plan prior to submission 4. Opportunity for the DHSC and MA to feedback on the implementation plan prior to approval (within agreed timeframes) 5. Detailed explanation of product, quality, detail and plan within the implementation plan before submission. | Closed |  |
| Technical | Risk: Evaluation does not sufficiently take account of 'One Health' Cause: Good technical input from the core team on the laboratory/HH side but potentially a gap in agriculture, food, AH, and environment. Potentially a low risk depending on the portfolio of grants given. Effect: One Health approach was not considered complete, and aspects of the Fleming Fund were not evaluated. Impact: EQs not fully answered | Mitigating Action: 1. One Health aspects to be considered and approach detailed in the implementation plan. 2. Check-ins with stakeholders on the meaning of EQs in relation to One Health 3. Monitoring of grants given and their one health consideration 4. Continued discussion of evaluation approach with DHSC and MA 5. ToCs to take into account One Health aspects. 6. New Itad team member with AH expertise and talking to Kitty at Department for Environment, Food & Rural Affairs to bring in One Health expertise. | Closed |  |
| Data | Risk: Poor or variable quality of survey or interview data Cause: Survey data quality may be variable in different areas due to different challenges to data collection due to remoteness and other factors. Effect: Survey results are of insufficient quality or standard. Impact: Poorer quality deliverables, lost budget by repeat exercises | Mitigating Action: 1. The evaluation team has extensive experience conducting surveys and all the considerations will be taken to ensure robust survey use and QA processes. 2. The evaluation team builds capacity with the staff involved in the survey/interview work to ensure a common understanding of requirements (normalisation process). 3. Interview guides will be designed to gather the right information from KIIs | Closed |  |
| Team | Risk: The evaluation team lacks sufficient technical evaluative capacity to deliver the Evaluation Plan. Cause: poor selection, lack of availability, attrition Effect: inability to deliver Impact: poorer deliverables | Mitigating Action: 1. The DHSC and evaluation team will continue to manage detailed work plans to anticipate 'pinch points' where specific or additional capacity is needed and ensure the right people are engaged at the right times. | Closed |  |
| Relationship | Risk: Unable to engage effectively with the external world to disseminate findings Cause: Unable to broker an agreement to share evaluation products with third parties, conflict with MA messages. No budget for engagement and communication products, and no stated requirement in the proposal. Effect: Evaluation findings and recommendations not shared optimally or strategically Impact: VfM of evaluation reduced, public good diminished | Mitigating Action: 1. Clear communication plan - Project communications plan to be discussed in accordance with the DHSC's plans. Implementation plan to include engagement strategy for project-specific interested parties. 2. To work with DHSC to form an ongoing agreement regarding the utility of evaluation to the outside world and select appropriate dissemination audiences. 3. Make a proposal for additional funding to disseminate findings and evaluation products in a strategic way | Closed |  |

Annex 14: Evaluation Management and Roles and Responsibilities

This section details the management and governance arrangements that were established in order to ensure the effective operation of the evaluation team, and the delivery of high-quality, independent evaluation products within agreed timeframes and budgets.

Governance and management

Error! Reference source not found. provides an overview of the evaluation team, with key accountabilities and support relationships. The blue lines denote accountabilities, and the dotted lines show relationships. These are described in more detail below.

Figure 26 Governance and internal management structure for the Evaluation Supplier

Day to day engagement between the evaluation team and DHSC has been with the DHSC Fleming Fund Project Team.

The Project Director (Jon Cooper) was accountable for the delivery of the evaluation as agreed with the DHSC. The Team Leader was responsible for the technical delivery of the evaluation to quality standards. Accountability has been assured through a number of mechanisms, including:

- Regular reporting, in the form of:

- Informal monthly updates between the DHSC Fleming Fund Project Team and evaluation project manager to review progress against agreed work plans, discuss any budget concerns, and any other business as required;

- Quarterly reporting on progress against agreed activities and financial status against planned funding/budget – this has been both through the submission of a quarterly report document and a face-to-face meeting between the evaluation project manager, bringing in other members of the senior leadership team as required, and the Fleming Fund Project Team plus others as required by the DHSC;

- Annual reporting which includes a review of the total contract budget, work completed and work plan moving forward. The Annual Review was delivered as a presentation, a budget document, and was discussed in a face-to-face/remote meeting between the evaluation project manager and the DHSC Fleming Fund Project Team;

- Delivery of the evaluation products as follows:

- January 2019 Formative report including judgements for the DHSC, MA and HMT to support a decision on future Fleming Fund funding.

- Formative deliverable for the DHSC, MA to support adaptive learning in key windows of opportunity, submitted January 2020.

- Formative deliverable requested by the DHSC to inform the design of the second phase of the Fleming Fund (specifically focusing on Fleming Fellows, RGs, and Use of data) and identify any potential adaptations for the remaining time of phase 1, submitted March 2021.

- Summative report for the DHSC on whether the grants programme is likely to meet its overall objectives (covering all the six EQs), submitted December 2022.

- Participation in the Fleming Fund TAG meetings as required.

- The DHSC’s participation in quarterly meetings between the MA and the evaluation team.

Jon Cooper, the Itad Project Director, had overall accountability for delivering a high-quality evaluation, within agreed timeframes and budgets, and Julie-Anne Darsley, as Project Manager, had overall responsibility for project management with the support of Jack Dale, one of Itad’s Project Officers.

Paul Balogun, the evaluation Senior Advisor, played a QA role by reviewing deliverables before they were submitted to the DHSC and providing focused strategic support to the team.

The evaluation Team Leader was Tim Shorten who brings expertise in leading complex, multisectoral, multi-country longitudinal evaluations, and in managing multi-disciplinary teams to achieve high-quality utility focused results. The Team Leader was the primary liaison between the evaluation team and the DHSC on high level technical issues. The Team Leader, with support from Giada Tu Thanh as Deputy Team Leader, was responsible for ensuring the timely delivery of quality outputs from the evaluation team. Individual team members were responsible for specific aspects of the evaluation design. More detail on the specific roles and responsibilities of the evaluation team members is included in Table 46.

Together Project Director, Project Manager, Senior Advisor, Team Leader, and Deputy Team Leader form a Senior Leadership Team (SLT) that was responsible for ensuring adequate capacity to deliver the evaluation. Itad staff facilitate linkages, as required, to ensure that Itad’s institutional capacity and deep experience of managing complex, multi-stakeholder, multi-country evaluations are brought to support the evaluation.

The Team

The evaluation team composition has been designed to ensure relevant and appropriate sectoral and methodological expertise, and diverse perspectives, in order to implement the approach set out in Annex 3, and to address the EQs at the heart of the evaluation design. An overview of the team is provided below in Table 46.

Table 46 Evaluation team members

| Name | Role and Description |
| --- | --- |
| Senior Leadership Team |  |
| Jon Cooper | Project Director: Represents Itad and was accountable to the DHSC and Itad for the successful delivery of the evaluation. A key role maintaining an effective working relationship with the MA and DHSC and promoting effective learning and communication. |
| Paul Balogun | Senior Advisor: Responsible for key deliverables QA and engaging with the DHSC TAG, and the DHSC Fleming Fund Project Team on key high-level issues: - Worked with the Team Leader and Deputy Team Leader, inputting into the development of methodologies, providing strategic vision and support to the evaluation, and ensuring the needs of the client are met through the evaluation; - Worked with the Team Leader and contributes to the development of formative and summative reports; - Ensured the EAG were briefed and engaged such that they could support the evaluation team as envisaged. |
| Tim Shorten | Team Leader and Quantity and Sustainability Lead: Responsible for the evaluation’s technical delivery and for ensuring it fulfils EQuALS Quality Standards: - Led on the refinement of the methodology for the evaluation and liaises with and engages the DHSC and MA on high level technical issues as appropriate; - Led on the development of guidance, protocols, and tools for data collection/analysis and training other team members on the evaluation methodology; - Undertook pilot country visits to test and refine our approach and other country visits as required; - Led on the development of formative and summative reports. - Ensured EAGs were briefed and engaged such that they could support the evaluation team as envisaged. - Lead on the sustainability workstream; - Contributed to L&D as requested; - Contributed to regular team calls and evaluation management calls with the project manager; - Contributed to quarterly and annual reporting. |
| Giada Tu Thanh | Deputy Team Leader & Coherence and Contribution Analysis Lead: Led on the development of a protocol for Contribution Analysis and Coherence to ensure that all country visits were contributing as required to the overall approach: - Input to a number of deliverables as required to ensure that Itad’s expertise and best practice on methodologies and approaches were reflected in the evaluation tools and guidance; - Contributed to learning and dissemination activities; - Undertook a number of country visits and provided senior inputs to the ToC and Contribution Analysis work; - Worked with the Team Leader in the development of methodologies and in delivering the Client’s overall ToR for this evaluation; - Contributed to the drafting of the Summative Report as instructed by the Team Leader, - Monitored the progress towards and quality of deliverables by team members; - Engaged with the MA as appropriate; - Engaged with the DHSC as requested on technical matters and makes sure the evaluation meets their needs; - Contributed to L&D as requested and to quarterly and annual reporting. |
| Julie-Anne Darsley | Project Manager (PM): Responsible for the day to day running of the evaluation from Itad's side: - Liaised with the DHSC and MA on day-to-day issues and scaled up issues as appropriate; - Closely monitored the budget and the work plan together with the Project Officer, in liaison with the Project Director and the Team Leader; - Worked with the Team Leader and Deputy Team Leader in delivering the Client’s overall ToR for this evaluation; - Managed TEAMS and ensured all deliverables were filed appropriately; - Led regular team calls, evaluation management calls with the Team Leader and Deputy Team Leader, and meetings, and ensured work was delivered against our overall plan. - Led on quarterly and annual reporting to the DHSC. |
| Thematic Leads |  |
| Syed Abbas | Predicting Change Expert and One Health Expert: Responsible for the delivery of the One Health workstream and undertaking a number of country visits as required: - Fed into the revision of data collection tools; - Contributed to annual deliverables, team training workshops, and analysis workshops; and - Contributed to L&D as requested. - Attended regular team calls and provided regular updates on the One Health workstream. |
| Jennifer Armitage | VfM Lead: Responsible for the delivery of this workstream: - Led on the development of the VfM approach and fed into the revision of data collection tools, training team members in relevant aspects of VfM and inputs into relevant deliverables; - Contributed to annual deliverables, team training workshops, and analysis workshops; - Conducted global KIIs and contributed to L&D as requested. - Attended regular team calls and provided regular updates on the VfM workstream. |
| Ankur Gupta-Wright | Quality Lead: Responsible for the delivery of the Quality workstream and leading the development of the Quality approach and feeding into the revision of data collection tools, training team members in relevant aspects of Quality and inputting into relevant deliverables: - Contributed to annual deliverables, team training workshops and analysis workshops. - Conducted global KIIs and contributed to L&D as requested. - Attended regular team calls and provided regular updates on your workstream. |
| Archie Drake | USE Lead: Responsible for the delivery of this workstream. Led the development of the USE approach and fed into the revision of data collection tools, training team members in relevant aspects of USE and inputting into relevant deliverables: - Contributed to annual deliverables, team training workshops and analysis workshops; - Conducted global KIIs and contributed to L&D as requested; - Attended regular team calls and provided regular updates on the Quality workstream. |
| Cheryl Brown | Learning and Dissemination (L&D) Lead: Responsible for the delivery of L&D. Lead on learning and dissemination activities, engagement with the MA and DHSC for learning purposes, and on the production and dissemination of learning products: - Facilitated internal and external workshops as requested; - Contributed to the drafting of deliverables as per the guidance of the Team Leader/Deputy Team Leader. |
| Country Leads |  |
| Tim Shorten (Zambia) Giada Tu Thanh (Laos & Vietnam) Aminah Rajput (Pakistan & Bangladesh) Marco Maragno (Nepal, Sierra Leone, Uganda & Timor-Leste) Archie Drake (Ghana, Nigeria & Senegal) Abbas Syed (Indonesia) Ruth Sherratt (Bhutan. Kenya & Tanzania) | Country Leads: Responsible for the successful delivery of the country level data collection exercise, and the production of high-quality outputs. The Country Leads oversaw the work of the In-Country Consultants and the Country RAs to ensure all document reviews and tools were complete and the team was ready for the country visit. The Country Leads undertook country visits either remotely (if travel restrictions were in place) or in person and worked with the In-Country Consultants and the Country RAs to ensure tools, analysis and debriefs were complete post country visits and contributed to annual deliverables and team training workshops as required. |
| In-Country Consultants |  |
| Pascalina Chanda (Zambia) Murshid Hasan (Bangladesh) Isma Novitasari Yusadiredja (Indonesia) Ozioma Nwagwu (Nigeria) Ismael Barreto (Timor-Leste) Eric Ogola (Kenya) Pham Hong Hanh (Vietnam) Robert Sam-Kpakra (Sierra Leone) Sylla Thiam (Senegal) Yusaf Hamba (Uganda) Hussein Mohammed (Bangladesh) Prakash Ghimire (Bhutan) Latsany Phakdisoth (Laos) Alex Afram (Ghana) Megha Raj Banjara (Nepal) | Research Support Team: Involved in desk-based research in preparation for the country visits. The In-Country Consultants supported data collection following the guidance provided by the CL/core team, including taking a lead on KIIs (if the CL could not join in person) and site visits. They also took on other responsibilities as long as the CL maintained oversight. The research support team contributed to annual deliverables and team training workshops as required. |
| Country Research Analysts |  |
| Krista Kruja Juliette Gautron Zoe Bonnell Shiuli Das | Country Ras: Responsible for completing desk-based research in preparation for the country visits, working with country leads and in-country consultants to ensure all tools were complete. The country Ras contributed to annual deliverables and team training workshops as required. |
| Central Research Analyst |  |
| Zoe Bonnell | Central RA: Responsible for liaising with the MA on documentation for country visits and for uploading it onto TEAMs. The central RA supported desk-based research ahead of country visits, working with USE and VfM thematic leads to complete TrACSS and VfM deliverables; and contributed to annual deliverables and team training workshops as required. |
| Technical Advisor |  |
| Gerry Bloom | Health Systems Strengthening (HSS) and Health Policy Advisor: Input into the development of tools and protocols, provided technical advice in HSS and Health Policy, and provided input in various deliverables as needed. |
| Central Support roles |  |
| Jack Dale | Project Officer: Worked closely with the Project Manager and DHSC to ensure the smooth delivery of the evaluation. The Project Officer supported team members on contractual and logistic issues related to the project and numerous country visits, closely monitored the budget and the work plan, in collaboration with the Project Manager and the Project Director, and oversaw invoicing with team members and the DHSC. |

In addition, the evaluation team was guided by an EAG. This is a group of leading experts whose role is to i) ensure the team was aware of other key initiatives in AMR that might affect what we did; ii) check that the team was not overlooking key technical issues that might strengthen our approach if addressed or would provide an alternative explanation for what we found in the evaluation; iii) to input into our adaptive learning approach to provide a practitioners’ perspective on our findings and how to present them in a way useful to the broader AMR constituency. The EAG is made up of:

- Prof Tim Peto, Professor of medicine at the University of Oxford and a consultant in infectious diseases; co-leader for the Infection Theme of the Oxford Biomedical Research Centre, and a co-lead of the Oxford Health Protection Research Unit on Healthcare associated infections and AMR and a National Institute for Health Research Senior Investigator.

- Prof David Heyman, Professor of Infectious Disease Epidemiology, LSHTM; head of the Centre on GHS at Chatham House; and chairman of Public Health England.

The above organisational structure and accountabilities and responsibilities were designed to promote both the independence of the evaluation and ensure efficient implementation through a clear division in roles, accountabilities and responsibilities.

- Annex 15: Country categorisation

The original 23 Fleming Fund countries had different starting points in terms of what surveillance systems were already in place (Figure 27) and were assigned to one of four broad categories as follows. Table 47 provides a description of the A-D categories that the MA used to describe the status of AMR surveillance across Fleming Fund focus countries (source MA implementation plan v2.5).

Figure 27 Country Categorisation

Table 47 Country Categorisation A-D

| Category | Description | Countries |  |
| --- | --- | --- | --- |
| A | Countries which had no NAP These were countries without a NAP in process or where it was in draft and not yet close to being finalised. They also tended to lack a functional coordination committee, may not have had a situation analysis and may not be engaging with the AMR issue. These were not favoured for investment at this time. | Sierra Leone Myanmar |  |
| B | Countries which have a NAP but no surveillance system in operation These countries had received support from the Tripartite Alliance (or others) to develop a NAP or have developed a response to AMR on paper. There was recognition that a surveillance system needs to be developed and there was a plan for doing so, or the plans were well advanced. Little or no progress had been made with implementation largely due to resource constraints, rather than an absence of political will. These countries were targeted for the majority of investment through the Fleming Fund Grants and Fellowship Scheme. | Ghana Senegal Eswatini Malawi Zambia Laos Pakistan Tanzania | Zimbabwe Kenya Bhutan Bangladesh Indonesia Timor-Leste Papua New Guinea |
| C | Countries where modest surveillance was established, gaps needed to be filled and activities needed to be connected These countries had some form of surveillance system in place, but that system was solely or predominantly in HH, small scale, and likely to be fragmented. There were other significant constraints such as poor QA, lack of capacity to analyse data and/or weak laboratory capacity, and/or sustainability issues. Weak connection between sectors for One Health approaches. | Nigeria Uganda Nepal Sri Lanka |  |
| D | Countries which were relatively more advanced and would benefit from nuanced support and/or could be supported to do more in One Health These countries had a surveillance system (some including AH) which was relatively well established, or likely to be well established with donor support. Investment areas were likely to be in addition and aligned with the actions of other donors and/or the government, seeking to add value. | India Vietnam |  |

Three-fifths (16/24) of the countries selected were in category B. In these countries there was an AMR NAP in place and the MA believed, based on a review of desk material and KI views, there was political will to move on the AMR surveillance agenda. However, while aspects of a basic surveillance system were in place in these countries, an operational surveillance system was not, therefore, these 16 countries were the main focus in terms of resources and time. Six of the remaining eight countries had an operational surveillance system in place and for these countries the focus was on filling gaps in the already functioning system.

- Annex 16: Participation of stakeholders

Table 48 below details how and when stakeholders were engaged in the Summative Evaluation. Further details for how the evaluation findings will be disseminated can be found in Annex 17.

Table 48 Participation of stakeholders

| Stage of Summative Evaluation | Stakeholder | Participation | When |
| --- | --- | --- | --- |
| Design of summative evaluation | DHSC | Discussions held with key stakeholders at DHSC to ensure focus of the evaluation met their needs | Q4 2021 |
| Pilot Data Collection (Pakistan and Zambia) | MA, DHSC, RCs, CGs & KIs | Itad worked with the MA and RCs on the timing of the pilot country visits. The MA provided documentation on CGs to support document reviews and country visit preparation. The evaluation team liaised with RCs and CGs on the logistics of the pilot country visits, setting up KIIs and arranging site visits. The evaluation team contacted KIs to arrange interviews and site visits and conducted these during the pilot country visit. On completion of the pilot country data collection, a pre debrief meeting was held with RCs for comment and to check factual accuracy. Following this the debrief presentation was shared with and presented to the MA and DHSC for discussion. | Q4 2021 |
| Data Collection: - Document Review - Country KIIs - Site Visits - KIIs with DPs, DHSC and MA | MA, DHSC, RCs, CGs, HIs, KIs & DPs | Itad worked with the MA and RCs on the timing of the country visits. The MA and DHSC provided documentation on country, regional and global grants to support document reviews and country visit preparation. The evaluation team liaised with RCs and CGs on the logistics of the country visits, setting up KIIs and arranging site visits. Ahead of data collection, a copy of the data collection ToRs was shared with the MA, DHSC and CGs. The evaluation team contacted KIs to arrange interviews and site visits and conducted these during the country visit. The evaluation team also conducted interviews with key stakeholders at the DHSC, MA, RCs, HIs and DPs. | Q4 2021-Q3 2022 |
| Country Level Debriefs | MA, DHSC, RCs, CGs & KIs | A debrief meeting was held for each of the 16 countries in the sample. An initial meeting took place with RCs for comment and to check factual accuracy. Following this the debrief presentation was shared with and presented to the MA and DHSC for discussion. Following the debrief meeting, the country teams shared the presentation with CGs to check for sensitivities, this was then distributed to the KIs who took part in the interviews. | Q2 2022-Q4 2022 |
| Report drafting | EAG, MA & DHSC | A draft of the report was shared with the EAG for review and comments. A draft of the report was also shared with the MA for comment and to check factual accuracy. Finally, the high-level findings were shared with the DHSC before submission of the report. | Q4 2022 |
| Submission & Dissemination | MA, DHSC, TAG, KIs | The Summative Evaluation was submitted to DHSC in December. Following feedback and revisions the final report will be made publicly available, it will also be shared with those who were interviewed as part of the evaluation. A series of findings workshops will take place with the DHSC, TAG and MA. The report and products will also be disseminated as per Annex 17. | Q4 2022 – Q1 2023 |

- Annex 17: Use and Influence Plan

Purpose of use and influence plan

The evaluation team are committed to making the evaluation as useful as possible and recognise that the Summative evaluation will have utility only if it is understood and used to inform decisions. The following section outlines how we improve utility through the dissemination of evaluation results, which will be done collaboratively with DHSC.

Throughout the evaluation, Itad aimed to provide learning at key stages, to support adaptive management and inform decision-making for this and other AMR programmes. Three key objectives for learning and dissemination were agreed with the DHSC within the evaluation, these were as follows:

- Objective 1: To support adaptive management of the Fleming Fund, particularly of the grant making and implementation processes.

- Objective 2: To support evidence-based decision-making by the DHSC and HMT on whether to fund a new phase and how to design it.

- Objective 3: To make lessons learned through the evaluation of the Fleming Fund available externally as global public goods.

Objectives 1 and 2 were addressed throughout the evaluation and in previous deliverables:

- Report 1: January 2019 Formative report including judgements for the DHSC, MA and HMT to support a decision on future Fleming Fund funding;

- Report 2: Formative deliverable for the DHSC, and MA to support adaptive learning in key windows of opportunity, submitted January 2020.

- Report 3: Formative deliverable requested by the DHSC to inform the design of the second phase of the Fleming Fund (specifically focusing on Fleming Fellows, RGs and Use of data) and identify any potential adaptations for the remainder of phase 1, submitted March 2021.

The summative evaluation focuses primarily on meeting learning objective 3 which focuses on turning the learning from the Fleming Fund evaluation into global public goods that are accessible and useful to the AMR and donor communities. However, because a second phase of the Fleming Fund has been agreed, to improve the usefulness of the report, we will also look to broaden the focus of this plan to ensure findings and recommendations can be incorporated into phase 2 of the Fleming Fund. (The design and planning of phase 2 has already started but we hope our recommendations can be incorporated into later adaptions of the programme). With this in mind, the use and influence plan is built with our guiding principles for learning and dissemination in mind:

- Making evaluation findings as useful as possible to key stakeholders – using appropriate language, medium, format, level of detail, etc.

- Sharing learning in time to inform the MA and DHSC’s planning and decisions

- Using resources wisely - activities capitalise on Fleming Fund events, and use existing digital channels, where appropriate.

- Continuously improving – monitoring dissemination, asking for feedback from the MA and DHSC, and regularly reviewing the work plan.

Target audience and key stakeholders

We believe that the key audiences for the summative evaluation are:

- DHSC

- DHSC Investment Committee

- MA

- Fleming Fund RG and CG recipients and Fleming Fellows

- TAG

- HMG & HMT

- Fleming Fund partners (The Fleming Fund Tripartite, GRAM, South Centre etc. including their regional and country offices).

- Aid agencies in other countries currently funding initiatives similar to the Fleming Fund.

- International initiatives, including the UN Interagency Coordination Group on AMR, and Global Health Security Agenda.

- Other donors and organisations interested in funding AMR.

- Wider AMR and One Health communities, e.g. the ReAct group, the GARP, One Health Commission, etc. and those operating at national and regional levels.

- Other organisations and networks recommended by the TAG.

Planned activity

To support dissemination and increase utility, we have planned a range of activities from ensuring that evaluation outputs that can be shared externally are hosted online and promoted to key audiences; to developing tailored learning products and dissemination activities that meet the information needs of those audiences in terms of timeliness, format, language, etc. The final evaluation report is written in a short and accessible style with data annexed, so that evidence is available to back up findings. We also plan to make the report and supporting products accessible to people with disabilities.

Review of summative report findings

Although Itad have already shared evaluation findings with the DHSC and MA, the production of the summative deliverable is a critical point at which to take stock of the evaluation findings before they are shared with a wider set of audiences. A workshop has been held with the DHSC, MA and the TAG to present and discuss the findings and recommendations of the summative evaluation.

Learning events and workshops

Events that bring Fleming Fund partners together present opportunities for Itad to make the evaluation more useful (and more likely to be used). The evaluation team is well situated to take on the role of ’honest broker’ within the programme; the team is committed to helping the Fleming Fund be as effective as possible while not being directly affected by the programme’s results. Based on this, and the likely global interest in learning that comes from the programme, we will work with the organisers of annual Fleming Fund DP events to include interactive learning sessions (facilitated by Itad). We suggest that the DHSC, MA and Itad, collectively decide the themes for these sessions. We are also due, at the request of the DHSC, to facilitate thinking on how to strengthen adaptive management during phase 2; this is expected to take place during Q1 or early Q2 of 2023.

As well as supporting the adaptive management of the Fleming Fund, and informing the DHSC’s decision making, learning captured through the workshops will be shared externally through reports, blog posts and articles following a process of approval by workshop participants.

Itad will work with the DHSC to design and facilitate a set of strategic shift workshops for Fleming Fund partners which revisit the discussions held in 2022, provide an opportunity for partners to share their plans, and identify potential areas of collaboration, and into which relevant findings from the evaluation can feed in.

Producing materials for DHSC to communicate to their network

Itad’s evaluation deliverables will be an important reference for the DHSC to check the quality of the evidence and dig into the detail of the findings. For busy policymakers who are less familiar with the Fleming Fund, a well-timed email of bullet points from a trusted source, is more likely to have an impact than a chunky report, so the evaluation team will discuss and agree with the DHSC what additional materials could be generated to support it to communicate with its key audiences such as HMT and other donors. These could include:

- short briefing notes for the DHSC to share or to draw on when drafting memos;

- slides of key messages that the DHSC can incorporate into presentations;

- charts, tables and quotes that illustrate key messages; and

- infographics.

Evaluation deliverables will also be used to support decisions on further investment into the Fleming Fund. With this in mind, Itad will create products to support the Fleming Fund project team to develop a business case.

Making the evaluation findings and recommendations available and accessible in a range of formats

Full and detailed reports, usually with several annexes, are a necessary product of evaluations, but they are unlikely to be relevant for many people with an interest in what the Fleming Fund has achieved and the learning that has come from it. So, while all public versions of the evaluation reports will be produced in attractive and easy-to-read formats, using infographics where appropriate, we will also continue to discuss and agree with the DHSC, other products that share the findings of the summative evaluation report.

In our experience, a report of 50 pages, can be neatly reduced to a summary of just a few pages. This may be enough for some readers, while for others it can serve as a springboard to exploring sections of the longer report. Some audiences may be interested in a single EQ e.g. ‘Did the Fleming Fund’s investments at the country level offer VfM?’ and we will produce briefing notes on individual evaluation themes. Academic audiences will be used to a more formal and in-depth approach, and for them we intend to submit papers based on evaluation data, to open access peer-reviewed journals.

In addition, any material that is produced for publishing on the Fleming Fund website, will be compliant with the Web Content Accessibility Guidelines 2 (WCAG2) and where resources allow for it, key outputs, such as the Executive Summary of the summative report, will be translated into French.

Using a mix of channels to reach different audiences

For key stakeholders of the Fleming Fund, we want to communicate the evaluation reports interactively. By using face-to-face roundtables and webinars with the DHSC and their invited guests e.g. the TAG and HMG, the evaluation team will be available to present headlines, answer questions and offer frank reflections in a way that is not possible through other communication tools. In addition, Itad will support the DHSC to design and deliver a hybrid Delivery Partners Event in September 2023, with a face-to-face meeting in Ghana complemented by online participation.

We expect the Fleming Fund website to be the first port of call for people wanting to find out what the grants and Fleming Fellows have achieved and learned. Itad will produce (subject to the identification of relevant and interesting topics) a series of news articles for the Fleming Fund website and send the Fleming Fund website editors digital copies of all evaluation outputs for hosting in the Knowledge and Resources section as soon as they are signed off for external publication by the DHSC. In addition, we will work with the DHSC to provide content from the summative report that responds to requests issued to all Fleming Fund partners for contributions to Knowledge and Resource blog posts. We will also explore other repositories for these publications such as the National Institute for Health and Care Research website.

To widen the reach of the evaluation findings to Itad’s connections in the development and evaluation communities, we will produce a dedicated page on the Itad website about the Fleming Fund evaluation (linking to the Fleming Fund site), use the Itad blog and Itad’s Twitter account to share news of the evaluation, mentioning @FlemingFund to prompt retweeting by the DHSC (if permitted by DHSC).

Being responsive to AMR discussions

Timeliness and relevance are key factors in making information useful to people. By monitoring hashtags such as #AMR and #OneHealth on Twitter, Itad will work with DHSC to share key messages from the evaluation when our intended audiences are likely to be receptive and direct them to our online publications.

Similarly, we will track discussions on other social media, on AMR and One Health, including any created to support Fleming Fellows, so that we can contribute evaluation findings in a timely manner. As a good starting point, the One Health Commission manages a global One Health community listserv and maintains a list of relevant social media accounts.

Finally, we will identify conferences and workshops taking place later in the programme to which we can submit papers that speak to the planned themes.

Feedback

Sharing findings and recommendations with participants is an important step to ensure those involved understand how the results are being used. There is also a possibility that the outcome of the evaluation may influence future decisions which will directly affect the people who have participated in the evaluation. Itad therefore intends to share the report with all the evaluation participants.

The Plan

This table shows when activities are expected to take place but will be reviewed regularly with the DHSC to align with their communications plans. To support this coordination, Itad will produce a live communications calendar that the evaluation team and DHSC can use to identify opportunities for timely and effective evidence utilisation activities.

| Activity | Target Audience | Intended Outcome / Result | Timing |
| --- | --- | --- | --- |
| Findings and recommendations workshops | DHSC, Special Envoy, MA Senior Management Team (SMT )& TAG | Key stakeholders fully informed and clear on recommendations – discussion for how these can be incorporated into phase 2 | Q1 2023 |
| Report and executive summary slides available on Fleming Fund website | DHSC, MA SMT and RTs, CG, RCs TAG, Fleming Fellows, Fleming Fund partners | Key stakeholders fully informed and clear on recommendations | Q2 2023 |
| Link to report and executive summary slides sent to participants | Participants of evaluation (MA RTs CGs, RCs, Fleming Fellows, KIIs) | Key stakeholders fully informed on findings and recommendations of evaluation – potential for recommendations to be incorporated into AMRCC meetings/country level discussions | Q2 2023 |
| Report and executive summary slides available on Itad website (pending DHSC approval) | Aid agencies, international initiatives, other donors and organisations interested in funding AMR, wider AMR and One Health communities. | Wider audience informed and clear on recommendations | Q2 2023 |
| Version of report available for external sites | Aid agencies, international initiatives, other donors and organisations interested in funding AMR, wider AMR and One Health communities, other organisations and networks recommended by the TAG. | Wider audience informed and clear on recommendations | Q2 2023 |
| Blog post of Itad site to promote report | Aid agencies, international initiatives, other donors and organisations interested in funding AMR, wider AMR and One Health communities. | Wider audience informed and clear on recommendations Findings and recommendations processed and reflected upon | Q2 2023 |
| 2-3 thematic focused blog posts for Fleming Fund website | DHSC, MA SMT and RT, CG, RCs, TAG, Fleming Fellows, Fleming Fund partners | Findings and recommendations processed and reflected upon | Q2 2023 |
| Learning event – DPs Event | DHSC, MA SMT, CG, RCs, TAG, Fleming Fellows, Fleming Fund partners | Findings and recommendations processed and reflected upon | Q3 2023 |
| Support to strategic shift workshops | DHSC, TAG, Fleming Fund partners & MA SMT | Findings and recommendations processed and reflected upon | Q1 and Q2 2023 |
| Adaptive management workshops | DHSC & MA SMT | Most important lessons and recommendations for course correction are agreed and actioned |  |
| Internal communication material for DHSC | DHSC, Special Envoy, DHSC investment committee, FCDO, HMT & HMG | Key stakeholders fully informed and clear on recommendations which can be used to support decisions on future funding/design | Q2 2023 |
| Academic paper (if felt to be relevant) | Academic communities focused on AMR, GHS, policymaking, One Health etc. | Evidence processed and reflected upon Lessons shared with audience to guide other AMR programmes | Q3-4 2023 |
| Speaking slot at AMR conference or workshop – partnering with the DHSC & MA | Aid agencies, international initiatives, other donors and organisations interested in funding AMR, wider AMR and One Health communities, other organisations and networks recommended by the TAG | Evidence processed and reflected upon. Lessons shared with audience to guide other AMR programmes | TBC – in 2023 |

Dependencies:

Delivery of the outlined plan is based on a number of dependencies:

- Time available after the summative report is signed off for making available online via the Fleming Fund website;

- Approval from the DHSC on dissemination material.

How we will monitor and report on learning and dissemination:

During phase 2 of the Fleming Fund we intend to monitor and report on learning through:

- Quarterly reviews of the six-month joint work plan for the MA and Itad, using these to discuss joint opportunities for learning and dissemination.

- Six-monthly reviews with the DHSC, specifically of the Learning and Dissemination work plan for the year ahead, this will help us to time and prioritise activities.

- Itad will be submitting quarterly and annual reports to the DHSC and we propose including a section on Learning and Dissemination: progress against the activities for the period covered, activities planned for the forthcoming one, highlights/challenges/lessons learned and a report on uptake indicators.

Our monitoring and reporting serve the dual needs of:

- Keeping the plan on track and relevant

- Sharing successes, challenges and learning which will help us make improvements to our use and influence plan in phase 2.

Figure 28 Hierarchy of learning uptake indicators

Proposed indicators for learning and dissemination activities

The activities in this plan are ultimately aimed at encouraging the uptake of learning from the evaluation and our approach to this is built on an understanding of information behaviour – how people encounter and engage with information. Our reading of the stages of learning uptake is shown in Figure 28. It recognises the many barriers that can lead to learning being used by a small proportion of those to whom it was made available. While our plan focuses on trying to respond to as many of these barriers as possible e.g. directing people to information at a time when they need it, there will be some attrition and a limit to what we can monitor. In the context of this evaluation, successful uptake begins with Itad making learning available in appropriate formats and through appropriate channels e.g. producing an evaluation report and uploading it to the Fleming Fund and Itad’s website, and ends when the reader or listener has processed the information and decided that it is of value to them (or to other people) for evidence-informed practice or decision-making. Our indicators for monitoring the learning and dissemination activities are linked to these stages and include a set of indicators on client satisfaction with Itad’s activities.

Table 49 Proposed indicators for L&D Activities

| Category of Uptake | Indicators | Data sources |
| --- | --- | --- |
| Learning from the evaluation is made available | - Number of open access publications and other learning products published online. - Reach of promotional activities about publications put online. - Distribution of publications (sent directly, put in repositories, or on webpages) - Number of events at which learning from the programme is shared. | Itad quarterly reports, social media statistics (followers), website statistics (views and visits). |
| Learning from the evaluation is accessed | - Number of views / engagements made of publications. - Number of people attending events/sessions where programme learning is shared. | Website statistics, Itad quarterly reports. |
| Learning from the evaluation is read, heard or discussed | - Responses on Twitter and other social media - Number and nature of questions or comments made in response to presentations/during roundtables, etc. | Monitoring blogs, social media statistics, Itad quarterly reports. |
| Learning from the evaluation is valued | - Number of times products are referenced in other publications, event proceedings, online discussions, etc. - Number of times products are shared by readers, with others (e.g. posted to the online community by someone outside of the programme). - DHSC satisfaction with Itad-facilitated events. - DHSC satisfaction with usefulness of materials produced and presentations, and Itad’s ability to respond to reasonable requests for support. - MA’s feedback that evaluation reports and country trip debriefs are useful and used to inform their management of grants. | Social media discussions, feedback from stakeholders, links and references made to Itad outputs, feedback from DHSC and MA, quarterly meetings with MA, follow-up country visits. |

- Annex 18: Fleming Fund programme theory of change

Following the submission of the first formative evaluation report in January 2019, Itad supported the DHSC to set out a portfolio-level theory of change for the Fleming Fund in mid-2019. This was revised in December 2021 along with a ToC narrative to describe the intervention logic. The narrative was developed in partnership with DHSC but has not been published to date so is not included here.

Figure 29 Fleming Fund ToC diagram

# Annex 19: Bibliography

Abbas, S. S., Shorten, T., & Rushton, J. (2022). Meanings and mechanisms of One Health partnerships: insights from a critical review of literature on cross-government collaborations. Health Policy and Planning, 37(3), 385-399.

American Veterinary Medical Association. (2022). One Health. Retrieved from AVMA: https://www.avma.org/resources-tools/one-health

Bailey, H. (2012). Stories of Change. Brighton: IDS.

BOND. (2012). BOND’s Value for Money: what it means for UK NGOs. BOND.

Brown, C., & Shorten, T. (2021, 07 21). Common elements of good practice for sustainability. Retrieved from The Fleming Fund: https://www.flemingfund.org/publications/common-elements-of-good-practice-for-sustainability/

Cairney, P., & Zahariadis, N. (2016). MSA: a flexible metaphor presents an opportunity to operationalize agenda setting processes. In N. Zahariadis, Handbook of Public Policy Agenda Setting. Cheltenham, UK and Northampton, MA:: Edward Elgar.

Chiolero, A., & Buckeridge, D. (2020). Glossary for Public Health Surveillance in the Age of Data Science. Journal of Epidemiology and Community Health, 74, 612-616.

Cooper, J. (2019, May 3). No time to wait: evaluating the fight against ‘Drugmageddon’. Retrieved from Itad: https://www.itad.com/article/no-time-to-wait-evaluating-the-fight-against-drugmageddon/

Davies, R. M. (2012). DFID Working Paper 38. Broadening the range of designs and methods for impact evaluations. . London: DFID.

Department of Health and Social Care. (2020). Fleming Fund annual review: January to December 2019. Department of Health and Social Care.

DFID. (2011). DFID’s Approach to Value for Money (VfM). London: DFID.

DFID. (2011). Withdrawn - DFID Ethics Principles For Research and Evaluation.

DFID. (2020). DFID's Approach to Value for Monney - Guidance for External Partners. London: DFID.

Forss, K., Marra, M., & Schwartz, R. (. (2011). Contribution Analysis: Addressing Cause and Effect. Transaction Publishers.

Frid-Nielsen, S. S., Rubin, O., & Baekkeskov, E. (2019). The state of social science research on antimicrobial resistance. Social Science & Medicine (1982), 242(112596).

Groves Williams, L. (2015). Review of Ethics Principles and Guidance in Evaluation and Research.

Hassel, A., & Wegrich, K. (2022). How to Set the Agenda. In A. Hassel, & K. Wegrich, How to Do Public Policy (p. 0). Oxford University Press.

HEART. (2019). Fleming Fund Implementation January-December 2018 Annual Review. HEART.

ICAI. (2015). DFID's approach to delivering impact.

ICAI. (2018). DFID's approach to value for money in programme and portfolio mannagement: a performance review. London: ICAI.

Interagency Coordination Group on Antimicrobial Resistance. (2018). Antimicrobial resistance: national action plans . Interagency Coordination Group on Antimicrobial Resistance.

Interagency Coordination Group on Antimicrobial Resistance. (2018). Call to Action on Antimicrobial Resistance 2018. Interagency Coordination Group on Antimicrobial Resistance.

Jones, D. M., Peterson, H. L., Pierce, J. J., Herweg, N., Bernal, A., Lamberta Raney, H., & Zahariadis, N. (2015). A River Runs Through It: A Multiple Streams Meta-Review. Policy Studies Journal, 44(1), 13-36.

Kingdon, J. (2010). Agendas, alternatives, and public policies, update edition, with an epilogue on health care, 2nd edition. Boston: Pearson.

Loft, P., & Brien, P. (2021). Reducing the UK's aid spend in 2021. House of Commons Library.

Mott MacDonald. (2018). Implementation Plan. London: Mott MacDonald.

Mott MacDonald. (2021). Fleming Fund Management Agent. Phase II Technical Proposal. March. London: Mott MacDonald.

Murray, J. L. (2022). Global burden of bacterial antimicrobial resistance in 2019: a systematic analysis. The Lancet, 399(10325), 629-655.

National Audit Office. (2022). Successful commissioning toolkit: Assessing value for money. Retrieved from National Audit Office: https://www.nao.org.uk/successful-commissioning/general-principles/value-for-money/assessing-value-for-money/

OECD. (2010). Quality Standards for Development Evaluation. OECD DAC Evaluation Network.

OECD. (2021). Applying Evaluation Criteria Thoughtfully. OECD.

OECD DAC Evaluation Network. (2012). UK Evaluation Society Good Practice Guidelines, and International Development . OECD DAC Evaluation Network (EvalNet).

OECD iLibrary. (2022). 4. Understanding the six criteria: Definitions, elements for analysis and key challenges . Retrieved from OECD iLibrary: https://www.oecd-ilibrary.org/sites/543e84ed-en/1/3/4/index.html?itemId=/content/publication/543e84ed-en&_csp_=535d2f2a848b7727d35502d7f36e4885&itemIGO=oecd&itemContentType=book#chapter-d1e2438

One Health Commission. (2022). Resources / Services. Retrieved from One Health Commission: https://www.onehealthcommission.org/en/resources__services/

One Health Trust. (2022). Global Antibiotic Resistance Partnership (GARP). Retrieved from One Health Trust: https://onehealthtrust.org/projects/global-antibiotic-resistance-partnership/

Patton, M. Q. (2002). Qualitative Research and Evaluation Options (3rd ed.). Thousand Oaks, California: Sage Publications.

Patton, M. Q. (2002). Qualitative Research and Evaluation Options (3rd ed.). Thousand Oaks, California: Sage Publications.

Review on Antimicrobial Resistance. (2022). Home. Retrieved from Review on Antimicrobial Resistance: https://amr-review.org/

Seale, A., Gordon, N., & Islam, J. e. (2017). AMR Surveillance in low and middle-income settings - A roadmap for participation in the Global Antimicrobial Surveillance System (GLASS). Wellcome Open Research, 2(92).

Sieleunou, I., Turcotte-Tremblay, A.-M., Fotso, J.-C., Tamga, D., Yumo, H., Kouokam, E., & Ridde, V. (2017). Setting performance-based financing in the health sector agenda: a case study in Cameroon. Globalization and Health, 13(52).

Spencer, L., Ritchie, J., Lewis, J., & Dillon, L. (2003). Quality in Qualitative Evaluation: A framework for assessing research evidence. London: Government Chief Social Researcher’s Office.

Spencer, L., Ritchie, J., Lewis, J., & Dillon, L. (2003). Quality in Qualitative Evaluation: A framework for assessing research evidence. Government Chief Social Researcher’s Office. London: Cabinet Office.

The Review on Antimicrobial Resistance. (2016). Tackling drug-resistant infections globally: final report and recommendations. The Review on Antimicrobial Resistance.

The Review on Antimicrobial Resistance. (2016). Tackling Drug-Resistant Infections Globally: final report and recommendations. London: The Review on Antimicrobial Resistance.

Thinking and Working Politically Community of Practice . (2022). Thinking and Working Politically Community of Practice . Retrieved from Thinking and Working Politically Community of Practice : https://twpcommunity.org/

UK Evaluation Society. (2018). Guidelines for Good Practice in Evaluation. Hertfordshire: UK Evaluation Society.

UK Health Security Agency. (2015). Human Animal Infections and Risk Surveillance group (HAIRS). Retrieved from Gov.uk: https://www.gov.uk/government/collections/human-animal-infections-and-risk-surveillance-group-hairs#:~:text=Contents&text=The%20Human%20Animal%20Infections%20and%20Risk%20Surveillance%20(%20HAIRS%20)%20group%20is,threat%20to%20UK%20public%20health

United Nations. (2010, April 21). Hanoi Declaration Sets Global Framework for Avian Influenza, Pandemic Readiness, Proposes National Steps to Detect Animal-Human Transmission, Control Outbreaks. Retrieved from United Nations Meetings Coveage and Press Releases: https://press.un.org/en/2010/sag433.doc.htm

Vähämäki, J., & Verger, C. (2019). Learning from Results-Based Management evaluations and reviews. OECD Development Co-Operation Working Paper 53. Paris: OECD.

Wilson-Grau, R. (2018). Outcome Harvesting: Principles, Steps, and Evaluation Applications. IAP.

World Bank. (2021, June 3). The World Bank. Retrieved from Safeguarding Animal, Human and Ecosystem Health: One Health at the World Bank : https://www.worldbank.org/en/topic/agriculture/brief/safeguarding-animal-human-and-ecosystem-health-one-health-at-the-world-bank

World Health Organisation. (2020, August 10). Global Leaders Group Terms of Reference . Retrieved from World Health Organisation: https://www.who.int/news-room/articles-detail/global-leaders-group-terms-of-reference

World Health Organisation. (2021, November 17). Antimicrobial Resistance. Retrieved from World Health Organisation: https://www.who.int/news-room/fact-sheets/detail/antimicrobial-resistance

World Health Organisation. (2021). Tripartite AMR Country Self-Assessment Survey (TrACSS) 2020-2021. Geneva: World Health Organisation.

World Health Organisation. (2021). WHO integrated global surveillance on ESBL-producing E. coli using a “One Health” approach. Geneva: WHO.

World Health Organisation. (2022). GLASS Resource Centre. Retrieved from World Health Organisation: https://www.who.int/initiatives/glass/resource-centre#glassreports

World Health Organisation. (2022). Global Antimicrobial Resistance and Use Surveillance System (GLASS) . Retrieved from World Health Organisation: https://www.who.int/initiatives/glass

World Health Organisation. (2022). PPS-AMU: Point prevalence survey on antibiotic use in hospitals. Retrieved from World Health Organisation: https://www.who.int/initiatives/glass/glass-modules-8

World Health Organisation. (2022). Strengthening WHO preparedness for and response to health emergencies: Strengthening collaboration on One Health. World Health Organisation.

World Health Organisation. (2022). Tripartite Zoonoses Guide: Operational tools and approaches for zoonotic diseases. Retrieved from World Health Organisation: https://www.who.int/initiatives/tripartite-zoonosis-guide

World Health Organisation. Regional Office for the Western Pacific. (2008). Zoonotic diseases : a guide to establishing collaboration between animal and human health sectors at the country level. . WHO Regional Office for the Western Pacific.

World Health Organization; Food and Agriculture Organization of the United Nations; United Nations Environment Programme; World Organisation for Animal Health. (2022). Antimicrobial Resistance Multi-Partner Trust Fund annual report 2021. Geneva: United Nations MTPF Office.

Annex 20: List of consultees

Please note that some names are listed multiple times, under different categories, for the same country. When listed more than once within one country’s list of consultees, * is placed after the name the second time it is listed, ** is placed the third time the name is listed, etc.

Global KIIs

| Global KIIs |  |  |
| --- | --- | --- |
| Eileen A. Chappell | MA | Fleming Fellowship Scheme Coordinator |
| Steve A. Wilson | MA | Programme Director – Finance and programme management |
| Toby J. Leslie | MA | Technical Lead |
| Sriram Raghu | MA | Procurement |
| Adrienne Chattoe-Brown | MA | VfM Lead |
| Luna Parry | MA | Regional Coordinator |
| Jemima Clarke | DHSC | Fleming Fellowship Scheme Coordinator |

Host Institutions KIIs

| Bhutan, Nepal, Timor-Leste, Pakistan |  |  |
| --- | --- | --- |
| Benjamin Howden | Doherty Institute/University of Melbourne | Programme Director, Fleming Fund Fellowship Scheme |
| Glenn Browning | Doherty Institute/University of Melbourne | Veterinary Microbiologist |
| Chantel Lin | Doherty Institute/University of Melbourne | Programme Manager for the Fellowship programme at the Doherty Institute |
| Ghana, Kenya |  |  |
| Clare Chandler | LSHTM | Academic Lead, Secretariat Member |
| Richard Stabler | LSHTM | Co-principal investigator for the Fleming Fund Programme |
| Ghana, Nigeria |  |  |
| Pernille Nilsson | Technical University of Denmark (DTU Food) | Project Manager for Seek Africa |
| Rene Hendriksen | Technical University of Denmark (DTU Food) | Professor, Head of the Unit |
| Uganda |  |  |
| Hilary Snaith | University of Edinburgh | Fellowship Coordinator |
| Tanzania |  |  |
| Pascale Ondoa | ASLM | PI for Fleming Fund programme and Regional Grant |
| Edwin Shumba | ASLM | MAAP Project Lead |
| Pakistan, Zambia |  |  |
| Katherine Heitz | American Society for Microbiology (ASM) | Programme Officer, Global Public Health Programmes |
| Nigeria |  |  |
| Hemanti Patel | UK Health Security Agency | Human Health Mentor |
| Indonesia, Vietnam |  |  |
| Annelise Pires Ferreira | Erasmus | Programme manager, Fleming Fund Fellowship Scheme |
| Juliette A. Severin | Erasmus | Programme Director, Fleming Fund Fellowship Scheme |
| Senegal, Laos |  |  |
| Chrystèle Corbery | Fondation Mérieux | Head of West Africa |
| Florence Pradel | Fondation Mérieux | Responsable d'un réseau de laboratoires de recherche dans les pays en développement |
| François-Xavier Babin | Fondation Mérieux | Director for international operations |
| Benoit Chevalier | Fondation Mérieux | Fellowship Coordinator |

Regional Grants KIIs

| ASLM |  |  |
| --- | --- | --- |
| Marianne Holmes | ASLM | Project Technical Lead of MAAP |
| Edwin Shumba* | ASLM | MAAP Project Lead |
| Anafi | ASLM | Training |
| Beatrice | ASLM | EQA |
| CAPTURA |  |  |
| Marianne Holmes* | International Vaccine Institute (IVI) | Project technical lead of CAPTURA |
| RADAAR |  |  |
| Marianne Holmes** | IVI | RADAAR Project Lead |
| Anthony Burnett | IVI | RADAAR Project |
| EQAsia, SEQAfrica |  |  |
| Rene Hendrikson | Technical University of Denmark (DTU Food) | Professor, Head of the Unit |
| Pernille Nilssonn | Technical University of Denmark (DTU Food) | Project Manager for Seek Africa |
| Paulina Tamez Hilgado | Technical University of Denmark (DTU Food) | Project Manager for EQA Grant (Asia) |

Bangladesh

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Professor Nitish Debnath and team | Fleming Fund Country Grant to Bangladesh (FFCGB) | Country Team Lead |
| AMRCC Members |  |  |
| Dr Abu Sufian | Department of Livestock Services (DLS) | Assistant Director (Animal Health and Administration) |
| Dr Aninda Rahman | CDC | DPM |
| Fleming Fund Fellows |  |  |
| S.M. Sabrina Yesmin | Directorate General of Drug Administration (DGDA) | Assistant Director |
| Gazi Shah Alam | DLS | Director |
| Nawroj Afreen | Institute of Epidemiology, Disease Control And Research (IEDCR) | Programmer NIO |
| Dr Markatul Alam | FIQC, Savar | FIQC Officer |
| Other decision makers |  |  |
| Dr Md Shahinur Alom | DLS, Prani sastho | Deputy Director |
| Professor Nazmul Islam | CDC | Director |
| Policy Fellows |  |  |
| Major General Mahbubur Rahman | DGDA | DG |
| AMR Focal Point |  |  |
| Dr Muzaffar Ghani Osmani | DLS | ULO |
| Prof Tahmina Shirin | IEDCR | Director |
| Development Partners/ Academia |  |  |
| Dr Ismail Ramzy | WHO | MO |
| DR Abul Kalam Azad | United States Agency for International Development (USAID) | Global Health Security Specialist |
| Mr Eric Braum | FAO | Team Leader |
| NRL & Site Visit |  |  |
| Dr Zakir Hossain Habib | IEDCR | PSO & Head, Department of Microbiology |
| Dr Md. Abdus Samad | Bangladesh Livestock Research Institute | PSO & Head, AHRD |
| Dr Golam Azam Chowdhury | Central Disease Investigation Laboratory (CDIL) | Principal Scientific Officer, CDIL |
| Prof. S M Samsuzzaman | Dhaka Medical College and Hospital | Head of Department of Microbiology |

Bhutan

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Sonam Wangda | RGOB | Project Director |
| Ugyen Kelzang | RGOB | Project Officer |
| Tshering Dorji | RGOB | M&E Officer |
| Kezang Mangmo | RGOB | Project Officer |
| Purmila Gurung | RGOB | Project Assistant |
| AMRCC Members |  |  |
| Rinzin Pem | National Centre for Animal Health (NCAH), Ministry of Agriculture and Forests (MOAF) | Chief Veterinary Officer, Animal Health Division, Department of Livestock |
| Ratna Gurung | NCAH | Programme Director |
| Pema Tshewang | National Veterinary Hospital | Deputy Chief Veterinary Officer |
| Dr Pem Chuki | JDWNRH National Referral Hospital and HH NRL | Medical Superintendent, Antimicrobial Stewardship Coordinator |
| Sonam Wangchuk | RCDC (Royal Center for Disease Control, HH Reference Laboratory) | Specialist/Head, Department of Public Health |
| Other decision makers |  |  |
| Kinley Panjor | Bhutan Agriculture and Food Regulatory Authority | Deputy Chief Regulatory and Quarantine Officer and Head- Animal Biosecurity Section, Plant and Animal Biosecurity Division |
| Policy Fellows HH |  |  |
| Sonam Wangda* | RGOB | Project Director |
| Professional Fellows HH |  |  |
| Kinley Wangchuk | JDWNRH National Referral Hospital and HH NRL | AMR Laboratory Fellow, Officer in Charge of the Microbiology Unit, Department of Pathology and Laboratory Medicine |
| Professional Fellows Animal Health |  |  |
| Pema Tshewang* | National Veterinary Hospital | AMC/U Surveillance Fellow, Deputy Chief Veterinary Officer |
| Puspa Sharma | National Veterinary Hospital | AMR Laboratory Fellow, Unit Head, Bacteriology and Molecular Biology and Biosafety and Biosecurity Sections |
| Ugyen Namgyel | NCAH, MOAF | AMR Surveillance Fellow, Senior Veterinary Officer, AH Unit, Regional Livestock Development Centre (WOAH Focal Point) |
| AMR Focal Point |  |  |
| Nirmal Kumar Thapa | National Centre for AH, MOAF | Animal Specialist, AH Division, Department. of Livestock, AMR AH Focal Point |
| Jigme Tenzin | Drug Regulatory Authority | AMR Focal Point |
| Dr Tshokey | JDWNRH National Referral Hospital and HH NRL | Microbiologist, AMR HH Focal Point |
| Kinley Gyem | RCDC, HH Reference Laboratory | Senior laboratory officer (AMR Focal Point) |
| WOAH Focal Point |  |  |
| Ugyen Namgyel* | National Centre for AH, MOAF | Senior Veterinary Officer, AH Unit, Regional Livestock Development Centre (WOAH Focal Point) |
| Development Partners/ Academia |  |  |
| Chadho Tenzin | FAO | Assistant Representative |
| Sonam Wangdi | WHO | National Professional Officer |
| NRL & Site Visit |  |  |
| Kinley Wangchuk* | JDWNRH National Referral Hospital and HH NRL | AMR Laboratory Fellow, Officer in Charge of the Microbiology Unit, Department of Pathology and Laboratory Medicine |
| Ragunath Sharma | JDWNRH National Referral Hospital and HH NRL | Laboratory Officer. Department of Pathology and Laboratory Medicine |
| Kinley Gyem* | RCDC HH Reference Laboratory | Senior laboratory officer |

Ghana

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Prof. Japheth Opintan | University of Ghana Department of Medical Microbiology | Medical Microbiologist (CG Team Leader) |
| Jabina Anaman | Aurum | Head, M&E Officer |
| Dziedzorm Awalime | Aurum | Head, M&E Officer |
| AMRCC Members |  |  |
| Dr Joycelyn Azeez | Ministry of Health | Chief Programme Officer, Pharmacy |
| Prof. Kwame Ohene-Buaben | Kwame Nkrumah University of Science & Technology | Vice chair AMR platform |
| Fleming Fund Fellows |  |  |
| Jennifer Bonnah | Food and Drugs Authority of Ghana | Pharmacist |
| Other decision makers |  |  |
| Dr Emmanuel Odame | Policy Planning, Budgeting, Monitoring and Evaluation Directorate (PPBMED), Ministry of Health | Director of Policy, Planning, Monitoring and Evaluation |
| Policy Fellows HH |  |  |
| Saviour Yevutsey | Chief Pharmacist’s Office, Ministry of Health | AMR Policy Analysis |
| Policy Fellows AH |  |  |
| William Kumah Adu | Director, Veterinary Services Directorate | AMR Advocacy & Resource Mobilization |
| Professional Fellows HH |  |  |
| Brian Adu Asare | Ministry of Health | AMR Health Informatics HH Fellow |
| Professional Fellows AH |  |  |
| Victoria Sedor | National Food Safety Laboratory | Laboratory technician |
| Dr Bashiru Boi Kikimoto | Ministry of Agriculture, Directorate of Veterinary Services | AMU/C Surveillance AH Fellow |
| Professional Fellow Aquaculture |  |  |
| Eric Sawyerr | Ministry of Fisheries and Aquaculture Development | Head, National Food Safety Laboratory |
| AMR Focal Point |  |  |
| Dr Bashiru Boi Kikimoto* | Ministry of Agriculture, Directorate of Veterinary Services | AMU/C Surveillance AH Fellow |
| Development Partners/ Academia |  |  |
| Uzoamaka Gilpin | FCDO | Health Adviser |
| Shamwill Issah | FCDO | Health Adviser |
| Yvonne Esseku | CwPAMS | Ghana Lead |
| Prof Eric Sampane-Donkor | Medical Microbiology Department at University of Ghana | Head (and PI PAARSE - RG) |
| Beatrice Puije | ASLM | EQuAfrica Lead |
| Raymond Fatchu | ASLM | EQuAfrica manager |
| MA |  |  |
| Adjo Mfodwo | MA | Regional Coordinator- West Africa |
| Bashiru Adams | MA | Regional Monitoring and Evaluation Coordinator- West Africa |
| Ruth Gaisie | MA | Regional Finance Officer |
| Hilary Lopes | MA | Regional One Health Specialist |
| ITAD |  |  |
| Kwame Asante | Former ITAD | Consultant |

Indonesia

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Dr Tom Weaver | Dewan Asuransi Indonesia (DAI) | Team Leader |
| Ms. Desrina Sitompul | DAI | Project Coordinator/Technical Programme Lead |
| Mr. Havan Yusuf | DAI | Lead Surveillance Specialist |
| Ms. Asih Hartanti | Health Security Partners (HSP) | Lead Laboratory Specialist |
| Prof. Amir Soebandrio | Eijkman Institute | Expert/Sub Grantee |
| Other decision makers |  |  |
| Dr Agus Suprapto., M.Kes | Coordinating Ministry for Human Development and Cultural Affairs/Kemenko PMK (Coordinator of AMR coordinating body) | Deputy of Quality Health Improvement and Population |
| Drh. Christina Retna Handayani | Ministry of Marine and Fish Affairs | Coordinator of Pest and Fish Diseases |
| Professional Fellows HH |  |  |
| Dr Titiek Sulistyowati, SpMk | Balai Besar Laboratorium Kesehatan (BBLK) Surabaya | AMR HH Laboratory Fellow |
| Ms. Tati Febriyanti., S.Si | National Institute of Health Research Development (NIHRD) | AMR HH Surveillance Fellow |
| Professional Fellows AH |  |  |
| Ms. Dinarti | Station for Investigation of Fish Disease and Environment (SIFDE) Serang | AMR AQ Laboratory Fellow |
| Drh. Liys Desmayanti | Directorate of Animal Health (DAH) – MoA | AMC/U AH Surveillance Fellow |
| Drh. Imron Suandy, MVPH | Directorate of Veterinary Public Health (DVPH) | AMR AH Surveillance Fellow |
| AMR Focal Point (no formal AMR Focal point at MoH and MoMF yet) |  |  |
| Prof. Dr Anis Karuniawati, PhD | National Agency Antimicrobial Resistance (KPRA) - MoH | Executive Secretary |
| Drh. Christina Retna Handayani., Msi* | Ministry of Marine and Fish Affairs | Coordinator of Pest and Fish Diseases |
| Drh. Purnama Martha Oktavia Simanjuntak., M.Si | Directorate Animal Health - Ministry of Agriculture | Surveillance and Animal Health Testing Sub Coordinator |
| GLASS Focal Point |  |  |
| Dr Nelly Puspandari , SpMK | NIHRD | GLASS Focal Point |
| WOAH Focal Point |  |  |
| Ms. Nuraini Triwijayanti | Directorate Animal Health - Ministry of Agriculture | WOAH Focal Point /Coordinator |
| Development Partners/ Academia |  |  |
| Dr Gunawan Budioutomo | FAO Emergency Centre for Transboundary Animal Diseases (ECTAD) | Senior Technical Advisor |
| Dr Luuk Schoonman | FAO-ECTAD | AMR/Chief Technical Advisor |
| Mr. Benyamin Sihombing | WHO | WHO Rep for Infection Prevention Control |
| Dr John Weaver | Australian Department of Foreign Affairs and Trade | International Veterinary Consultant |
| Prof. Agus Suwandono | INDOHUN (Indonesia One Health University Network) | One Health Workforce Technical Adviser for Indonesia |
| NRL & Site Visit |  |  |
| Dr H. Abidin, MPH | BBLK Surabaya | Chief of Laboratory |
| Mr. Yayan Sofyan, A.PI, MP | Station for Investigation of Fish Disease and Environment (SIFDE) Serang | Chief of Laboratory |
| Drh. Nasirudin MSc | NRL for Animal Health (BPMSPH) | Chief of Laboratory |
| Dr Titiek Sulistyowati, SpMk* | BBLK Surabaya | Head of Microbiology Installation |
| Dr Nida Hajidati Fauziyah | BBLK Jakarta | Medical Microbiologist |
| Ms. Dinarti* | Station for Investigation of Fish Disease and Environment (SIFDE) Serang | Laboratory Analyst |
| Dr Siti Rochmanah Oktaviani, SpMK | RSUP Dr Soetomo Surabaya (Sentinel Hospital) | Clinical Microbiologist |
| Dr Leonardus Widyatmoko, SpMK | RSUP Hasan Sadikin Bandung (Sentinel Hospital) | Clinical Microbiologist |
| Drh. Tri Widayati., MSc | DIC Wates /NRL AH | Medical Veterinary epidemiologist |
| Drh. Yuli Yanti., MSc | DIC Subang/Sentinel Laboratory AH | Medical Veterinary laboratory epidemiologist |
| Drh. Oli Susanti | BPSMPH Bogor, Ministry of Agriculture (Sentinel Laboratory AH) | Laboratory Coordinator |

Kenya

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Dr Revathi Gunturu | Aga Khan University Hospital, Nairobi | Associate Professor |
| Prof Sam Kariuki | KEMRI | Director of the Centre for Microbiology Research |
| Prof Eric Fevre | International Livestock Research Institute (ILRI) | Scientist |
| Dr Loice Acheng | Infectious Diseases Unit, University of Nairobi | Head of Department |
| Dr Morris Buliva | PATH Kenya | Former Operations Officer |
| NASIC Members |  |  |
| Dr Evelyn Wesangula | MOH Patient and Health Worker Safety Unit/ National Focal Point on AMR | Head of Patient and Health Worker Safety Unit; National Focal Point on AMR |
| Dr Allan Azegele | Department of Veterinary Services | Deputy Director |
| Dr Damaris Mwololo | Disease Control, Directorate of Veterinary Services (DVS), Ministry of Agriculture Livestock Fisheries and Cooperatives (MoLF), Kabete | WOAH AMR Focal Point |
| Dr Emmanuel Tanui | Laboratory | Head Biologist Analyst Unit |
| Susan Githij | National Public Health Laboratory | AMR Laboratory Coordinator |
| Dr Romona Ndanyi | Diagnostic Services & Efficacy Trials Centres, Directorate of Veterinary Services, | Assistant Director of Veterinary Services |
| Policy Fellows HH |  |  |
| Dr Evelyn Wesangula* | MOH Patient and Health Worker Safety Unit | Head of Patient and Health Worker Safety Unit |
| Policy Fellows AH |  |  |
| Dr Romona Ndanyi* | Diagnostic Services & Efficacy Trials Centres, Directorate of Veterinary Services, | Assistant Director of Veterinary Services |
| Professional Fellows HH |  |  |
| Susan Githij** | National Public Health Laboratory | AMR Laboratory Coordinator, AMR HH Laboratory Fellow |
| Grace Bartonjo | Ministry Of Health, National Public Health Laboratory | Epidemiologist, AMR Surveillance Fellow |
| Professional Fellow AH |  |  |
| Eunice Atieno Omondo | Veterinary Epidemiology and Economics Section/Directorate of Veterinary Services | Assistant Director of Veterinary Services |
| AMR Focal Point |  |  |
| Dr Evelyn Wesangula** | MOH Patient and Health Worker Safety Unit | Head of Patient and Health Worker Safety Unit; National Focal Point on AMR |
| Dr Allan Azegele* | Department of Veterinary Services | Deputy Director |
| GLASS Focal Point |  |  |
| Susan Githij** | National Public Health Laboratory | AMR Laboratory Coordinator |
| WOAH Focal Point |  |  |
| Dr Damaris Mwololo* | Disease Control/DVS, MoLF, Kabete | WOAH Focal Point |
| Development Partners/ Academia |  |  |
| Dr Joseph Mukoko | Management Sciences for Health/MTaPS Programme | Principal Technical Advisor |
| Fasina Folorunso | FAO ECTAD | Country Team Lead |
| Dr Tabitha Kimana | FAO | Regional ECTAD Veterinary Socio Economist & AMR Coordinator (Eastern Africa) |
| Dr Jane Lwoyero | WOAH | Programme Officer for AMR |
| NRL & Site Visit |  |  |
| Susan Githii*** | National Public Health Laboratory | AMR Laboratory Coordinator |
| Dr Romona Ndanyi** | Diagnostic Services & Efficacy Trials Centres, Directorate of Veterinary Services, Kenya | Assistant Director of Veterinary Services |
| David Ounah | Department of Veterinary Services; Head of CVL | Deputy Director of Veterinary Services |
| Dr Mahacla Odongo | University of Nairobi | Lecturer in Microbiology |
| Ann Munene | University of Nairobi | Microbiology Laboratory Head, Department of Veterinary Pathology |
| Dr Peninah Wamboi | Mariakani Veterinary Laboratory | Veterinary Officer |
| George Ambale | Mariakani Veterinary Laboratory | Chief Technologist |
| Merci Zawadi | Ministry Of Health, National Public Health Laboratory | Quality Manager |
| Tobias Nyanjong | Jaramogi Oginga Odinga Teaching and Referral Hospital | Assistant Laboratory Manager and QA manager |
| Grade Ndeda | Jaramogi Oginga Odinga Teaching and Referral Hospital | Laboratory Technologist and Officer in Charge, Microbiology Lab |

Laos

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Ms. Caroline Spigelski | UNOPS (former CG) | Project Manager |
| Dr Yu Kee Park | WHO (former CG) | Coordinator, Health Systems and Social Determinants of Health |
| Mr. Jean-Pierre LOMBART | Fondation Merieux | FM Country Representative |
| Francois-Xavier Babin* | Fondation Merieux | Systems |
| Benoit Chevalier* | Fondation Merieux | Country representative 2020-2021 |
| Dr Rungtip Chuanchuen | Faculty of Veterinary Science, Choulalongkorn University (Sub-grantee) | Professor |
| AMRCC Members |  |  |
| Mr. Intha Phoungsouvan | NAHL/DLF | Head of Project Management Unit and Head of Veterinarian Vaccination Centre |
| Other decision makers |  |  |
| Ms. Phouthavan Inlorlham | Food and Drug Department (FDD), MOH | Former Director of Drug and Medical Devices Control Division |
| Ms. Phuangmalay | Medical Supply Centre, MOH | Director of Procurement Division |
| Ms. Chantanee Buranathai | WOAH | One Health Coordinator |
| Dr Rattanaxay Phetsouvanh | DCDC | Director General |
| Policy Fellows HH |  |  |
| Dr Souphatsone Houattonkham | NCLE | Deputy Chief of Epidemiology unit |
| Professional Fellows HH |  |  |
| Dr Khambai Nouaylath | NCLE | Technical Officer, Laboratory |
| Professional Fellows AH |  |  |
| Dr Phouvong Phommachanh | NAHL/DLF | Director of NAHL |
| AMR Focal Point |  |  |
| Dr Bouakham Vannachone | DCDC | National AMR Focal Point |
| Dr Bounlom Douangngeun | FAO | AMR Focal Point |
| Development Partners/ Academia |  |  |
| Mr. Cashel Gleeson | UK Embassy | Deputy Head of Mission |
| Dr Elizabeth Ashley | LOMWRU | Director |
| NRL & Site Visits |  |  |
| Ms.Somphaivanh Chanthavong | NHAL | Head of micro lab, NAHL |
| Ms. Bouaphanh Khamphaphongphane | NCLE | Deputy Director of NCLE |
| Dr Noikaseumsy Suthivong | NCLE | Deputy Chief of Laboratory (and head of micro lab) |
| Dr Chanthala Phamisith | Savannakhet Human Health Laboratory | Vice Director, Savannaket Hospital |
| Dr Vatsana | Savannakhet Human Health Laboratory | Head of Savannaket Hospital Lab |
| Ms. Alavanh Samartmanivong | Savannaket Provincial Livestock and Fisheries Section | Director |
| Mr. Tony Duangchan | Savannaket Provincial Livestock and Fisheries Section | Deputy Director |
| Ms. Khamma Nammonty | Savannaket Provincial Livestock and Fisheries Section | Head of Savannaket Provincial Livestock and Fisheries Section Lab |
| Dr Phailin Maniphonh | Luang Prabang Provincial Hospital | Deputy Director of LPB hospital |
| Dr Valy Phongsavanh | Luang Prabang Provincial Hospital | Head of LPB hospital lab |

Nepal

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Khagendra KC, Bhagawan Shresta | FHI | Country Director |
| Dr Ritu Amatya | FHI | Programme Director |
| Parishan Shrestha | FHI | AMU/C |
| Nabin Paudel | FHI | AH |
| Sanjay Bhandari | FHI | Surveillance |
| Hari Shankar Joshi | FHI | Food Sector |
| AMRCC Members |  |  |
| Dr Madan Upadhyaya | AMRMSC Member Secretary (MoHP) | Chief QSRD |
| Other decision makers |  |  |
| Dr Dipendra Raman Singh | Department of Health Services | Director General |
| Dr Rama Nandan Tiwari | Department of Livestock Services | Director General |
| Policy Fellows HH |  |  |
| Dr Bikash Devkota | Lumbini Province, Ministry of Health | Secretary |
| Policy Fellows AH |  |  |
| Dr Barun Sharma | DGVS, Pulchowk | Joint Secretary |
| Professional Fellows HH |  |  |
| Mrs. Jyoti Acharya | National Public Health Laboratory | Human Health Fellow |
| Professional Fellows AH |  |  |
| Dr Suraj Subedi | CVL, Tripureshwor | Veterinary Officer |
| Dr Tulsi Ram Gampo | CVL | Veterinary Officer |
| AMC Focal Point |  |  |
| Kiran Sundar Bajracharya | Department of Drug Administration, Bijulibazar | Pharmacy Officer |
| AMR Focal Point |  |  |
| Dr Arun Govindakarnavara | WHO | Technical Officer |
| Dr Palpasa Kansakar | WHO | National Professional Officer |
| GLASS Focal Point |  |  |
| Mrs. Jyoti Acharya* | NPHL, Teku | GLASS Focal Point |
| WOAH Focal Point |  |  |
| Dr Nabin Upadhyaya | Government of Nepal, Ministry of Agriculture | WOAH Focal Point |
| Development Partners/ Academia |  |  |
| Dr Arun Govindakarnavara* | WHO | Medical Officer (Focal person for AMR) |
| Dr Palpasa Kansakar* | WHO | Medical Officer |
| Dr Surendra Karki | FAO | National Technical Coordinator at FAO |
| NRL & Site Visit |  |  |
| Mrs. Jyoti Acharya** | National Public Health Laboratory, Kathmandu (NRL, HH) | NRL Laboratory Manager |
| Dr Runa Jha | National Public Health Laboratory, Kathmandu (NRL, HH) | Director |
| Dr Sharmila Chapagain | CVL, Tripureshwor | Chief |
| Krishna Prasad Rai | Department of Food Technology and Quality Control, Food Microbiology Laboratory, Babarmahal, Kathmandu | Chief of Microbiology Laboratory |

Nigeria

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Blessing Stephen | DAI | Team Leader |
| Bernard Ebruke | IFAIN | Human Health Advisor |
| Sam Peters | IHVN | Human Health Advisor |
| MA |  |  |
| Adjo Mfodwo* | MA | Regional Coordinator- West Africa |
| ITAD |  |  |
| Paul Balogun | Itad | Senior Consultant |
| AMRCC Members |  |  |
| Dr Peter Umanah | FMARD DV | Co Chair, National Antimicrobial Coordination Committee (AMRCC) |
| Dr Tochi Okwor | Nigeria Centre for Disease Control (NCDC) | Chair/Programme Coordinator |
| Rita Okea | Ministry of Environment | Assistant Director, Pollution Control |
| Other decision makers |  |  |
| Prof. Onyebuchi Chukwu | National AMR-AMU Community of Practice | Chair |
| Dr Tosan Erhabor | Medical Science Laboratory Council of Nigeria (MSLCN) | Registrar/CEO |
| Dr Mudashir Idayat | NAFDAC | Director of Registration & Regulatory Affairs |
| Josephine Gatua | Overseas Development Institute | Overseas Development Institute/ Fleming Fund Fellow |
| Policy Fellows HH |  |  |
| Prof Aaron Aboderin | NTWG | Chair National Technical Working Group |
| Policy Fellows AH |  |  |
| Dr Peter Umanah* | FMARD DV | Co Chair, National Antimicrobial Coordination Committee (AMRCC) |
| Professional Fellows HH |  |  |
| Dr Abiodun Egwenu | NCDC | Field Epidemiologist |
| Dr Oluwadamilola Abiodun-Adewusi | NAFDAC | Field Epidemiologist |
| Professional Fellows AH |  |  |
| Mabel Aworh-Ajumobi | FMARD DVPCS | Epidemiologist |
| AMR Focal Point |  |  |
| Dr Abiodun Egwenu* | NCDC | Field Epidemiologist, AMR Focal Point Human Health |
| Mwapu Ndahi | FMARD DVPCS | Veterinarian, AMR Focal Point AH |
| WOAH Focal Point |  |  |
| Mwapu Ndahi* | FMARD DVPCS | Veterinarian, AMR Focal Point AH |
| Development Partners/ Academia |  |  |
| Guy Kouame | FAO ECTAD | FAO representative |
| Olubunmi Negedu-Momoh | UK Health Security Agency (Public Health England) | Laboratory Technical Adviser to the DG NCDC at Public Health England |
| Olusola Aruna | UK Health Security Agency (Public Health England) | Consultant in Public Health Medicine |
| NRL & Site Visit |  |  |
| Nwando Mba | NCDC | Director of Laboratory Services |
| Dr Sati Ngulukun | National Veterinary Research Institute (NVRI) | Director Diagnostics and Extension Services |

Pakistan

Pilot

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Dr Ayesha Rasheed | DAI | Team Lead |
| Dr Qadeer Ahsan | DAI | Technical Director |
| AMRCC Members |  |  |
| Dr Muhammad Akram | Ministry of National Food Security & Research (MONFSR) | Deputy AHC |
| Dr Muhammad Salman | National Institute of Health (NIH) | Chief PHLD, Head NRL |
| Munnaza Sarfaraz | NIH Secretariat | Coordinator AMR Secretariat |
| Other decision makers |  |  |
| Maj. Gen. Aamer Ikram | NIH | ED |
| Dr Qadeer Ahsan* | DAI | Technical Director |
| Dr Agha Waqar Yunus | National Veterinary Laboratories (NVL) | DG |
| Policy Fellows HH |  |  |
| Dr Ayesha Farooq | NIH | Head of Microbiology Department |
| Policy Fellows AH |  |  |
| Dr Naila Siddique | NRLPD | Programme Lead |
| Dr Muhammad Akram* | MONFSR | Deputy AHC |
| Professional Fellows HH |  |  |
| Zurva Ashraf | NIH | Senior Scientific Officer |
| Ayesha Zaman | NIH | Assistant Scientific Officer |
| Professional Fellows AH |  |  |
| Dr Muhammad Abubakar | NVL | Senior Scientific Officer |
| AMR Focal Point |  |  |
| Dr Muhammad Salman* | NIH | Chief PHLD |
| Muhammad Abubakar* | NVL | Senior Scientific Officer |
| WOAH Focal Point |  |  |
| Dr Muhammad Akram** | MONFSR | WOAH Focal Point |
| Development Partners/ Academia |  |  |
| Dr Syed Mashkoor Mohsin | Institute of Microbiology, University of Agriculture | Assistant Professor |
| Dr Muhammad Afzal | FAO | Programme Director |
| Asif Bettani | Public Health England (PHE) | Technical lead |
| NRL & Site Visit |  |  |
| Dr Muhammad Salman** | NIH | Chief PHLD, Head NRL |
| Dr Muhammad Abubakar** | NVL | Senior Scientific Officer |
| Dr Naila Siddique* | NRLPD | Programme Lead |
| Dr Ayesha Farooq* | NIH | Head of Microbiology Department |
| Dr Athar Abbas | NRLPD | Principal Scientific officer |
| Farhhan Afzal | PIR, RWP | Chief Scientific Officer |
| Dr Amtul Qadus | Jinnah Postgraduate Medical College (JPMC) | Head of Microbiology |

Country visit 2022

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Dr Usman Zaheer | DAI | Surveillance Lead |
| Tauqeer Mustafa | DAI | Project Officer |
| Farooq Tahir | FAO (Previously DAI) | National Project Coordinator (Previously Animal Health Lead) |
| Other decision makers |  |  |
| Dr Syed Asad Ali Shah | Directorate of Livestock & Dairy Development | Epidemiologist |
| Dr Shaheen Afridi | Department of Health - Khyber Pakhtunkhwa | Director General Health Services |
| Ghulam Fatima | Dr Ruth K.M.P Civil Hospital | Chief Pathologist Central Laboratory |
| Dr Quaid Saeed | Islamabad Health Regulatory Authority (IHRA) | CEO |
| AMR Focal Point |  |  |
| Dr Naveed Masood Memon | Health Department Government of Sindh | Deputy Director PDSRU AMR Focal Person for Human Health |
| GLASS Focal Point |  |  |
| Dr Afreenish Hassan | NIH | GLASS Focal Point |
| Development Partners/ Academia |  |  |
| Dr Saeed Ahmed | CDC | Consultant |
| Suban Qadir | CDC | Consultant |
| Dr Muhammad Sirtai | Public Health England | Lead |
| Dr Yusra Shafqat | Diagnostic and Research Laboratory, Liaquat University of Medical and Health Sciences (LUMHS) Jamshoro/Hyderabad | Assistant Professor |
| Dr Amtul Qadus* | Jinnah Postgraduate Medical College (JPMC) | Head of Microbiology |
| Pr Dr Azghar Amin | Pathology Department- Khyber Teaching Hospital MTI Peshawar | Professor |
| NRL & Site Visit |  |  |
| Dr Amtul Qadus** | Jinnah Postgraduate Medical College (JPMC) | Head of Microbiology |

Senegal

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Tafsir Abdoulaye Thiam | PATH | Technical Coordinator |
| Ahmadou Niang | FAO ECTAD | Country Team Leader |
| Coumba Diouf | FAO ECTAD | Country Team Leader |
| Aicha Marceline Sarr | Fondation Mérieux | Project Manager |
| MA |  |  |
| Adjo Mfodwo** | MA | Regional Coordinator, West Africa |
| AMRCC Members |  |  |
| Dr Adjaratou Diakhou Ndiaye | One Health Secretariat | Permanent secretary |
| Professional Fellows HH |  |  |
| Aissatou Ahmet Niang | Ministry of Health and Social Action, Laboratories Directorate | Head of the National Network of Laboratories Division |
| Professional Fellows AH |  |  |
| Anta Diagne | Division of Pharmacy and Veterinary Medicine, Ministry of Livestock | Fleming Fund Professional Fellow |
| Bissoume Sambe | Institut Pasteur de Dakar | Researcher/FAO AMR expert/ Professional Fellow Food Security & Environment |
| AMR Focal Point |  |  |
| Professor Amadou Moctar Dieye | Laboratories Directorate, Ministry of Health | Director of Laboratories |
| Dr Chantal Biagui | Ministère de l'Elevage (MEPA) Direction des Services Vétérinaires (DSV) | Chef du Bureau de l'Assurance Qualité / Point Focal RAM |
| WOAH Focal Point |  |  |
| Dr Moutar Seydi | Ministère de l'Elevage (MEPA) Direction des Services Vétérinaires (DSV) | Chef Bureau de la Pharmacie vétérinaire |
| Development Partners/ Academia |  |  |
| Dr Ndella Konate | Direction de la Qualité, de la Sécurité et de l’Hygiène Hospitalières | Director |
| Dr Mbargou Lo | Ministère de l'Elevage (MEPA) Direction des Services Vétérinaires (DSV) | Directeur des Services vétérinaires |
| Mme Fatou Bèye Sarre | LANAC - Ministère du Commerce | AMR Contact Point |
| Dr Mady Ba | WHO | NPO |
| Doudou Diop | PATH | USAID IDDS Lead |
| Pr Makhtar Camara | Institut de Recherche en Santé, de Surveillance Epidémiologique et de Formation (IRESSEF) | Professor |
| Awa Ba Diallo | Hopital Le Dantec | Colleague of Pr. Camara |
| NRL & Site Visit |  |  |
| Dr Rokhaya Diagne | Laboratoire National de Santé Publique | Director |
| Dr Mame Nahe Diouf | Laboratoire National de l'Elevage et de Recherches Vétérinaires (LNERV) | Director of the laboratory |
| Dr Mamadou Alpha Diallo | LNERV | Responsible for the microbiology laboratory |
| Mr Thierno NDIAYE | Hopital de St Louis | Director of the hospital |
| Pr Rihanatou Alambedji | Ecole Inter-Etats des Sciences et Medecine Vétérinaires (EISMV) | Director of the Microbiology lab |
| Pr Makhtar Camara* | Hopital Le Dantec | Responsable du laboratoire |
| Awa Ba Diallo* | Hopital Le Dantec | Responsable de l'unité de bactériologie |

Sierra Leone

| Fleming Fund CG |  |  |
| --- | --- | --- |
| James Bunn | WHO | BPEHS Cluster Lead |
| Anna Maruta | WHO | AMR/IPC Lead |
| Victoria Katawera | WHO | Laboratory Lead |
| Austine Bitek | FAO ECTAD | Epidemiologist |
| Bridget Oyah Kamara | FAO ECTAD | National Project Coordinator |
| Jacqueline Kasiiti Lichoti | FAO ECTAD | Laboratory Expert |
| MA |  |  |
| Adjo Mfodwo*** | MA | Regional Coordinator, West Africa |
| Bashiru Adams* | MA | M&E Officer |
| Ruth Gaisie* | MA | Finance Officer |
| Other decision makers |  |  |
| Dr James S. Squire | Ministry of Health and Sanitation (MoHS) | Programme Manager, National Disease Surveillance Programme |
| AMR Focal Point |  |  |
| Dr Joseph S Kanu | MoHS | Deputy Programme Manager, National Disease Surveillance Program, National AMR Focal Point |
| Kadiatu Kamara | MoHS | AMR Focal Point, Human Health |
| Dr Sahr R Gborie | Ministry of Agriculture and Forestry (MAF) | AMR Focal Point, AH |
| WOAH Focal Point |  |  |
| Dr Mohamed Alpha Bah | Ministry of Agriculture and Forestry (MAF) | Director of Livestock, WOAH Focal Point |
| AMU Focal Point |  |  |
| Jeanete Buck | MoHS | AMU focal person in Directorate Pharmaceutical Services |
| Development Partners/ Academia |  |  |
| Dr Shuwary Ade Barlatt | MoHS | CwPAMS |
| NRL & Site Visit |  |  |
| Dr Zikan Koroma | MoHS | National Programme Manager Clinical Laboratories and National Coordinator BioBanking & Biosecurity. |
| Santigue Kamara | MoHS | Laboratory Lead, Connaught Teaching Hospital |
| Alhaji Thaimu Kamara | MoHS | Laboratory Lead, Ola During Children's Hospital |
| Ahmed F Samba | Ministry of Agriculture and Forestry (MAF) | Laboratory Manager, Central Veterinary Laboratory |
| Roy Macaulay | MoHS | Laboratory Lead, Makeni Government Hospital |
| Dr Raoul Emeric Guetiya Wadoum | WHO | Laboratory Lead, COVID-19, Makeni Government Hospital |

Tanzania

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Loss Mensah | ASM | Senior Programme Officer |
| Wes Kim | ASM | Director, Global Public Health Programs |
| Victoria Shek | ASM | Programme Officer, Global Public Health Programs, ASM |
| Ade Olarewaju | ASM | Programme Officer, Global Public Health Programs, ASM |
| Mayur Banjara | ASM | Programme Officer, Global Public Health Programs, ASM |
| AMRCC Members |  |  |
| Dr Mtebe Majigo | Muhimbili University of Health and Allied Sciences | Microbiologist/Chair of the surveillance TWG |
| Elibariki Mwakapeje | FAO ECTAD | National Consultant for AMR ECTAD and Food Security |
| Rose Shija | WHO | Essential Medicines Advisor |
| Siana Mapunjo | Ministry of health community development gender elderly and children | Pharmaceutical Coordinator |
| Daudi Msasi | Ministry of health community development gender elderly and children | Director Pharmaceutical Services Unit |
| Dr Hezron Nonga | Ministry of Agriculture Livestock and Fisheries | Country Rep for WOAH, Director of veterinary services |
| Policy Fellows HH |  |  |
| Witness Mukalukwatage Mchwampaka | Ministry of health community development gender elderly and children | Epidemiologist and National IHR Focal Point |
| Policy Fellows AH |  |  |
| Dr Gibonce Kayuni | Ministry of Agriculture and Fisheries | AMU AH Surveillance Fellow, AMR Focal Point |
| Professional Fellows HH |  |  |
| Neema Camara | Ministry of Health/National Health Laboratory Quality Assurance and Training Centre | Epidemiologist, AMR HH Surveillance Fellow |
| Emmanuel Magembe | Ministry of Health/National Health Laboratory Quality Assurance and Training Centre | Laboratory Scientist, AMR HH Laboratory Fellow |
| Siana Mapunjo* | Ministry of health community development gender elderly and children | Pharmaceutical Coordinator, AMU HH Surveillance Fellow |
| Professional Fellows AH |  |  |
| Emmanuel Laurent Mayenga | Department of veterinary health | Public health veterinary officer, AMR AH Surveillance Fellow |
| AMR Focal Point |  |  |
| Dr Gibonce Kayuni* | Ministry of Agriculture and Fisheries | AMR Focal Point, AMU AH Surveillance Fellow |
| AMC Focal Point |  |  |
| Siana Mapunjo** | Ministry of health community development gender elderly and children | Pharmaceutical Coordinator, AMU Focal Point |
| AMC Focal Point |  |  |
| Godwin Minga | Ministry of Agriculture Livestock and Fisheries & Central Veterinary Laboratory | Laboratory Technologist - Microbiology |
| GLASS Focal Point |  |  |
| Reuben Abednego | Ministry of health community development gender elderly and children | Laboratory Scientist |
| WOAH Focal Point |  |  |
| Dr Hezron Nonga* | Ministry of Agriculture Livestock and Fisheries | Country Rep for WOAH, Director of veterinary services |
| Development Partners/ Academia |  |  |
| Edgar Lusaya | Medicines, Technologies and Pharmaceutical Services Programme (MTaPS), USAID | Country Project Director |
| Elibariki Mwakapeje* | FAO ECTAD | National Consultant for AMR ECTAD and Food Security |
| Rose Shija* | WHO | Essential Medicines Advisor |
| Dr Sril Kullaya | PATH | Tanzania Team Lead, Infectious Disease Detection and Surveillance (IDDS) Programme |
| NRL & Site Visit |  |  |
| Godwin Minga* | Ministry of Agriculture Livestock and Fisheries & Central Veterinary Laboratory | Laboratory Technologist - Microbiology |
| Adelina Gadiye | Muhimbili National Hospital Laboratory | Health Laboratory scientist |
| Ronald Benju | TVLA Mwanza Vet Lab | Laboratory Manager |
| Zechariah Igembe | Bugando Medical Centre | Head of Section, Microbiology, Laboratory Scientist |

Timor-Leste

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Dr Josh Francis | Menzies | Team Leader of CG1 grant |
| Dr Shawn Ting | Menzies | AH technical lead |
| MA |  |  |
| Professor Stanley Fenwick | MA | Regional Coordinator |
| AMRCC Members |  |  |
| Dr Joanita Jong | Ministry of Agriculture and Fisheries (MAF) | National AMRCC member |
| Other decision makers |  |  |
| Suzana Soares Hendriques | National Directorate for Pharmacy and Medicine - MoH | Lead on drafting the NAP |
| Dr Joanita Jong* | Ministry of Agriculture and Fisheries (MAF) | Lead on drafting the NAP |
| Professional Fellows HH |  |  |
| Dr Helio Sarmento Freitas Guterres | Guido Valadares National Hospital (HNGV) - MoH | Human Health AMR Clinician |
| Suzana Soares Hendriques* | National Directorate for Pharmacy and Medicine - MoH | Human Health AMU/C Surveillance fellows |
| AMR Focal Point |  |  |
| Suzana Soares Henriques** | Ministry of Health (MoH) | HH AMR focal point, Directorate for Pharmacy and Medicines |
| Dr Joanita Jong** | Ministry of Agriculture and Fisheries (MAF) | National Director of Veterinary Directorate, National AMRCC member |
| GLASS Focal Point |  |  |
| Delfim da Costa Xavier Ferreira | Ministry of Health (MoH) | National Directorate of Pharmacy & Medicines |
| WOAH Focal Point |  |  |
| Dr Joanita Jong*** | Ministry of Agriculture and Fisheries (MAF) | WOAH Focal Point |
| Development Partners/ Academia |  |  |
| Dr Dongbao Yu | WHO | Surveillance officer |
| NRL & Site Visit |  |  |
| Sra. Endang da Silva | Ministry of Health - National Health Laboratory | Executive Director of The National Health Laboratory |
| Suzana Soares Hendriques*** | HNGV | National Directorate for Pharmaceutical and Medicines, National AMR focal point |
| Delfim da Costa Xavier Ferreira* | National Directorate of Pharmacy & Medicines | Ministry of Health (MoH) |
| Dra. Joanita Jong**** | Ministry of Agriculture and Fisheries (MAF) | National Director of Veterinary Directorate |
| Dr Felisiano Da Conceicao | Veterinary Diagnostic Laboratory | Chief of Veterinary Diagnostic Laboratory |

Uganda

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Dr Jonathan Mayito | Infectious Diseases Institute | Project Manager |
| Francis Mohammed Larmode | Infectious Diseases Institute | Head of the Global Health Security Programme |
| Francis Kakooza | Infectious Diseases Institute | Deputy head, Global Health Security Department |
| Richard Walwema | Infectious Diseases Institute | Project Director |
| Simon Kasango | Infectious Diseases Institute | Senior Laboratory coordinator |
| Andrew Busuge | Infectious Diseases Institute | M&E officer |
| Rodney Mugasha | Infectious Diseases Institute | Health Information Manager |
| MA |  |  |
| Patrick Mubangizi | MA | Regional grants Coordinator |
| AMRCC Members |  |  |
| Dr Henry Kajumbula | Makerere University College of Health sciences | Chair, National AMR Sub-committee |
| Other decision makers |  |  |
| Dr Emmanuel Isingoma | Ministry of Agriculture, Animal Industry and Fisheries | Veterinary Officer |
| Betty Mbolanyi | Ministry of Water & Environment | Senior Environmental Officer |
| Policy Fellows HH |  |  |
| Mr. Musa Ssekamatte | Ministry of Health | National One Health Coordinator |
| Policy Fellows AH |  |  |
| Michael Kimaanga | Ministry of Agriculture, Animal Industry and Fisheries | Senior Veterinary Officer |
| Professional Fellows HH |  |  |
| Ibrahim Mugerwa | NRL | Secretary National AMR Sub-committee |
| Professional Fellows AH |  |  |
| Michael Omodo | National Animal Disease Diagnostics and Epidemiology Centre | Senior Veterinary Officer |
| Merab Acam | National Animal Disease Diagnostics and Epidemiology Centre | Senior Veterinary Officer |
| AMR Focal Point |  |  |
| Delegated to Dr Harriet Akello | Ministry of Health | Senior Pharmacist |
| Dr Anna Rose Ademun | Ministry of Agriculture, Animal Industry and Fisheries | Commissioner AH |
| GLASS Focal Point |  |  |
| Dr Grace Najjjuka | Uganda NRL | Director National Microbiology Reference Laboratory |
| Development Partners/ Academia |  |  |
| Prof Joel Bazira | Mbarara University | Head of Department Microbiology, Mbarara University |
| Wilberforce Owembabazi | USAID | Project Management Specialist/Global Health Security Lead |
| NRL & Site Visit |  |  |
| Dr Grace Najjjuka* | Uganda NRL | Director National Microbiology Reference Laboratory |
| Andrew Mbonye | Kabale Regional Referral Hospital | Laboratory Manager |
| Chrispus Ngabirano | Kabale Regional Referral Hospital | Microbiologist |
| Dr Celestine Barigye | Mbarara Hospital | Hospital Director |
| Professor Francis Oriokot | Mbarara Hospital | Senior Consultant |
| Dr William Olum Pjathui | Jinja Regional Hospital | Principal Pharmacist |
| Didas Atwebembere | Mbale Regional Referral Hospital | Head of Laboratory |
| Phiona Katami | Mbale Regional Referral Hospital | Head of Quality Assurance |
| Philip Wakimwere | Mbale Regional Veterinary Laboratory | Laboratory Manager |
| Mr. Godfrey Katumba | Ministry of Water& environment | Principal Water Analyst & NWQRL Laboratory |

Vietnam

| Fleming Fund CG |  |  |
| --- | --- | --- |
| Nguyen Thu Nam | FHI360 | Director |
| Nguyen Thi Le Quyen | FHI360 | M&E consultant |
| Mrs Nguyen To Nhu | PATH | Programme Director |
| AMRCC Members |  |  |
| Nguyen Thu Thuy | Ministry of Agriculture and Rural Development (DAH/MARD) | Vice Director, Department of AH |
| Cao Hung Thai | Ministry of Health (MSA/MOH) | Vice Director, Medical Services Administration |
| AMR Focal Point |  |  |
| Le Thi Hue | Vice Head of Veterinary Drugs Management Division (VDMD/DAH) | AMR Focal Point |
| Truong Le Van Ngoc | MSA/MOH | Vice Head of Professional Affairs, Inspection, Staff Health Protection Division |
| GLASS Focal Point |  |  |
| Truong Le Van Ngoc* | MSA/MOH | Vice Head of Professional Affairs, Inspection, Staff Health Protection Division |
| WOAH Focal Point |  |  |
| Le Thi Hue* | Vice Head of Veterinary Drugs Management Division (VDMD/DAH) | WOAH Focal Point |
| Development Partners/ Academia |  |  |
| Pawin Padungtod | FAO | Senior Technical Coordinator ECTAD |
| Michael J. O'leary | USAID | Senior Infectious Diseases Advisor |
| Rogier van Doorn | OUCRU-Ha Noi | Director |
| NRL & Site Visit |  |  |
| Chu Van Tuat | NCVHI1 | Head of Microbiology Department |
| Truong Thien Phu | Cho Ray Hospital | Head of Microbiology Department |
| Mai Van Tuan | Hue General Centre Hospital, Hue city | Head of Microbiology Department |
| Vo Minh Chau | National Centre for Veterinary Hygiene Inspection No. 2 (NCVHI 2) | Vice Head |
| Vu Phuong Thom | Saint Paul Hospital | Head of Microbiology Department |

Zambia

Pilot

| Fleming Fund CG |  |  |
| --- | --- | --- |
| David Ojok | Centre for Infectious Disease Research in Zambia (CIDRZ) | Director, Team Leader |
| Kaunda | Centre for Infectious Disease Research in Zambia | Project Manager |
| Prof. John Muma | University of Zambia (UNZA) | Professor, University of Zambia, School of Veterinary Medicine |
| Mott MacDonald |  |  |
| Patrick Mubangizi* | Mott MacDonald | Regional Coordinator, ESA |
| Other decision makers |  |  |
| Dr Swithine Kabilika | Department of Veterinary Services | Director |
| Prof. Roma Chilengi | Zambia National Public Health Institute (ZNPHI) | Director |
| Policy Fellows HH |  |  |
| Dr Otridah Kapona | ZNPHI | AMR Focal person |
| Professional Fellows HH |  |  |
| Dr Daniel Ndambasia | Zambia Medicines Regulatory Agency | Registration Officer – Veterinary Medicine |
| Mpanga Kasonde | ZNPHI | Laboratory Scientist |
| Professional Fellows AH |  |  |
| Taona Sinyawa | Central Veterinary Research Institute (CVRI) | Fleming Fund Fellow/Veterinary Officer |
| AMR Focal Point |  |  |
| Dr Otridah Kapona* | Zambia Public Health Institute | AMR Focal person |
| Dr Fusya Goma | National Livestock Epidemiological and Information Centre | Senior Veterinary Officer |
| Development Partners/ Academia |  |  |
| Yingst Samuel | CDC | Head of Laboratory |
| Joseph Pett | PHE | Senior Public Health Advisor |
| Dr Fred Masaninga | WHO | AMR Focal Person |
| Dr Geoffrey Mainda | FAO/DVS | Senior Veterinary Officer |
| NRL & Site Visit |  |  |
| Dr Chileshe Lukwesa | Lusaka District Health Office | Head of Laboratories |
| Dr Fredrick Banda | CVRI | Chief Veterinary Research Officer |
| Dr Aaron Shibemba | University Teaching Hospital | Head of Pathology and Microbiology |

Country Visit 2022

| Fleming Fund CG |  |  |
| --- | --- | --- |
| David Ojok* | Centre for Infectious Disease Research in Zambia | Director, Team Leader |
| Kaunda Kaunda* | Centre for Infectious Disease Research in Zambia | Project Manager |
| Mott MacDonald |  |  |
| Patrick Mubangizi** | Mott MacDonald | Regional Coordinator, ESA |
| Other decision makers |  |  |
| Prof. Roma Chilengi* | ZNPHI | Director |
| Policy Fellows HH |  |  |
| Dr Otridah Kapona | Zambia Public Health Institute | AMR Focal person |
| Professional Fellows HH |  |  |
| Mpanga Kasonde* | ZNPHI | Laboratory Scientist |
| Professional Fellows AH |  |  |
| Taona Sinyawa* | CVRI | Fleming Fund Fellow/Veterinary Officer |
| AMR Focal Point |  |  |
| Dr Otridah Kapona* | Zambia Public Health Institute | AMR Focal person |
| Dr Fusya Goma* | National Livestock Epidemiological and Information Centre | Senior Veterinary Officer |
| Development Partners/ Academia |  |  |
| Dr Geoffrey Mainda* | FAO/DVS | Senior Veterinary Officer |
| NRL & Site Visit |  |  |
| Dr Chileshe Lukwesa* | Lusaka District Health Office | Head of Laboratories |

Annex 21: Line of sight between findings, conclusions and recommendations

| Finding | Conclusion | Recommendation |
| --- | --- | --- |
| Quantity and quality (EQ1) |  |  |
| The starting position in most focus countries, whilst variable, gave something for the Fleming Fund to build on. AMR was a known problem, but NAPs were not being resourced or implemented; data on AMR existed in all countries to some extent, and in most countries, some laboratory capacity existed, although less in terms of quality processes. Capacity was stronger in HH than in AH. |  |  |
| There is evidence of increases in the quantity of HH AMR surveillance data in 11 of the 16 focus countries (69%), although the extent of change varies; and of increases in the quantity of other types of HH data beyond AMR. Progress is expected to continue during 2022 in most countries. | Conclusion 1: During phase 1, the Fleming Fund has made important progress in supporting countries develop foundations for national AMR and AMU surveillance programmes. |  |
| There is evidence of increases in the quantity of AH AMR surveillance data in 12 of the 16 focus countries (75%), with the extent of change also varied; fewer countries than in HH expect to see more progress during 2022. |  |  |
| Improvements in the quality of AMR testing were seen in HH and AH in a majority of countries, and progress is expected to continue. |  |  |
| With performance to date, it is clear that the MA achieved its stated aims for data generation as set out in the implementation plan, albeit targets reflecting low success criteria and not sector specific. |  |  |
| However, quality improvements have varied on a site-by-site basis and it is not clear whether the MA’s aims have been consistently achieved (given the limited delineation of quality goals at the start of phase 1). |  |  |
| Major drivers of increases in quantity and quality were identified as renovation of sites and provision of equipment, training of laboratory workforce, supporting laboratory quality management systems, and AMR governance. In some countries, increases in data were driven to some extent, by the addition of sites or pathogens to the surveillance system – drivers that are broadly outside Fleming Fund control. |  |  |
| Where no progress or reversals in quantity and quality were observed, we identified constraints to progress. In many cases, these were expressed in terms of ‘absence of’ or ‘delays with’ factors that were drivers of progress when present. |  |  |
| Overall, the Fleming Fund has made a vital or important contribution to most key drivers of increased quantity and quality in both HH and AH AMR data, albeit to a variable extent. |  |  |
| Use of AMR surveillance data (EQ4), including international data sharing (EQ5) |  |  |
| In summary, for phase 1 overall, there are initial indications that data from AMR surveillance systems are starting to be used. However, progress has been slower than anticipated, especially at the national level. | Conclusion 2: Building on these necessary foundations it is reasonable to expect that the Fleming Fund will be able to make progress towards achieving its higher-level goals for phase 2 (in terms of use of data for clinical improvement, policy and behaviour change), providing there is a stronger focus on understanding the needs and priorities of decision makers. Conclusion 6: The Fleming Fund deserves recognition for prioritising One Health and for convening cross-sectoral dialogues. The lack of models on how this can be operationalised at national scale has impacted the design of the Fleming Fund’s One Health approach. Experience from the joint research aspects of the Fellowship programme, which echoes wider experience in One Health, may help identify informal mechanisms to replicate during phase 2. Conclusion 7: During phase 1, planning by both the MA and DHSC was over-optimistic in terms of the time taken for design and approval and then delivery and it is not clear that this has been fully addressed for phase 2. | - Recommendation 3: The process of establishing goals at the country level should be focused on understanding the priorities and needs of key decision makers on AMR, recognising that a) AMR action will take place through multiple policy processes, and that differentiation between HH and AH is of fundamental importance; and b) achieving higher-level goals requires action by other actors and therefore effective collaboration with key stakeholder groups. |
| At the national level, data sharing with relevant committees is happening in six of the 16 focus countries. Even where AMR/C/U data is not yet being shared with relevant committees on a routine basis, some progress towards this goal has been realised in most countries. Despite good progress, Fleming Fund’s performance on data sharing falls short of the targets set out in the MA’s implementation plan, although this assessment differs from MA reporting because it is undertaken on a different basis. |  |  |
| Also at the national level, despite progress with sharing, AMR surveillance data is not yet playing a prominent role in relevant decision making at the national level. Some countries are taking action using different data. |  |  |
| At the international level, for HH more AMR data has been made available, with 81% (13 out of 16) of our focus countries sharing data to GLASS since 2018. In the AH sector, more data on AMC/U has been reported to WOAH by nine of the 16 focus countries. |  |  |
| - At the local/facility level, there is emergent evidence that Fleming Fund interventions are stimulating positive changes to practices and attitudes as clinicians and other stakeholders start to interact differently with improved laboratories. However, these are not yet representative of wider system changes within countries. We have identified a number of factors that have driven examples of data sharing and data use noted above. For data sharing these include increases in data availability, development of surveillance functions to link data to governance structures, and formal governance structures (albeit with important limitations observed) |  |  |
| - A wider range of drivers are relevant to the actual use of data (i.e. beyond data sharing) at the national level, recognising the limits of surveillance data itself and the complexity of non-linear policy processes. Key drivers include broader conditions for prioritisation of AMR being in place, and the availability of other forms of information. Similar drivers for data sharing at the international level were identified to those described at the national level – in terms of data availability and development of surveillance functions, with some differences in emphasis (e.g. less importance given to governance structures) |  |  |
| Facility-level drivers are less clear so far, although there is some indication that data availability is important and clinical engagement feedback loops have the potential to drive use. |  |  |
| - The Fleming Fund has made very substantial contributions to the main drivers of data sharing at the national level, primarily through CGs’ engagement with AMRCCs or equivalent committees. - Fleming Fund’s approach in phase 1, especially emphasising One Health and Fellowships, has contributed positively to the prospects for data use. Phase 1 RG activities have also helped to build consensus on data use issues and to equip stakeholders for future initiatives. However, limitations in the MA’s conceptual frameworks currently limit the prospects for Fleming Fund contributions to data use as part of a sustainable, aligned, country-owned approach. As a result, the Fleming Fund has so far only made a limited contribution to advancing the prospects for sustainable country-owned data use. - For changes in reporting to GLASS, the Fleming Fund has contributed to most but not all key drivers of data sharing in all countries, albeit with less significance than the Fleming Fund’s contribution to changes in data availability. For reporting to WOAH, the Fleming Fund has contributed to some drivers of data sharing in some countries, with limited contribution understandable given that this was not an area of focus for phase 1. |  |  |
| Sustainability (EQ3) |  |  |
| The MA has been clear that prospects for achieving sustainability during phase 1 were limited given the starting points in most countries and limited implementation time of some grants (this is backed up by broader evidence which underlines that sustainability is hard to achieve and takes time). The MA’s approach to sustainability has focused on a) hardwiring sustainability prospects in grant design, b) delivering success in Fleming Fund 1, c) increasing the focus on sustainability in CG2s. | Conclusion 5: Experience from phase 1 suggests that the Fleming Fund can strengthen its approach through further reflection, including in terms of using a stronger and prioritised sustainability lens from the start in deciding what support to provide to laboratories, working at the organisational level to sustain capacity building results, focusing on other data types as well as AMR, and differentiating more strongly between support provided to AH and HH phase 1 | Recommendation 4: The Fleming Fund should make specific adaptations to or emphases within its technical approach for phase 2, that are supported by experience from phase 1, including focusing on AMU and other data sources, identifying informal approaches to One Health multisector collaboration, and maximising the prospects for sustaining laboratory functions. |
| The MA approach to sustainability has limited the extent to which realistic expectations and plans have been established and actively discussed with key counterparts. |  |  |
| Based on action to date and the current status of country-level conditions, there are limited prospects for sustainability. Albeit somewhat moot now that a second phase of the Fleming Fund has been approved, if the Fleming Fund had stopped at the end of phase 1, sustaining results would have been extremely challenging. This is linked to the lack of progress in establishing key conditions, as identified in published literature; resources, capacity, and motivation. |  |  |
| For the drivers of progress on quantity and quality, the prospects for sustainability appear limited. Allocation of resources to AMR surveillance is key to sustainability but has not been a strong focus for phase 1. Some aspects of the Fleming Fund design could make securing resources more challenging. |  |  |
| Sustaining progress with capacity building and governance is challenging, relying on work at organisational and institutional levels. The MA has not focused strongly on this during phase 1. |  |  |
| - phase 2 appears set to address some of the challenges noted above, but it is not currently clear to the evaluation team exactly how this will be done. Sustainability is a shared responsibility between the DHSC, MA team and recipient governments. |  |  |
| Value for Money (EQ6), including alignment and coherence (EQ2) |  |  |
| In narrow terms (economy, efficiency) there is evidence of VfM having been delivered. But in terms of effectiveness (as defined by OECD) the case is less clear. |  |  |
| Economy: There is evidence of significant cost savings delivered by the MA, underpinned by strong systems to manage budgets and expenditure; performance is comparable to similar programmes. |  |  |
| Efficiency: delivering efficiently has been challenging in the context, and with the operational model that has been chosen, which affects VfM in terms of internal and external coherence, as well as management overheads. Efficiency has also been challenging to track given the focus on reporting implementation rates and the lack of a link between financial reporting and outputs; this seems to be driven by systems and cultures within DHSC. There is some evidence that the value of leveraged resources is reasonably significant in some grants . However, this indicator has not been reported or consistently tracked across all grants. The alignment between Fleming Fund expenditure, contribution and progress in generating quality AMR data was found to be high, suggesting a positive outcome in terms of VfM. | Conclusion 3: The programme has operated within a challenging context, which will continue into phase 2. The Fleming Fund has proven flexible enough to respond effectively, even though some features of the programme design made responding more challenging. |  |
| - Effectiveness: Overall there is evidence across the 16 countries in our sample that the Fleming Fund has contributed to improvements in establishing surveillance systems and data use. The headline finding varies slightly when we look at HH, AH and data use separately. The category of the country (level of surveillance system in place at the start of the grant) does not seem to be related to performance, however there is alignment between the length of grant implementation and performance – i.e. the longer the grant has been running the more change and contribution seen. | Conclusion 9: The Fleming Fund could strengthen its approach to managing for effectiveness at the country and portfolio levels. There has been progress in this regard during the course of phase 1, , in terms of developing a portfolio-level theory of change (ToC) and a core set of indicators; and the challenges observed reflect factors common in many aid programmes. But some challenges are particular to the Fleming Fund, and addressing these will be of increasing importance in phase 2.phase 1 | Recommendation 1: The DHSC and MA should ensure that clear, ambitious, realistic goals for phase 2 are in place from the outset, with targets to track progress. These should be established at the country and portfolio levels, based on understanding the current status of AMR surveillance systems and their use as developed during phase 1. Key areas to cover are around the phase 2 strategic shifts, in particular on the use of data (for clinical outcomes, national-level policy, behaviour change, and international-level sharing), and sustainability. |
| - Coherence: The model has created challenges in terms of delivering internal coherence between CGs, RGs and Fellowships. External coherence between all Fleming Fund grants and other DPs interventions was found to be strong in a majority of the focus countries but does not focus on linkages to wider (non-surveillance) aspects of the AMR response. | Conclusion 8: The complexity of the programme, with multiple Fund grantees operating at country level, has made it challenging to deliver coherence across the Fleming Fund’s investments. This has been exacerbated by the DHSC’s decision to expand the number of grantees. The challenge was recognised, and progress was made but focused mainly on avoiding duplication. Less progress has been made in enhancing synergy and greater overall effectiveness. Evidence of external coherence with external partners is strong within limits but reflects the lack of working formal government coordination mechanisms: ultimately external coherence should be the remit of AMRCCs but these are not always fully functional and do not always include all relevant non-government stakeholders. | Recommendation 5: The Fleming Fund should place greater emphasis on internal and external coherence and coordination from the outset of phase 2, including strengthening AMRCCs and NAPs to play this role and their linkages to institutional homes. |
| - The approach taken by DHSC and the MA to VfM generally aligns with FCDO and ICAI guidance. Overall, there are strong systems in place to manage economy and efficiency. However, the Fleming Fund has been weaker at establishing systems managing for effectiveness. In spite of some existing and planned adaptations to strengthen in this area, and Fleming Fund experience is not uncommon compared with other equivalent programmes, this is a key strategic requirement for phase 2. | Conclusion 4: The MA has successfully operationalised strong and effective procedures to manage economy and efficiency at activity level. With further use of the laboratory capacity established during phase 1, the overall VfM of the programme will be enhanced. | Recommendation 2: The DHSC and MA should ensure systems and processes for establishing expectations and tracking progress are proportionate, timely and sufficiently flexible to deal with uncertainty and the need for strategic adaptation. These must strike the right balance between strategic reflection and accountability and avoid focusing too heavily on tracking the implementation of inputs and activities. |

Annex 22: Contribution analysis visual summaries

C1a Changes in quantity of HH AMR data

| Countries | Extent of change | Renovation & Equipment | Human capacity | Governance/prioritisation | Consumables | Number of sites | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Appropriate spaces and equipment to perform microbiology/AST tests | Availability of well-trained laboratory staff at all levels | Effective oversight, coalition-building, regulation, attention to system-design and accountability and Increased focus by policymakers and senior staff within the system creating signals about importance | Availability of good quality consumable in sufficient quantity | Increase in the number of sites part of the AMR surveillance system | Clinician’s engagement, number of patients, data sharing |
| Indonesia | Considerable | Important | Important | Some |  |  |  |
| Kenya | Considerable | Important |  |  | Important | Important | Important |
| Nepal | Considerable | Important | Vital |  |  | Vital |  |
| Tanzania | Considerable | Vital | Important | Important | Important |  | Important |
| Uganda | Considerable |  | Important |  | Important | Vital |  |
| Vietnam | Considerable |  |  |  |  | Important | Important |
| Zambia | Considerable | Vital | Important | Important |  |  |  |
| Bangladesh | Limited | Vital | Vital | Vital |  |  |  |
| Ghana | Limited | Important | Some | Important |  |  |  |
| Laos | Limited | Important | Important |  |  | Important | Some |
| Timor-Leste | Limited | Vital | Vital | Some |  |  |  |
| Pakistan | Unclear | Vital | Important | Important |  |  |  |
| Nigeria | None yet | Vital |  | Some |  |  |  |
| Senegal | None yet | Important |  | Limited | Limited |  |  |
| Sierra Leone | None yet | Vital |  | Vital |  |  | Vital |
| Bhutan | Negative | Important |  |  | Vital |  |  |

C1b Changes in quality of HH AMR data

| Countries | Extent of change | Human capacity | Renovation & Equipment | QA | SOPs | Consumables | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Availability of well-trained laboratory staff at all levels in sufficient numbers | Appropriate spaces and equipment to perform microbiology/AST tests; equipment is working/serviced/maintained | Presence of appropriate internal and/or external QA systems/processes | Presence of appropriate and up-to-date SOPs | Availability of good quality consumable in sufficient quantity | Governance, data sharing, prioritisation, staff motivation, appropriate supervision |
| Bhutan | Considerable | Vital |  |  |  | Vital | Important |
| Ghana | Considerable | Important | Vital |  | Some |  |  |
| Kenya | Considerable | Important |  | Vital | Important | Important | Vital |
| Tanzania | Considerable | Important |  |  | Important | Important | Important |
| Timor-Leste | Considerable | Vital | Vital | Important |  |  |  |
| Vietnam | Considerable | Important |  | Some |  |  | Important |
| Bangladesh | Some | Vital | Vital |  |  |  | Vital |
| Indonesia | Some | Important | Vital |  |  |  | Some |
| Laos | Some | Important | Important | Some |  |  |  |
| Nepal | Some | Vital | Vital |  | Vital |  |  |
| Pakistan | Some | Vital |  | Important | Important |  |  |
| Zambia | Some | Important | Important |  |  |  |  |
| Nigeria | Limited |  | Important |  |  | Important | Important |
| Uganda | Limited | Important | Vital | Important | Important |  |  |
| Senegal | Limited | Important |  | Important |  |  | None |
| Sierra Leone | None yet | Vital | Vital |  |  |  |  |

C2a Changes in quantity of AH AMR data

| Countries | Extent of change | Human capacity | Renovation & Equipment | Governance/prioritisation | Number of sampling exercises | Consumables | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Availability of well-trained laboratory staff at all levels | Appropriate spaces and equipment to perform microbiology/ AST tests | Effective oversight, coalition-building, regulation, attention to system-design and accountability and Increased focus by policymakers and senior staff within the system creating signals about importance | Increase in the number of pathogens monitored as part of the AMR surveillance system | Availability of good quality consumable in sufficient quantity | Engagement with industry, research activities, situation analysis |
| Ghana | Considerable |  |  | Important | Important | Some |  |
| Indonesia | Considerable | Important | Important | Limited |  |  |  |
| Kenya | Considerable | Important | Vital | Important | Vital | Vital |  |
| Laos | Considerable | Vital | Vital |  | Vital |  |  |
| Nepal | Considerable | Vital | Vital |  |  | Vital |  |
| Vietnam | Considerable | Important |  |  | Vital |  |  |
| Bangladesh | Some | Important | Vital | Important |  |  |  |
| Bhutan | Some | Important | Vital |  |  |  |  |
| Senegal | Some |  | Important |  | Vital |  | Important |
| Tanzania | Some | Important |  |  | Important | Vital | Vital |
| Timor-Leste | Some | Vital | Vital | Some |  |  |  |
| Uganda | Limited | Vital |  |  | Vital | Vital |  |
| Zambia | Limited | Important | Vital | Important |  |  |  |
| Pakistan | Unclear | Vital | Vital | Vital |  |  |  |
| Nigeria | None yet |  |  | Important | Vital |  | None |
| Sierra Leone | None yet |  |  | Vital |  | None | Vital |

C2b Changes in quality of AH AMR data

| Countries | Extent of change | Human capacity | Renovation & Equipment | SOPs | Governance | QA | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Availability of well-trained laboratory staff at all levels | Appropriate spaces and equipment to perform microbiology/AST tests | Presence of appropriate and up-to-date SOPs | Effective oversight, coalition-building, regulation, attention to system-design and accountability | Presence of appropriate internal and/or external QA systems/processes | Consumable, staff motivation, appropriate supervision , transportation, situation analysis |
| Bhutan | Considerable | Vital | Vital |  |  |  | Vital |
| Kenya | Considerable | Important |  | Important | Important | Important |  |
| Tanzania | Considerable | Important | Vital |  |  |  | Vital |
| Timor-Leste | Considerable | Vital | Vital |  |  |  | Important |
| Vietnam | Considerable | Important | Some | Important |  |  |  |
| Bangladesh | Some |  | Vital | Important | Important |  |  |
| Indonesia | Some | Some |  | Limited |  | Some |  |
| Pakistan | Some | Vital |  |  |  | Important |  |
| Uganda | Some | Vital | Vital |  |  |  | Vital |
| Zambia | Some | Important | Important |  |  |  |  |
| Ghana | Limited | Important | Vital |  | Some |  |  |
| Nepal | Limited | Vital | Vital |  |  | Vital |  |
| Nigeria | Limited |  |  | Vital | Important | Vital |  |
| Laos | None yet | Vital | Vital |  |  |  | Important |
| Senegal | None yet | Important | Important |  | Some |  | Some |
| Sierra Leone | None yet | Some | None |  |  |  |  |

C3 Changes in data sharing with relevant committees

| Countries | Extent of change | Governance/ demand | Data supply | Data sharing processes | Incentives | Resourcing | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | One Health governance structures and systems to justify & enable data sharing; AMRCC exists or meets regularly | Availability of data in sufficient quantity/ quality to share | Adequate data sharing processes and systems (including IT systems) in place and functioning | People see specific value to data sharing; people want to take responsibility for data deficiencies | Availability of skilled personnel for work and/or of financing for work | Cooperation, entrepreneurs/champions, leadership demand, TA |
| Bangladesh | Considerable | Important | Important |  |  | Important |  |
| Nepal | Considerable | Vital | Vital |  |  |  |  |
| Kenya | Considerable | Important | Vital | Vital | Important |  |  |
| Tanzania | Considerable | Important | Important |  | Important |  |  |
| Uganda | Some | Vital | Important |  |  |  |  |
| Bhutan | Some | Important | Vital |  |  | Vital |  |
| Pakistan | Limited | ABSENT | PRESENT | Important |  |  | Some |
| Vietnam | Limited | Important | PRESENT | Some |  |  | Some |
| Laos | Limited | Important | PRESENT |  | Limited |  | Limited |
| Zambia | Limited | ABSENT | PRESENT | Important |  |  | Important |
| Ghana | Limited | Limited | Some | Important [CONSTRAINING] |  |  |  |
| Sierra Leone | Limited | PRESENT | Vital |  |  |  | Vital |
| Timor-Leste | Limited | ABSENT | Some |  | Some |  | Some |
| Indonesia | None yet | None | Limited | None |  |  |  |
| Nigeria | None yet | Important | Some |  |  |  | Some |
| Senegal | None yet | PRESENT | Some | Limited | Limited |  |  |

C4 Changes in data sharing with GLASS

| Countries | Extent of change | Data supply | TA | Data sharing processes | Resourcing/human capacity | Incentives | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Availability of data in sufficient quantity/quality to share | Proactive engagement of WHO or other partners to encourage and support collection and reporting of information to GLASS | Adequate data sharing processes and systems (including IT systems such as the new user-interface database platform) in place and functioning | Availability of skilled personnel for work and/or of financing for work/Shall be recoded to data supply or resourcing? | People see specific value to data sharing; people want to take responsibility for data deficiencies | Governance, external assistance, cooperation, leadership demand |
| Bhutan | Considerable | Vital |  |  |  |  | Important |
| Indonesia | Considerable |  |  |  | Important | Some |  |
| Nepal | Considerable | Vital |  | Vital | Vital |  |  |
| Pakistan | Considerable | Some |  |  |  |  | Important |
| Tanzania | Considerable | Important |  | Important |  |  | Important |
| Timor-Leste | Considerable | Vital |  |  |  |  |  |
| Uganda | Considerable | Vital | Vital | Some |  |  |  |
| Bangladesh | Some | Some |  |  | Limited |  |  |
| Kenya | Some | Important |  | Important | Important |  |  |
| Laos | Some | Important |  |  |  |  |  |
| Zambia | Some |  | Some | Important | Important |  |  |
| Ghana | Limited | Some | None |  |  |  | None |
| Nigeria | Limited | Important | Important | Limited |  |  |  |
| Senegal | None yet | Limited | None |  |  | Important |  |
| Sierra Leone | None yet |  | Vital |  |  |  |  |
| Vietnam | None yet | Important |  |  |  | Limited |  |

C5 Changes in data sharing with WOAH

| Countries | Extent of change | Data sharing processes | Data supply | Resourcing | TA/External assistance | Incentives | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Adequate data sharing processes and systems (including IT systems such as the new user-interface database platform) in place and functioning | Availability of data in sufficient quantity/ quality to share | Availability of skilled personnel for work and/or of financing for work | TA: Proactive engagement of WOAH, FAO or other partners to encourage and support collection and reporting of information to OIE | People see specific value to data sharing; people want to take responsibility for data deficiencies | Governance, cooperation, agenda linkage |
| Bhutan | Considerable | Vital | Vital |  |  |  | Important |
| Nepal | Considerable | Vital | Vital |  | Important |  |  |
| Senegal | Considerable | None |  |  | Important |  | Limited |
| Timor-Leste | Considerable | Vital |  | Vital |  |  |  |
| Zambia | Considerable | Important |  |  | Some |  | Important |
| Nigeria | Some |  | Important |  | None | Some |  |
| Tanzania | Some | None |  | None | None |  |  |
| Kenya | Limited | Important |  |  |  |  | Limited |
| Uganda | Limited | Important | Important |  |  |  |  |
| Bangladesh | Unclear | Important | Important | Important |  |  |  |
| Ghana | Unclear |  |  | None |  | None | None |
| Indonesia | Unclear |  |  |  |  |  | Some |
| Laos | Unclear |  | Important | Some |  | Limited |  |
| Pakistan | Unclear | Limited |  | Limited |  | Limited |  |
| Sierra Leone | None yet |  |  |  | Vital |  |  |
| Vietnam | None yet | Important | Limited |  |  |  |  |

Annex 23: Examples of Itad support to adaptations within phase 1 of the Fleming Fund

Itad facilitated a series of meetings to support the DHSC and MA to revisit learning from programme delivery and reflect on progress made on responding to the findings and suggestions from the country trip debriefs, evaluation reports and recommendations from the Annual Reviews. While the group agreed that some of this learning would be more feasible to address in a second phase of the Fleming Fund, the meetings identified several areas where action had been taken to incorporate learning into adaptation of the programme and what more could be done during the current phase, three of which are presented below.

Adaptive Management – Introducing an adequately resourced and more formalised approach. Progress included agreeing to hold regular reflection meetings between the DHSC and MA (informed by evidence from the evaluation) and holding a workshop dedicated to adaptive management. This workshop (held on 13th October, 2022) helped the DHSC and MA reflect on their experiences of adaptive management, compare these to lessons learned by others working in development, and to reach a better shared understanding of what an appropriate approach to adaptive management in phase 2 would look like.

Monitoring Success/Tracking Results – The second evaluation visit to Nepal had found that the current approach to monitoring and oversight of the Fleming Fund grants programme focused mainly on efficient delivery and not enough on whether the grant programme was on track to deliver the right things. Changes made in response to this issue included:

- A revamped and formalised management review processes at the quarterly review point including routine QA of the quarterly grantee review process by the UK team (oversight of risk and other management action and validation of grant RAG rating etc.)

- An introduction of KPIs on grantee progress along the LSHTM road map and submission of quality data to GLASS; this was reported by DHSC to be useful in giving a sense as to whether the programme was on track to achieve outcomes.

Need for a more efficient grant process for country grants to maximise the time available for implementation – While work continues on finding further ways to streamline the recommendation and approval process, progress has already been made, including:

- Revised work plan agreed in Summer 2019 that provided a flexible approach to the roll out of second round of Country Grants.

- Revised budget received and agreed with consideration of the delays to country grant roll-out.

- Ernst & Young assurance started at the same time as the London application reviews to save time.

- Updated fellowships approval process to save time.

- Agreement of six-month ‘no cost’ extension of Mott MacDonald’s contract to maximise achievement of original ambition whilst retaining VfM between fees and expenses, and grants.

The evaluation has also inputted into discussions on other key thematic issues, including:

- VfM – supporting a sharper focus on management and measurement of VfM, e.g. through discussion around VfM deep dives, requesting financial data for key elements of the programme;

- Sustainability – supporting work to strengthen sustainability approach to address key elements that are supported as ‘common practice’ from published literature;

- Use – encouraging focus on audiences, purposes of sharing etc. which contributed to a stronger focus on facility-level use as an important consideration that had originally been underemphasised in phase 1 design;

- Quality – as part of exploring EQ1, reviewing how quality was being measured contributing to an increased focus on how work to strengthen quality was being articulated;

- Coordination – highlighting issues that (whilst already known by the MA) contributed to improvements in information sharing between country and regional grantees and Fleming Fellows, plus other stakeholders (varying on a country-by-country basis).

Annex 24: Alignment and coherence of Fleming Fund interventions

| Country / criteria | Fleming Fund investments aligned with the NAP and other government policies/plans | MA portfolio and Global Projects well coordinated and internally coherent | Fleming Fund investments aligned with interventions funded by other DPs | Overall Summative Judgement on Coherence |
| --- | --- | --- | --- | --- |
| Bangladesh | All Fleming Fellows are government officials holding major positions and working on NAP priorities with close collaboration between the Fleming Fund, the government and the NRLs to align to government activities. | Coordination with RGs was more robust as compared with Fleming Fellows. Many Fleming Fellows have not contributed to the Country Coordination Meeting (CCM) and communication started in the late stages, especially for policy fellows. The Country Grantee (CG) promoted coordination and collaboration with the RGs and Fleming Fellows through bilateral meetings. More than 45 participants attended the CCM and shared their progress/updates. | There are examples of good collaboration, such as working with the WHO on PPS, A combined scoping visit etc. There were joint activities with the FAO and World Bank. However, there was no duplication. But the DPs feel that partnerships and alignments could be improved in future. | Very good coherence with NAP and government plans. Mechanisms for communication and working to develop synergies with Fellowships could be improved. External coordination with DPs was good and there was no chance of duplication. DPs expect more alignment in the future and feel consultation should be done at a higher level and in the design phase. |
| Bhutan | Strong alignment with government: strong AMR governance structure and clear government planning procedures to prevent duplication. The Fleming Fund contributes significantly to NAP activities. There is a close relationship between the Fleming Fund, RGOB and implementing departments. This is because the RGOB is the CG and because there are close existing personal and professional relationships between those involved in CG implementation, Fellowships etc. | Good coherence improved with stakeholders particularly between the CG and Fellowships. There was a good relationship between the MA’s Regional Coordinator (RC) the wider team and Host Institution (HI), and strong AMR governance has been supported for improvement. However, internal coherence between RGs and other investments could be improved. Most stakeholders were only aware of or familiar with one of the RGs due to stakeholders not being kept informed of what the RGs were doing. | Medium to strong coherence: the Fleming Fund provided most AMR support, with most other support coming from RGOB. WHO, and FAO. WOAH support focused on World Antibiotic Awareness Week (WAAW). FAO and WHO were not members of AMR governance committees but their membership in one of the committees may be useful in the future when the Fleming Fund ends. | Overall strong coherence/alignment, but there is room to improve internal coherence with RGs, and external coherence with DPs. |
| Ghana | The Fleming Fund seems to be well aligned with the NAP and supports its implementation. Also, alignment with government plans/policies seem to have improved significantly over time. However, there were (and still remain to be) challenges (in CG1) of bypassing the MoH and engaging directly with the University of Ghana (UG) leading to delay in implementing activities. Another concern is supported sentinel sites sitting outside the public healthcare delivery system (selected laboratories are outside the NPHRL) and AH laboratories work with the NFSL is limited. Lack of integration into national structures means collating data and reporting to GLASS/WOAH depends heavily on individual efforts. This threatens medium to long term sustainability. | Overall, there is limited internal coordination especially between CGs and regional/global grants. Multiple Fleming Fund activities were running concurrently but were somewhat disconnected and recipients were unaware these supports were all coming from the Fleming Fund. Persistence of original structural issues – choice of UG as original CG plus as main HH laboratory beneficiary has since been adjusted but has created path dependence where the lead HH organisation/NRL naturally looks more to the research side of the Fleming Fund programme than to national surveillance systems. | The Fleming Fund seems to be well aligned and coordinated to some extent with some key DPs – e.g., WHO, FAO, UNDP. However, the strength of coordination between the Fleming Fund and these DPs is not clear. Also, very limited funders are known for AMR work in Ghana beyond the Fleming Fund. Also, multiple funders were mentioned at some sites (e.g. Central Veterinary Laboratory) but they seem not to have any links/coordination with the Fleming Fund. There is potential overlap/duplication as these partners also provide equipment and consumables. | Alignment with government has multiple weaknesses. It improved over time but the effects of the Fleming Fund working outside government structures were still felt in different ways. There are good relations with the AMRCC. The AMRCC plays a coordinating role to ensure partner activities are aligned to government plans/priorities of the NAP. Some coordination exists especially among CGs and Fleming Fellows and this seems to have also improved over time especially at the introduction of CCMs. However, there is limited/weak coordination between CGs and regional and global grants. There is evidence of good alignment with a small circle of DPs, but not of formal coordination; and little to no evidence of coordination with other wider DPs. |
| Indonesia | Good alignment with government priorities. Examples of responding to emerging government requests. | There are some positive examples of collaboration between CG, Fleming Fellows and RGs. Country coordination meetings seem to be very effective and had good participation from internal and external stakeholders . | The risk of external duplication is currently very low, activities are coordinated with other DPs in the country like FAO, DFAT, WHO and USAID | Overall good coherence with government, CG, RG and DPs. |
| Kenya | Fleming Fund investments are very well aligned with the National AMR strategy, NAP and other government policies to alleviate AMR. | Various attempts by a former CG to support internal coordination, with mixed results. Ending original CG early compounded these challenges and reduced internal coherence - stakeholders raised lack of communication between different Fleming Fund interventions and there was an over-focus on individual work plans at the expense of coherence. | Fleming Fund investments were well aligned with interventions funded by other DPs because most DPs use the NAP and work through the NASIC. | Overall, there is strong GoK governance via the NASIC/AMRCC is ensuring strong overall coherence, despite weaker internal coherence between Fleming Fund investments partly as a result of the early termination of the first Country Grant. |
| Laos | Fleming Fund investments aligned with the NAP objective 2 on strengthening AMR surveillance. However, alignment with NAP objective 1 on awareness-raising could be strengthened. The Fleming Fund’s work also aligned with other government plans, such as the National Antimicrobial Resistance Surveillance Plan in Health Food Animals in Lao People’s Democratic Republic from 2020-21. | Internal coordination is challenging due to the multi-layered consortium, and a change in consortium with CG2. Multi-layered management of the consortium, and management of the Fleming Fund itself (MM and DHSC) creates challenges in managing duplication and ensuring effective communication, leading to limited collaboration between consortia members and AH and HH grantees. CGs and Fellowships were well coordinated, as Fellows are integrated into laboratories that the Fleming Fund supports. But there is limited evidence of coordination with RGs. CG had some coordination with QUARTZ, CAPTURA and EQASIA, but NCLE could not be involved in those due to the burden of COVID-19 work being too high. In contrast, LOMWRU had no interactions with RGs. | Fleming Fund and KOICA were two very similar projects which were able to complement each other due to the fact that WHO managed both. WHO’s AMR agenda used both KOICA and Fleming Fund funds interchangeably, as both focus on the same goals. Both projects were reported as well coordinated, by focusing on different geographical locations. There is no evidence that activities were duplicated by any other stakeholder in Laos. Despite the lack of duplication, there is a lack of coordination with not much coordination between the CG and other partners that are now outside of the consortia. | Overall, coherence has not been particularly successful and remains a weak point in the Fleming Fund’s intervention in Laos. Internal coherence was particularly weak, particularly due to the multi-layered consortium. Within both CG consortia there were communication issues. There was good alignment with the NAP, though this could be strengthened. External coherence has been somewhat successful. No regular formal AMR coordination meeting for all external AMR stakeholders; however, all AMR actors in Laos informally know each other and work together on various projects, which reduces the risk of duplication. |
| Nepal | It is clear that the Fleming Fund has been aligned with draft NAPs. The Fleming Fund focused on strategic objective 2 of the NAP - building a functional surveillance system. However, there are grounds to believe that alignment with national laboratory needs has not always been optimal. In particular, most of the equipment provided by the Fleming Fund remains unutilised. This has been attributed to 1) delays from CG in addressing non-functional equipment. 2)equipment not being always relevant for the specific laboratories, and 3) concerns by laboratory staff that using equipment will increase costs for the laboratory/patient. | Although activities are eventually aligned, thanks to regular communication and forums across Fleming Fund grants, this has not always been ingrained from the design stage. In particular, CGs are not always aware of what RGs are preparing at design stage. Fellowship seems to happen in parallel to the CG and RG rather than integrated, despite there being an intention for fellowships to support some CG activities. Rather than a problem of duplication, this causes lost synergies/missed opportunities for economies of scale. | There is good evidence of alignment with other DPs, both in terms of sharing progress and activities, as well as in laboratories supported by multiple partners. | The Fleming Fund very much aligned with NAPs. However, the actual implementation of the CG has not always been relevant to the needs of national laboratories. There are some examples of collaboration with RGs and Fleming Fund Fellows, but overall these operate parallel to CGs. There is good alignment with other DPs. There is no evidence of duplication, and risk is low. DPs and government are well connected thanks to different mechanisms such as meetings, training, and workshops. |
| Nigeria | The CG adapted programme plans to the NAP objectives. The Fleming Fund CG have actively engaged with the NCDC, FMARD, other government agencies & partners through the AMRCC, and TWGs. | CCM drives the process of collaboration and quarterly coordination meetings to maximise resources and effectively manage the Fleming Fund investments. But AH Fellows were frustrated with surveillance plans being dropped; there are many HH Fellows who are working in the system but not clear about CG work plans. | There is not much donor coordination. Alignment is not really developing into true synergy. Yet there are some examples of effective coordination, e.g. RKI working from CG SOPs in secondary sites or REDISSE being requested to provide HH consumables beyond the end of the CG. Coordination is ensured mostly through the AMRCC and TWG. | NCDC plays a lead role in ensuring partner, including Fleming Fund, activities meet needs and NAP objectives. The Fleming Fund has formal, periodic coordinating mechanisms: CCMs enable Fleming Fund grantees to share activity updates, progress and lessons which helps regional leads to improve coordination. External partners are engaged to share updates on partner projects which helps to avoid duplication. |
| Pakistan | Very good alignment with the government priorities, alignment is clear with all the objectives of NAP. Examples of need assessments, consultative meetings, and joint activities with Ministry of Food and Agriculture and also with NIH The Fleming Fund proposal built on the NAP and the activities proposed were mainly to address the gaps; starting from ensuring basic infrastructure and equipment are in place to allow surveillance of AMR . | Some positive examples of collaboration between CG, Fleming Fellows and RGs. CCM seems to be very effective and had good participation from internal stakeholders. Fellowships have incurred some challenges partly linked to coordination/design issues. CCMs are a good start but mechanisms to ensure internal coherence could be stronger. | Government to lead the coordination efforts and align the partners. WOAH, PHE, Islamabad health regulatory authority, FAO, FCDO, CDC are the key partners. There is close coordination and joint activities with FAO where possible. AMRCC remains the major platform where all partners working in AMR participate and activities are discussed. One on one meetings with technical partners are done as per the requirement. Activities can be better aligned with DPs (PHE, CDC) | Overall good coherence internally and externally but there is room for improvement. There is strong coordination with government. Fellowships have incurred some challenges partly linked to coordination/design issues. CCMs are a good start but mechanisms to ensure internal coherence could be stronger. The risk of external duplication is low and external coordination is somewhat outside the remit of the Fleming Fund. Alignment and Coordination with partners can be improved (CDC, PHE). |
| Sierra Leone | Fleming Fund grantees in HH and AH have been involved in the development of a NAP. This is central to the design of most Fleming Fund activities, which in CG1 have centred around building AMR governance structures. The Ministry of Health has good awareness of the Fleming Fund activities. | CG, RGs, and Global Projects are well aligned. 1. WHO collaboratively worked with FAO and RGs, through regular CCMs and ad-hoc engagement. 2. CG has good collaboration with procurement grantee in developing plans for laboratory refurbishment and to speed up decision making on refurbishment. | The Fleming Fund funds the main DPs working on AMR in Sierra Leone. Good coordination with other DPs through CCMs & ad-hoc meetings, working closely to identify gaps and strategies for addressing AMR challenges. Technical meetings were held with USAID and CDC. | The Fleming Fund CG has worked closely with other agencies. Fleming Fund grantees meet to share activity updates, progress and lessons, and leverage on relevant partner resources. There were few issues with Fleming Fellows. |
| Senegal | Stakeholders stated full alignment with the NAP and other government policies. The National High Council for Global Health Security provides a central One Health function with which the Fleming Fund is coordinating. | Fleming Fund investments in Senegal were mostly reported to have been exceptionally well-coordinated, taking advantage of strong in-country networks. MA & CG initiatives on CCMs helped avoid potential duplications with RGs. Global funding is now being mobilised through the Multi Partner Trust Fund. | Alignment with interventions funded by other DPs was generally good, supported by government’s coordinating role and strong in-country networks. However, little communication was apparent between the Fleming Fund and other DPs at country level. External alignment depended on implementing partners with weak incentives to highlight duplications or integrate efforts. | The Fleming Fund’s key activity was strengthening the One Health governance structure for AMR/U and by its nature requires the coordination of government stakeholders and the set up of forums to ensure alignment across government, DPs, and Fleming Fund grants. This has been set up successfully, with good evidence of functioning governance mechanisms and collaboration. |
| Tanzania | There was strong alignment/coherence with government, and the key supporting factors were strong overall government buy-in for AMR; strong AMR governance structure; and alignment with other agendas including the broader One Health agenda and GHS agenda (National Action Planning for Health Security). | Generally strong internal, stakeholders noted complementary design of different FF investments, and CCM mechanism as helping to avoid duplication. However, still some examples of duplication (risk of and actual) e.g. in support for quality management systems and conducting of laboratory assessments. Having ASLM as the grantee for three of the RGs and the HI for the Fellows supported internal coordination. | CGs, fellowships and RGs complementing support from USAID (IDDS – supporting four other sentinel sites and governance; MTAPS –supporting AMS and governance). The Fleming Fund FAO Global grant provides complementary support in AH e.g. surveillance in cattle (The Fleming Fund CG supports surveillance in poultry). CCM ensures coordination overall. DPs are invited to CCM and TWG as observers. | Overall strong coherence/alignment, but some room to improve internal coherence further via CCM and/or other mechanisms. |
| Timor-Leste | The current activities implemented by the CG and MoH are aligned with the NAP 2017-2021. The Fleming Fund proposal was built on the NAP and the activities proposed were mainly to address the gaps; starting from ensuring basic infrastructure and equipment are in place to allow surveillance of AMR. | Good coordination and internal coherence. Most fellows and RGs trainees also work directly with the CG so there is good awareness of the different strands of the Fleming Fund. Good coordination between CG and HI (Doherty). However, the fellowship model has been challenging, requiring involvement of CGs to support fellows. There was no evidence of serious risk of duplication found. | There was good alignment, which is to be expected given the small number of interventions on AMR in Timor-Leste, and further enabled by the CG also being the grantee for other DP projects. | Strong alignment and internal and external coherence supported by structure of FF set up and facilitated by limited number of actors in Timor-Leste. |
| Uganda | Fleming Fund investments are well aligned with the NAP. However some issues flagged indicated misalignment between the CG and national laboratories and governance, relating to 1) supplies and relevance of equipment; 2) support of staff in laboratories; 3) Data flow and ownership | Overall, it seems improvements could be made to coordination and coherence between the CG, RG and Fellowships. KIs expressed interest in this. Good evidence of CG and fellowship interaction - e.g. document development, active surveillance participation – but there scope to strengthen coordination within the fellowship scheme itself. Currently, there is no contact/focal person between RG and CG to ensure alignment. | Excellent alignment of Fleming Fund activities with other DP interventions. E.g. CG using the CDC-funded GHS project as a platform to increase testing and quality capacity for Fleming Fund HH AMR/AMU surveillance sites. During FF design, FF spoke to CDC to ensure coherence with existing funding of AMR. The awareness of FF activities by other DPs could be bolstered. | Good coherence with the NAP AMR but some implementation issues which indicate misalignment. The FFCG leads initiatives to ensure coordination. AMRCC and OH meetings generally include relevant stakeholders. Internal coordination mechanisms exist, but FFCG, FFS and RGs exist mostly as standalone programmes. Overall, risk of duplication is low. |
| Vietnam | Strong alignment of FF with the surveillance pillar of the NAP and related government priorities thanks to FF scoping activities and CG working closely with government counterparts during implementation. Now supporting the development of the National AMR Strategy. No duplication. | Some joint training between CAPTURA and the CG. CCMs seem like a good mechanism: HI (Erasmus) and RG (CAPTURA, and RADAAR) join in. There is also a Google sheet tracker for Fleming Fund partners (both national and regional) to see who is doing what, with which hospitals/areas, etc. The Fellows are not really active. | Strong external coherence due to the fact that the same partners (PATH, OUCRU, FAO, WHO.) receive funds from multiple donors and Coordination Working Group meetings bring DPs together to update each other AMR work/research and find potential collaboration opportunities. The risk of overlap is low. | The CG interventions were designed to fill gaps in the NAP; hence alignment has been built in from inception. Internal coherence is supported by CCMs and there is proactive coordination between CGs and RGs. The pre-existing network of donors supports effective external coherence. |
| Zambia | Fleming Fund investments are mostly aligned with national priorities as per the NAP. | They are mostly coherent but there are concerns on the transition between grants. CCM works well but mostly focused on information sharing. Policy Fellowships are not yet operationalised. | With few DPs in AMR space, Fleming Fund investments really aligned with the NAP. The AMRCC structure is in place, but overall coordination requires strengthening to ensure information sharing happens timeously. | There are no major alignment or coherence concerns, which is a reflection of good design and implementation and a supportive context. The main priority is to strengthen the AMRCC’s coordinating role. |

Annex 25: Mapping of grants by sample country

The table below presents a mapping of Fleming Fund grants by evaluation sample country. Global Projects (i.e. grants that were directly managed by DHSC) are not included, as they were not in scope for phase 1 evaluation.

Annex 26: Data collection tools: KII guides

KII Guide for AH AMR FP

AH AMR FP

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| POLICY 4.2 | What factors do you think are most important for national policymakers when considering whether AMR is a very severe and urgent problem? PROBE: (Refer to MSA on Indicators/Problem stream, test analysis) § (if need more information on MSA Load) How does AMR compare to other health policy problems? § (if need more information on MSA Feedback / TrACSS suggest links to other plans) Have public policy activities to address other problems started to suggest that AMR is important? § (need more information on MSA Focusing) What has or might focus policymakers’ attention on AMR? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 / Change 3 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 / Change 3 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes and systems, resourcing, incentives, formal barriers, cooperation, governance, leadership demand, analytical entrepreneurs / champions, other.. |  |
| EQ4 / Change 3 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ4 / Change 3 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.3 [OH] | We understand the AMRCC is expected to facilitate sharing and joint analysis of AMR data across different sectors. What is the nature of cross-sector collaborations being convened by the AMRCC? Which are the key institutions involved from different ministries? What is the nature of their involvement? In addition to facilitating AMR data use, what have been some of the other achievements of the AMRCC in your country? |  |
| 4.3 [OH] | What are some of the other multisector coordination mechanisms in place to make decisions around AMR at the national and subnational levels? Are there any bodies or platforms or events where people from different sector meet outside the government? (e.g. seminars, AMR awareness week, etc.) Can you recall some examples of collaborations between different sectors in the past, even if these do not specifically revolve around AMR? Probe joint research activities; Training programmes, fellowships, including Fleming Fellows; Joint outbreak response activities, such as Avian Influenza, Ebola, etc. |  |
| 4.3 [OH] | Where are these (formal and informal) coordination mechanisms located? Are these hosted by a ministry, government agency, academic body, think tank? (Probe for each of the collaborating mechanisms identified above, if possible): o Who chairs / leads the discussion? o Who sets the agenda? o What are its major functions/mandates? o How is it funded? o Can you describe any achievements / outcomes from these interactions? |  |
| 4.4 INTENDED USE | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data?o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |

KII Guide for AH Fellows

AH Fellows

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions |  | Response |
| --- | --- | --- | --- |
| EQ1 (AH) / Change 2a | To what extent and in which ways do you think the quantity of AH AMR/C/U data generated has improved since 2018? Summarise our understanding of changes in data quantity (with a focus on, samples) obtained from document review. To what extent your records on quantity of AMR/U/C data generated match with our understanding? |  |  |
| EQ1 (AH) | To what extent have active surveillance surveys been undertaken as part of a broader strategy? Probe on when relevant strategy was published. |  |  |
| EQ1 (AH) / Change 2a | What were the key change drivers/factors, in order of importance, behind such change? Probes: Number of active sampling exercises, Number of pathogens , human capacity, Renovation and equipment, consumable, Prioritisation, governance, engagement with agriculture/industry for sampling |  |  |
| EQ1 (AH) / Change 2a | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |  |
| EQ1 (AH) / Change 2a | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |  |
| EQ1 (AH) / Change 2b | To what extent and in which ways do you think the quality of AH AMR data has improved? -some prompts that maybe helpful for this question are (1) SOPs, (2) automated instruments, (3) internal and/or external quality assurance procedures, (4) better supplies of reagents/better quality equipment or infrastructure (eg fridges/freezers), (5) Training and/or supervision, (6) Quality manager, (7) Accreditation processes, (8) Reporting of data to clinicians (for HH). - Would be useful to get a feel for what level the improvements are at (references labs and/or surveillance sites or facility laboratories) |  |  |
| EQ1 (AH) / Change 2b | What were the key change drivers/factors, in order of importance, behind such change? Probes: investments in human capacity, renovation work abd improved equipment, reliable supply of reagents, SOPs, internal QA/QM, participation in EQA, prioritisation, governance, other... |  |  |
| EQ1 (AH) / Change 2b | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |  |
| EQ1 (AH) / Change 2b | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |  |
| EQ1 (AH) | To what extent is it plausible that there will be significant additional change in the system (in terms of increases in quantity and quality of AMR data) by end 2022? |  |  |
| EQ5 (AH) / Change 5 | Has there been an improvement in quantity and quality of AH AMU data shared internationally with OIE since 2018? Which reporting option was used then and which reporting option is used now?: Reporting Option 1: allows countries to distinguish quantities of antimicrobial agents by type of use (therapeutic or growth promotion); Reporting Option 2: allows countries to distinguish quantities of antimicrobial agents by type of use and animal groups (food-producing terrestrial and aquatic species and companion animals); Reporting Option 3: allows countries to distinguish quantities of antimicrobial agents by type of use and routes of administration (distinguishing by group of animals is optional) |  |  |
| EQ5 (AH) / Change 5 | To what extent and in which ways do you think the quality of AMU data reported to OIE has improved since 2018? (including changes within reporting options) |  |  |
| EQ5 (AH) / Change 5 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing process and systems, resourcing, incentives, cooperation, TA etc |  |  |
| EQ5 (AH) / Change 5 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |  |
| EQ5 (AH) / Change 5 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |  |
| EQ2 | To what extent CG, RG, Fellowships and Global Projects have been well coordinated and internally coherent? Probe: Are there any duplications between CG, RG, Fellowships and Global Projects? Probe: How effective have been mechanisms put in place by the MA to ensure internal coherence (such as the Country Coordination mechanisms) in delivering coherence? |  |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillance? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |  |
| EQ3 | To what extent have you formulated and implemented an exit plan with milestones and shared objectives? If not, why not? Has sustainability received sufficient attention to date? In what ways? |  |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |  |
| ACTIONS 4.1 |  | If there are any examples from your work of surveillance data already being used by other people for taking decisions about actions related to AMR, for example: - Local health professionals in treatment practices or guidelines - Patients or agricultural producers thinking about the way they use antimicrobials Please can we send you our Example of Use template for you to complete and return to us? This will help us communicate this success to Fleming Fund. |  |

KII Guide for AH NRL

AH Fellows

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions |  | Response |
| --- | --- | --- | --- |
| EQ1 (AH) / Change 2a | To what extent and in which ways do you think the quantity of AH AMR/C/U data generated has improved since 2018? Summarise our understanding of changes in data quantity (with a focus on, samples) obtained from document review. To what extent your records on quantity of AMR/U/C data generated match with our understanding? |  |  |
| EQ1 (AH) | To what extent have active surveillance surveys been undertaken as part of a broader strategy? Probe on when relevant strategy was published. |  |  |
| EQ1 (AH) / Change 2a | What were the key change drivers/factors, in order of importance, behind such change? Probes: Number of active sampling exercises, Number of pathogens , human capacity, Renovation and equipment, consumable, Prioritisation, governance, engagement with agriculture/industry for sampling |  |  |
| EQ1 (AH) / Change 2a | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |  |
| EQ1 (AH) / Change 2a | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |  |
| EQ1 (AH) / Change 2b | To what extent and in which ways do you think the quality of AH AMR data has improved? -some prompts that maybe helpful for this question are (1) SOPs, (2) automated instruments, (3) internal and/or external quality assurance procedures, (4) better supplies of reagents/better quality equipment or infrastructure (eg fridges/freezers), (5) Training and/or supervision, (6) Quality manager, (7) Accreditation processes, (8) Reporting of data to clinicians (for HH). - Would be useful to get a feel for what level the improvements are at (references labs and/or surveillance sites or facility laboratories) |  |  |
| EQ1 (AH) / Change 2b | What were the key change drivers/factors, in order of importance, behind such change? Probes: investments in human capacity, renovation work abd improved equipment, reliable supply of reagents, SOPs, internal QA/QM, participation in EQA, prioritisation, governance, other... |  |  |
| EQ1 (AH) / Change 2b | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |  |
| EQ1 (AH) / Change 2b | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |  |
| EQ1 (AH) | To what extent is it plausible that there will be significant additional change in the system (in terms of increases in quantity and quality of AMR data) by end 2022? |  |  |
| EQ5 (AH) / Change 5 | Has there been an improvement in quantity and quality of AH AMU data shared internationally with OIE since 2018? Which reporting option was used then and which reporting option is used now?: Reporting Option 1: allows countries to distinguish quantities of antimicrobial agents by type of use (therapeutic or growth promotion); Reporting Option 2: allows countries to distinguish quantities of antimicrobial agents by type of use and animal groups (food-producing terrestrial and aquatic species and companion animals); Reporting Option 3: allows countries to distinguish quantities of antimicrobial agents by type of use and routes of administration (distinguishing by group of animals is optional) |  |  |
| EQ5 (AH) / Change 5 | To what extent and in which ways do you think the quality of AMU data reported to OIE has improved since 2018? (including changes within reporting options) |  |  |
| EQ5 (AH) / Change 5 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing process and systems, resourcing, incentives, cooperation, TA etcWhat were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), increased access, increased willingness to make data available, momentum etc. |  |  |
| EQ5 (AH) / Change 5 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |  |
| EQ5 (AH) / Change 5 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |  |
| EQ2 | To what extent CG, RG, Fellowships and Global Projects have been well coordinated and internally coherent? Probe: Are there any duplications between CG, RG, Fellowships and Global Projects? Probe: How effective have been mechanisms put in place by the MA to ensure internal coherence (such as the Country Coordination mechanisms) in delivering coherence? |  |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillance? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |  |
| EQ3 | To what extent have you formulated and implemented an exit plan with milestones and shared objectives? If not, why not? Has sustainability received sufficient attention to date? In what ways? |  |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |  |
| ACTIONS 4.1 |  | If there are any examples from your work of surveillance data already being used by other people for taking decisions about actions related to AMR, for example: - Local health professionals in treatment practices or guidelines - Patients or agricultural producers thinking about the way they use antimicrobials Please can we send you our Example of Use template for you to complete and return to us? This will help us communicate this success to Fleming Fund. |  |

KII Guide for AH Site

AH Fellows

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions |  | Response |
| --- | --- | --- | --- |
| EQ1 (AH) / Change 2a | To what extent and in which ways do you think the quantity of AH AMR/C/U data generated has improved since 2018? Summarise our understanding of changes in data quantity (a focus on, samples) obtained from document review. To what extent your records on quantity of AMR/U/C data generated match with our understanding? |  |  |
| EQ1 (AH) | To what extent have active surveillance surveys been undertaken as part of a broader strategy? Probe on when relevant strategy was published. |  |  |
| EQ1 (AH) / Change 2a | What were the key change drivers/factors, in order of importance, behind such change? Probes: Number of active sampling exercises, Number of pathogens , human capacity, Renovation and equipment, consumable, Prioritisation, governance, engagement with agriculture/industry for sampling |  |  |
| EQ1 (AH) / Change 2a | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |  |
| EQ1 (AH) / Change 2a | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |  |
| EQ1 (AH) / Change 2b | To what extent and in which ways do you think the quality of AH AMR data has improved? -some prompts that maybe helpful for this question are (1) SOPs, (2) automated instruments, (3) internal and/or external quality assurance procedures, (4) better supplies of reagents/better quality equipment or infrastructure (eg fridges/freezers), (5) Training and/or supervision, (6) Quality manager, (7) Accreditation processes, (8) Reporting of data to clinicians (for HH). - Would be useful to get a feel for what level the improvements are at (references labs and/or surveillance sites or facility laboratories) |  |  |
| EQ1 (AH) / Change 2b | What were the key change drivers/factors, in order of importance, behind such change? Probes: investments in human capacity, renovation work abd improved equipment, reliable supply of reagents, SOPs, internal QA/QM, participation in EQA, prioritisation, governance, other... |  |  |
| EQ1 (AH) / Change 2b | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |  |
| EQ1 (AH) / Change 2b | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |  |
| EQ1 (AH) | To what extent is it plausible that there will be significant additional change in the system (in terms of increases in quantity and quality of AMR data) by end 2022? |  |  |
| EQ5 (AH) / Change 5 | Has there been an improvement in quantity and quality of AH AMU data shared internationally with OIE since 2018? Which reporting option was used then and which reporting option is used now?: Reporting Option 1: allows countries to distinguish quantities of antimicrobial agents by type of use (therapeutic or growth promotion); Reporting Option 2: allows countries to distinguish quantities of antimicrobial agents by type of use and animal groups (food-producing terrestrial and aquatic species and companion animals); Reporting Option 3: allows countries to distinguish quantities of antimicrobial agents by type of use and routes of administration (distinguishing by group of animals is optional) |  |  |
| EQ5 (AH) / Change 5 | To what extent and in which ways do you think the quality of AMU data reported to OIE has improved since 2018? (including changes within reporting options) |  |  |
| EQ5 (AH) / Change 5 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing process and systems, resourcing, incentives, cooperation, TA |  |  |
| EQ5 (AH) / Change 5 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |  |
| EQ5 (AH) / Change 5 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |  |
| EQ2 | To what extent CG, RG, Fellowships and Global Projects have been well coordinated and internally coherent? Probe: Are there any duplications between CG, RG, Fellowships and Global Projects? Probe: How effective have been mechanisms put in place by the MA to ensure internal coherence (such as the Country Coordination mechanisms) in delivering coherence? |  |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillance? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |  |
| EQ3 | To what extent have you formulated and implemented an exit plan with milestones and shared objectives? If not, why not? Has sustainability received sufficient attention to date? In what ways? |  |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |  |
| ACTIONS 4.1 |  | If there are any examples from your work of surveillance data already being used by other people for taking decisions about actions related to AMR, for example: - Local health professionals in treatment practices or guidelines - Patients or agricultural producers thinking about the way they use antimicrobials Please can we send you our Example of Use template for you to complete and return to us? This will help us communicate this success to Fleming Fund. |  |

KII Guide for AMRCC

AMRCC

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| POLICY 4.2 | What factors do you think are most important for national policymakers when considering whether AMR is a very severe and urgent problem? PROBE: (Refer to MSA on Indicators/Problem stream, test analysis) § (if need more information on MSA Load) How does AMR compare to other health policy problems? § (if need more information on MSA Feedback / TrACSS suggest links to other plans) Have public policy activities to address other problems started to suggest that AMR is important? § (need more information on MSA Focusing) What has or might focus policymakers’ attention on AMR? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 / Change 3 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 / Change 3 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes and systems, resourcing, incentives, formal barriers, cooperation, governance, leadership demand, analytical entrepreneurs / champions, other.. |  |
| EQ4 / Change 3 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: - Global Projects (name any active in country) - Other influencing factors (could be government activities, - interventions by other DPs or - exogenous factors such as COVID-19)? |  |
| EQ4 / Change 3 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.3 [OH] | We understand the AMRCC is expected to facilitate sharing and joint analysis of AMR data across different sectors. What is the nature of cross-sector collaborations being convened by the AMRCC? Which are the key institutions involved from different ministries? What is the nature of their involvement? In addition to facilitating AMR data use, what have been some of the other achievements of the AMRCC in your country? |  |
| 4.3 [OH] | What are some of the other multisector coordination mechanisms in place to make decisions around AMR at the national and subnational levels? Are there any bodies or platforms or events where people from different sector meet outside the government? (e.g. seminars, AMR awareness week, etc.) Can you recall some examples of collaborations between different sectors in the past, even if these do not specifically revolve around AMR? Probe joint research activities; Training programmes, fellowships, including Fleming Fellows; Joint outbreak response activities, such as Avian Influenza, Ebola, etc. |  |
| 4.3 [OH] | Where are these (formal and informal) coordination mechanisms located? Are these hosted by a ministry, government agency, academic body, think tank? (Probe for each of the collaborating mechanisms identified above, if possible): o Who chairs / leads the discussion? o Who sets the agenda? o What are its major functions/mandates? o How is it funded? o Can you describe any achievements / outcomes from these interactions? |  |
| 4.4 INTENDED USE | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data?o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |

KII Guide for CG teams

CG teams

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ1 (HH) / Change 1a | To what extent and in which ways do you think the quantity of HH AMR/C/U data generated has improved since 2018? Summarise our understanding of changes in data quantity (with a focus on samples) obtained from document review. To what extent your records on quantity of AMR/U/C data generated match with our understanding? |  |
| EQ1 (HH) / Change 1a | What were the key change drivers/factors, in order of importance, behind such change? Probes: number of sites, number of pathogens, human capacity, renovation and equipment, consumable, prioritisation, governance, awareness, clinician/health facility´s engagement, patient numbers etc. |  |
| EQ1 (HH) / Change 1a | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ1 (HH) / Change 1a | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (HH) / Change 1b | To what extent and in which ways do you think the quality of HH AMR data has improved? -some prompts that maybe helpful for this question are (1) SOPs, (2) automated instruments, (3) internal and/or external quality assurance procedures, (4) better supplies of reagents/better quality equipment or infrastructure (eg fridges/freezers), (5) Training and/or supervision, (6) Quality manager, (7) Accreditation processes, (8) Reporting of data to clinicians (for HH). - Would be useful to get a feel for what level the improvements are at (references labs and/or surveillance sites or facility laboratories) |  |
| EQ1 (HH) / Change 1b | What were the key change drivers/factors, in order of importance, behind such change? Probes: investments in human capacity renovation work and, improved equipment, reliable supply of reagents, SOP, QA, supervision, prioritisation, governance, other |  |
| EQ1 (HH) / Change 1b | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ1 (HH) / Change 1b | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (HH) | To what extent is it plausible that there will be significant additional change in the system (in terms of increases in quantity and quality of AMR data) by end 2022? |  |
| EQ1 (AH) / Change 2a | To what extent and in which ways do you think the quantity of AH AMR/C/U data generated has improved since 2018? Summarise our understanding of changes in data quantity (with a focus on, samples) obtained from document review. To what extent your records on quantity of AMR/U/C data generated match with our understanding? |  |
| EQ1 (AH) / Change 2a | To what extent have active surveillance surveys been undertaken as part of a broader strategy? Probe on when relevant strategy was published. |  |
| EQ1 (AH) / Change 2a | What were the key change drivers/factors, in order of importance, behind such change? Probes: Number of active sampling exercises, Number of pathogens , human capacity, renovation and equipment, consumable, Prioritisation, governance, engagement with agriculture/industry for sampling |  |
| EQ1 (AH) / Change 2a | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? To what extent were these surveys funded by the FF? Completely, partially, not at all? |  |
| EQ1 (AH) / Change 2a | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (AH) / Change 2b | To what extent and in which ways do you think the quality of AH AMR data has improved? -some prompts that maybe helpful for this question are (1) SOPs, (2) automated instruments, (3) internal and/or external quality assurance procedures, (4) better supplies of reagents/better quality equipment or infrastructure (eg fridges/freezers), (5) Training and/or supervision, (6) Quality manager, (7) Accreditation processes, (8) Reporting of data to clinicians (for HH). - Would be useful to get a feel for what level the improvements are at (references labs and/or surveillance sites or facility laboratories) |  |
| EQ1 (AH) / Change 2b | What were the key change drivers/factors, in order of importance, behind such change? Probes: investments in human capacity, renovation work and improved equipment, reliable supply of reagents, SOPs, internal QA/QM, participation in EQA, prioritisation, governance, other... |  |
| EQ1 (AH) / Change 2b | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |
| EQ1 (AH) / Change 2b | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (AH) | To what extent is it plausible that there will be significant additional change in the system (in terms of increases in quantity and quality of AMR data) by end 2022? |  |
| EQ5 (HH) | To what extent and in which ways do you think the quantity of HH AMR data reported to GLASS has improved since 2018? Summarise our understanding based on document review. To what extent do your records on quantity of AMR data reported matches our understanding? [NB: note and clarify understanding where data generated at country level is higher than data reported to GLASS and reasons] |  |
| EQ5 (HH) / Change 4 | To what extent and in which ways do you think the quality of HH AMR data reported to GLASS has improved since 2020 (noting that 2018 data was reported in 2020)? |  |
| EQ5 (HH) / Change 4 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes & systems, resources, incentives, legal factors, cooperation, TA, etc. |  |
| EQ5 EQ2 / Change 4 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |
| EQ5 (HH) / Change 4 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ5 (AH) / Change 5 | Has there been an improvement in quantity and quality of AH AMU data shared internationally with OIE since 2018? Which reporting option was used then and which reporting option is used now?: Reporting Option 1: allows countries to distinguish quantities of antimicrobial agents by type of use (therapeutic or growth promotion); Reporting Option 2: allows countries to distinguish quantities of antimicrobial agents by type of use and animal groups (food-producing terrestrial and aquatic species and companion animals); Reporting Option 3: allows countries to distinguish quantities of antimicrobial agents by type of use and routes of administration (distinguishing by group of animals is optional) |  |
| EQ5 (AH) / Change 5 | To what extent and in which ways do you think the quality of AMU data reported to OIE has improved since 2018? (includingchanges within reporting options) |  |
| EQ5 (AH) / Change 5 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing process and systems, resourcing, incentives, cooperation, TA etc |  |
| EQ5 (AH) / Change 5 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |
| EQ5 (AH) / Change 5 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent CG, RG, Fellowships and Global Projects have been well coordinated and internally coherent? Probe: Are there any duplications between CG, RG, Fellowships and Global Projects? Probe: How effective have been mechanisms put in place by the MA to ensure internal coherence (such as the Country Coordination mechanisms) in delivering coherence? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillance? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent have you formulated and implemented an exit plan with milestones and shared objectives? If not, why not? Has sustainability received sufficient attention to date? In what ways? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| ACTIONS 4.1 | Please update us on progress in collecting Examples of Use using the template we provided? By way of reminder, this form is designed to capture - Local/facility-based changes (as opposed to national system changes) - Specific examples of how AMR surveillance data has been used in practice, not just within surveillance systems themselves but to inform actions outside surveillance systems (for example, in clinical practice or to influence peoples’ decisions). - Examples where action has already taken place, not planned or expected action. |  |
| POLICY 4.2 | What factors do you think are most important for national policymakers when considering whether AMR is a very severe and urgent problem? PROBE: (Refer to MSA on Indicators/Problem stream, test analysis) § (if need more information on MSA Load) How does AMR compare to other health policy problems? § (if need more information on MSA Feedback / TrACSS suggest links to other plans) Have public policy activities to address other problems started to suggest that AMR is important? § (need more information on MSA Focusing) What has or might focus policymakers’ attention on AMR? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 / Change 3 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 / Change 3 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes and systems, resourcing, incentives, formal barriers, cooperation, governance, leadership demand, analytical entrepreneurs / champions, other.. |  |
| EQ4 / Change 3 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ4 / Change 3 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.3 [OH] | We understand the AMRCC is expected to facilitate sharing and joint analysis of AMR data across different sectors. What is the nature of cross-sector collaborations being convened by the AMRCC? Which are the key institutions involved from different ministries? What is the nature of their involvement? In addition to facilitating AMR data use, what have been some of the other achievements of the AMRCC in your country? |  |
| 4.3 [OH] | What are some of the other multisector coordination mechanisms in place to make decisions around AMR at the national and subnational levels? Are there any bodies or platforms or events where people from different sector meet outside the government? (e.g. seminars, AMR awareness week, etc.) Can you recall some examples of collaborations between different sectors in the past, even if these do not specifically revolve around AMR? Probe joint research activities; Training programmes, fellowships, including Fleming Fellows; Joint outbreak response activities, such as Avian Influenza, Ebola, etc. |  |
| 4.3 [OH] | Where are these (formal and informal) coordination mechanisms located? Are these hosted by a ministry, government agency, academic body, think tank? (Probe for each of the collaborating mechanisms identified above, if possible): o Who chairs / leads the discussion? o Who sets the agenda? o What are its major functions/mandates? o How is it funded? o Can you describe any achievements / outcomes from these interactions? |  |
| 4.4 INTENDED USE | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data? o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |
| 4.4 INTENDED USE | Do you think that the Fleming Fund has already established clear expectations for programme partners about how national uses of AMR surveillance data should be promoted? If yes, what are the expectations and how have they been established? |  |
| 4.4 INTENDED USE | Do you think that your organisation’s interests and capabilities suggest specific opportunities and strengths for future Fleming Fund efforts to support national AMR actions using surveillance data? o If yes, what are they? |  |

KII Guide for FAO

FAO

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ1 (AH) / Change 2a | To what extent and in which ways do you think the quantity of AH AMR/C/U data generated has improved since 2018? Summarise our understanding of changes in data quantity (a focus on, samples) obtained from document review. To what extent your records on quantity of AMR/U/C data generated match with our understanding? |  |
| EQ1 (AH) | To what extent have active surveillance surveys been undertaken as part of a broader strategy? Probe on when relevant strategy was published. |  |
| EQ1 (AH) / Change 2a | What were the key change drivers/factors, in order of importance, behind such change? Probes: Number of active sampling exercises, Number of pathogens , human capacity, renovation and equipment, consumable, Prioritisation, governance, engagement with agriculture/industry for sampling |  |
| EQ1 (AH) / Change 2a | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? To what extent were these surveys funded by the FF? Completely, partially, not at all? |  |
| EQ1 (AH) / Change 2aEQ1 (AH) | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation |  |
| EQ1 (AH) / Change 2bEQ1 (AH) | To what extent and in which ways do you think the quality of AH AMR data has improved? -some prompts that maybe helpful for this question are (1) SOPs, (2) automated instruments, (3) internal and/or external quality assurance procedures, (4) better supplies of reagents/better quality equipment or infrastructure (eg fridges/freezers), (5) Training and/or supervision, (6) Quality manager, (7) Accreditation processes, (8) Reporting of data to clinicians (for HH). - Would be useful to get a feel for what level the improvements are at (references labs and/or surveillance sites or facility laboratories) |  |
| EQ1 (AH) / Change 2b | What were the key change drivers/factors, in order of importance, behind such change? Probes: investments in human capacity, renovation work abd improved equipment, reliable supply of reagents, SOPs, internal QA/QM, participation in EQA, prioritisation, governance, other... |  |
| EQ1 (AH) / Change 2b | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |
| EQ1 (AH) / Change 2b | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (AH) | To what extent is it plausible that there will be significant additional change in the system (in terms of increases in quantity and quality of AMR data) by end 2022? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillance? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |

KII Guide for GLASS FP

GLASS FP

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ5 (HH) | To what extent and in which ways do you think the quantity of HH AMR data reported to GLASS has improved since 2018? Summarise our understanding based on document review. To what extent do your records on quantity of AMR data reported matches our understanding? [NB: note and clarify understanding where data generated at country level is higher than data reported to GLASS and reasons] |  |
| EQ5 (HH) | To what extent and in which ways do you think the quality of HH AMR data reported to GLASS has improved since 2020 (noting that 2018 data was reported in 2020)? |  |
| EQ5 (HH) | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes & systems, resources, incentives, legal factors, cooperation, TA, etc. |  |
| EQ5 EQ2 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |
| EQ5 (HH) | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| POLICY 4.2 | What factors do you think are most important for national policymakers when considering whether AMR is a very severe and urgent problem? PROBE: (Refer to MSA on Indicators/Problem stream, test analysis) § (if need more information on MSA Load) How does AMR compare to other health policy problems? § (if need more information on MSA Feedback / TrACSS suggest links to other plans) Have public policy activities to address other problems started to suggest that AMR is important? § (need more information on MSA Focusing) What has or might focus policymakers’ attention on AMR? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 | What were the key change drivers/factors, in order of importance, behind such change ? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), increased access, increased willingness to share data, increased capacity to analyse data, increase demand, momentum etc |  |
| EQ4 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ4 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.3 [OH] | We understand the AMRCC is expected to facilitate sharing and joint analysis of AMR data across different sectors. What is the nature of cross-sector collaborations being convened by the AMRCC? Which are the key institutions involved from different ministries? What is the nature of their involvement? In addition to facilitating AMR data use, what have been some of the other achievements of the AMRCC in your country? |  |
| 4.3 [OH] | What are some of the other multisector coordination mechanisms in place to make decisions around AMR at the national and subnational levels? Are there any bodies or platforms or events where people from different sector meet outside the government? (e.g. seminars, AMR awareness week, etc.) Can you recall some examples of collaborations between different sectors in the past, even if these do not specifically revolve around AMR? Probe joint research activities; Training programmes, fellowships, including Fleming Fellows; Joint outbreak response activities, such as Avian Influenza, Ebola, etc. |  |
| 4.3 [OH] | Where are these (formal and informal) coordination mechanisms located? Are these hosted by a ministry, government agency, academic body, think tank? (Probe for each of the collaborating mechanisms identified above, if possible): o Who chairs / leads the discussion? o Who sets the agenda? o What are its major functions/mandates? o How is it funded? o Can you describe any achievements / outcomes from these interactions? |  |
| 4.4 INTENDED USE | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data?o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |

KII Guide for HH AMR FP

HH AMR FP

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| POLICY 4.2 | What factors do you think are most important for national policymakers when considering whether AMR is a very severe and urgent problem? PROBE: (Refer to MSA on Indicators/Problem stream, test analysis) § (if need more information on MSA Load) How does AMR compare to other health policy problems? § (if need more information on MSA Feedback / TrACSS suggest links to other plans) Have public policy activities to address other problems started to suggest that AMR is important? § (need more information on MSA Focusing) What has or might focus policymakers’ attention on AMR? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 / Change 3 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 / Change 3 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes and systems, resourcing, incentives, formal barriers, cooperation, governance, leadership demand, analytical entrepreneurs / champions, other |  |
| EQ4 / Change 3 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ4 / Change 3 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.3 [OH] | We understand the AMRCC is expected to facilitate sharing and joint analysis of AMR data across different sectors. What is the nature of cross-sector collaborations being convened by the AMRCC? Which are the key institutions involved from different ministries? What is the nature of their involvement? In addition to facilitating AMR data use, what have been some of the other achievements of the AMRCC in your country? |  |
| 4.3 [OH] | What are some of the other multisector coordination mechanisms in place to make decisions around AMR at the national and subnational levels? Are there any bodies or platforms or events where people from different sector meet outside the government? (e.g. seminars, AMR awareness week, etc.) Can you recall some examples of collaborations between different sectors in the past, even if these do not specifically revolve around AMR? Probe joint research activities; Training programmes, fellowships, including Fleming Fellows; Joint outbreak response activities, such as Avian Influenza, Ebola, etc. |  |
| 4.3 [OH] | Where are these (formal and informal) coordination mechanisms located? Are these hosted by a ministry, government agency, academic body, think tank? (Probe for each of the collaborating mechanisms identified above, if possible): o Who chairs / leads the discussion? o Who sets the agenda? o What are its major functions/mandates? o How is it funded? o Can you describe any achievements / outcomes from these interactions? |  |
| 4.4 INTENDED USE | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data?o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |

KII Guide for HH Fellows

HH AMR FP

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| POLICY 4.2 | What factors do you think are most important for national policymakers when considering whether AMR is a very severe and urgent problem? PROBE: (Refer to MSA on Indicators/Problem stream, test analysis) § (if need more information on MSA Load) How does AMR compare to other health policy problems? § (if need more information on MSA Feedback / TrACSS suggest links to other plans) Have public policy activities to address other problems started to suggest that AMR is important? § (need more information on MSA Focusing) What has or might focus policymakers’ attention on AMR? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 / Change 3 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 / Change 3 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes and systems, resourcing, incentives, formal barriers, cooperation, governance, leadership demand, analytical entrepreneurs / champions, other |  |
| EQ4 / Change 3 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ4 / Change 3 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.3 [OH] | We understand the AMRCC is expected to facilitate sharing and joint analysis of AMR data across different sectors. What is the nature of cross-sector collaborations being convened by the AMRCC? Which are the key institutions involved from different ministries? What is the nature of their involvement? In addition to facilitating AMR data use, what have been some of the other achievements of the AMRCC in your country? |  |
| 4.3 [OH] | What are some of the other multisector coordination mechanisms in place to make decisions around AMR at the national and subnational levels? Are there any bodies or platforms or events where people from different sector meet outside the government? (e.g. seminars, AMR awareness week, etc.) Can you recall some examples of collaborations between different sectors in the past, even if these do not specifically revolve around AMR? Probe joint research activities; Training programmes, fellowships, including Fleming Fellows; Joint outbreak response activities, such as Avian Influenza, Ebola, etc. |  |
| 4.3 [OH] | Where are these (formal and informal) coordination mechanisms located? Are these hosted by a ministry, government agency, academic body, think tank? (Probe for each of the collaborating mechanisms identified above, if possible): o Who chairs / leads the discussion? o Who sets the agenda? o What are its major functions/mandates? o How is it funded? o Can you describe any achievements / outcomes from these interactions? |  |
| 4.4 INTENDED USE | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data?o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |

KII Guide for HH NRL

HH NRL

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ1 (HH) / Change 1a | To what extent and in which ways do you think the quantity of HH AMR/C/U data generated has improved since 2018? Summarise our understanding of changes in data quantity (sites, pathogens, samples) obtained from document review. To what extent your records on quantity of AMR/U/C data generated match with our understanding? |  |
| EQ1 (HH) / Change 1a | What were the key change drivers/factors, in order of importance, behind such change? Probes: number of sites, number of pathogens, human capacity, renovation and equipment, consumable, prioritisation, governance, awareness, clinician/health facility´s engagement, patient numbers etc. |  |
| EQ1 (HH) / Change 1a | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ1 (HH) / Change 1a | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (HH) / Change 1b | To what extent and in which ways do you think the quality of HH AMR data has improved? -some prompts that maybe helpful for this question are (1) SOPs, (2) automated instruments, (3) internal and/or external quality assurance procedures, (4) better supplies of reagents/better quality equipment or infrastructure (eg fridges/freezers), (5) Training and/or supervision, (6) Quality manager, (7) Accreditation processes, (8) Reporting of data to clinicians (for HH). - Would be useful to get a feel for what level the improvements are at (references labs and/or surveillance sites or facility laboratories) |  |
| EQ1 (HH) / Change 1b | What were the key change drivers/factors, in order of importance, behind such change? Probes: investments in human capacity renovation work and improved equipment, reliable supply of reagents, SOP, QA, supervision, prioritisation, governance, other |  |
| EQ1 (HH) / Change 1b | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ1 (HH) / Change 1b | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (HH) | To what extent is it plausible that there will be significant additional change in the system (in terms of increases in quantity and quality of AMR data) by end 2022? |  |
| EQ5 (HH) / Change 5 | To what extent and in which ways do you think the quantity of HH AMR data reported to GLASS has improved since 2018? Summarise our understanding based on document review. To what extent do your records on quantity of AMR data reported matches our understanding? [NB: note and clarify understanding where data generated at country level is higher than data reported to GLASS and reasons] |  |
| EQ5 (HH) / Change 5 | To what extent and in which ways do you think the quality of HH AMR data reported to GLASS has improved since 2020 (noting that 2018 data was reported in 2020)? |  |
| EQ5 (HH) / Change 5 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes & systems, resources, incentives, legal factors, cooperation, TA, etc. |  |
| EQ5 EQ2 / Change 5 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |
| EQ5 (HH) / Change 5 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |

KII Guide for HH site

HH NRL

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ1 (HH) / Change 1a | To what extent and in which ways do you think the quantity of HH AMR/C/U data generated has improved since 2018? Summarise our understanding of changes in data quantity (sites, pathogens, samples) obtained from document review. To what extent your records on quantity of AMR/U/C data generated match with our understanding? |  |
| EQ1 (HH) / Change 1a | What were the key change drivers/factors, in order of importance, behind such change? Probes: number of sites, number of pathogens, human capacity, renovation and equipment, consumable, prioritisation, governance, awareness, clinician/health facility´s engagement, patient numbers etc. |  |
| EQ1 (HH) / Change 1a | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ1 (HH) / Change 1a | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (HH) / Change 1b | To what extent and in which ways do you think the quality of HH AMR data has improved? -some prompts that maybe helpful for this question are (1) SOPs, (2) automated instruments, (3) internal and/or external quality assurance procedures, (4) better supplies of reagents/better quality equipment or infrastructure (eg fridges/freezers), (5) Training and/or supervision, (6) Quality manager, (7) Accreditation processes, (8) Reporting of data to clinicians (for HH). - Would be useful to get a feel for what level the improvements are at (references labs and/or surveillance sites or facility laboratories) |  |
| EQ1 (HH) / Change 1b | What were the key change drivers/factors, in order of importance, behind such change? Probes: investments in human capacity renovation work and improved equipment, reliable supply of reagents, SOP, QA, supervision, prioritisation, governance, |  |
| EQ1 (HH) / Change 1b | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ1 (HH) / Change 1b | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (HH) | To what extent is it plausible that there will be significant additional change in the system (in terms of increases in quantity and quality of AMR data) by end 2022? |  |
| EQ5 (HH) / Change 5 | To what extent and in which ways do you think the quantity of HH AMR data reported to GLASS has improved since 2018? Summarise our understanding based on document review. To what extent do your records on quantity of AMR data reported matches our understanding? [NB: note and clarify understanding where data generated at country level is higher than data reported to GLASS and reasons] |  |
| EQ5 (HH) / Change 5 | To what extent and in which ways do you think the quality of HH AMR data reported to GLASS has improved since 2020 (noting that 2018 data was reported in 2020)? |  |
| EQ5 (HH) / Change 5 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes & systems, resources, incentives, legal factors, cooperation, TA, etc |  |
| EQ5 EQ2 / Change 5 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |
| EQ5 (HH) / Change 5 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |

KII Guide for HI teams

HI teams

KII name:

KII date:

KII interviewer(s):

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in [summarise focus as per below guide]

• Confidentiality / permission to record

• Duration

• Opportunity for questions

| Theme | List of questions | Response |
| --- | --- | --- |
| QUANT & QUAL of HH data generated | Thinking about changes in QUANT & QUAL of HH data generated in those countries, what were the key change drivers/factors, behind such change? Probes: renovation work, improved equipment, reliable supply of reagents, investments in human resources, health seeking behaviours, clinicians’ engagement, increase in morale, partnerships, momentum etc. |  |
|  | What was the Fleming Fund Fellows contribution to those drivers? How vital was that it compared to the contribution of: -CG/RG - Global Projects -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
|  | If there was no or negative change in this area, why was that? And what have the Fellows done to improve the situation? |  |
| QUANT & QUAL of HH data generated | Thinking about changes in QUANT & QUAL of AH data generated in those countries, what were the key change drivers/factors, behind such change? Probes: renovation work, improved equipment, reliable supply of reagents, investments in human resources, health seeking behaviours, clinicians’ engagement, increase in morale, partnerships, momentum etc. |  |
|  | What was the Fleming Fund Fellows contribution to those drivers? How vital was that it compared to the contribution of: -CG/RG - Global Projects -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
|  | If there was no or negative change in this area, why was that? And what have the Fellows done to improve the situation? |  |
| QUANT & QUAL of data reported to GLASS | Thinking about changes in QUANT & QUAL of data reported to GLASS in those countries, what were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), increased access, increased willingness to make data available, momentum etc. |  |
|  | What was the Fleming Fund Fellows contribution to those drivers? How vital was that it compared to the contribution of: -CG/RG - Global Projects -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
|  | If there was no or negative change in this area, why was that? And what have the Fellows done to improve the situation? |  |
| QUANT & QUAL of data reported to OIE | Thinking about changes in AMU data reported to OIE, what were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), increased access, increased willingness to make data available, momentum etc. |  |
|  | What was the Fleming Fund Fellows contribution to those drivers? How vital was that it compared to the contribution of: -CG/RG - Global Projects -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
|  | If there was no or negative change in this area, why was that? And what have the Fellows done to improve the situation? |  |
| Coherence | To what extent CG, RG, Fellowships and Global Projects have been well coordinated and internally coherent? Probe: Are there any duplications between CG, RG, Fellowships and Global Projects? Probe: How effective have been mechanisms put in place by the MA to ensure internal coherence (such as the Country Coordination mechanisms) in delivering coherence? |  |
|  | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| Sustainability | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? To what extent is FF focused on addressing these conditions? |  |
|  | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? To what extent is FF focused on addressing these conditions? |  |
|  | To what extent have you formulated an exit plan? If not, why not? Has sustainability received sufficient attention to date? In what ways? |  |
| VfM | What steps have been taken to maximize economy (value for money in operational support)? For example, are inputs purchased to ensure they are appropriate quality and the right price at country level (e.g. benchmarked/compared to market rates)? Are prices / rates negotiated? Any examples? |  |
|  | What examples are there of efficiency, particularly in terms of achieving more results than planned within the original budget? Were there challenges with achieving efficiency and how were these managed? |  |
|  | Are any cost-sharing arrangements in place for the fellowship? e.g. with host institution or other partners? If yes, please describe |  |
| Archie’s note | Take time to frame by explaining EQ4 to them and asking whether/how they think work as HI to PFs fits into that |  |
| ACTIONS 4.1 (only for Policy fellows HI) | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
|  | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| Sharing of data with relevant committees (only for Policy fellows HI) | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), increased access, increased willingness to share data, increased capacity to analyse data, increase demand, momentum etc |  |
|  | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
|  | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| 4.4 INTENDED USE (only for Policy fellows HI) | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data? o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
|  | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |
|  | Do you think that the Fleming Fund has already established clear expectations for programme partners about how national uses of AMR surveillance data should be promoted? If yes, what are the expectations and how have they been established? |  |
|  | Do you think that your organisation’s interests and capabilities suggest specific opportunities and strengths for future Fleming Fund efforts to support national AMR actions using surveillance data? o If yes, what are they? |  |

KII Guide for MA Regional teams

MA regional teams

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent CG, RG, Fellowships and Global Projects have been well coordinated and internally coherent? Probe: Are there any duplications between CG, RG, Fellowships and Global Projects? Probe: How effective have been mechanisms put in place by the MA to ensure internal coherence (such as the Country Coordination mechanisms) in delivering coherence? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent have you formulated and implemented an exit plan with milestones and shared objectives? If not, why not? Has sustainability received sufficient attention to date? In what ways? |  |
| EQ6 | VfM: you will receive tailored questions from Jennifer |  |

KII Guide for OIE FP

OIE FP

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ5 (AH) / Change 5 | Has there been an improvement in quantity and quality of AH AMU data shared internationally with OIE since 2018? Which reporting option was used then and which reporting option is used now?: Reporting Option 1: allows countries to distinguish quantities of antimicrobial agents by type of use (therapeutic or growth promotion); Reporting Option 2: allows countries to distinguish quantities of antimicrobial agents by type of use and animal groups (food-producing terrestrial and aquatic species and companion animals); Reporting Option 3: allows countries to distinguish quantities of antimicrobial agents by type of use and (distinguishing by group of animals is optional) |  |
| EQ5 (AH) / Change 5 | To what extent and in which ways do you think the quality of AMU data reported to OIE has improved since 2018? (including changes within reporting options) |  |
| EQ5 (AH) / Change 5 | What were the key change drivers/factors, in order of importance, behind such change? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing process and systems, resourcing, incentives, cooperation, TA etc |  |
| EQ5 (AH) / Change 5 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19? |  |
| EQ5 (AH) / Change 5 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? | Also ask about alignment btw fellowships and CG support, satisfaction with fellowship/mentor and whether enough time to complete the fellowship activities |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| POLICY 4.2 | What factors do you think are most important for national policymakers when considering whether AMR is a very severe and urgent problem? PROBE: (Refer to MSA on Indicators/Problem stream, test analysis) § (if need more information on MSA Load) How does AMR compare to other health policy problems? § (if need more information on MSA Feedback / TrACSS suggest links to other plans) Have public policy activities to address other problems started to suggest that AMR is important? § (need more information on MSA Focusing) What has or might focus policymakers’ attention on AMR? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 | What were the key change drivers/factors, in order of importance, behind such change ? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), increased access, increased willingness to share data, increased capacity to analyse data, increase demand, momentum etc |  |
| EQ4 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ4 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.3 [OH] | We understand the AMRCC is expected to facilitate sharing and joint analysis of AMR data across different sectors. What is the nature of cross-sector collaborations being convened by the AMRCC? Which are the key institutions involved from different ministries? What is the nature of their involvement? In addition to facilitating AMR data use, what have been some of the other achievements of the AMRCC in your country? |  |
| 4.3 [OH] | What are some of the other multisector coordination mechanisms in place to make decisions around AMR at the national and subnational levels? Are there any bodies or platforms or events where people from different sector meet outside the government? (e.g. seminars, AMR awareness week, etc.) Can you recall some examples of collaborations between different sectors in the past, even if these do not specifically revolve around AMR? Probe joint research activities; Training programmes, fellowships, including Fleming Fellows; Joint outbreak response activities, such as Avian Influenza, Ebola, etc. |  |
| 4.3 [OH] | Where are these (formal and informal) coordination mechanisms located? Are these hosted by a ministry, government agency, academic body, think tank? (Probe for each of the collaborating mechanisms identified above, if possible): o Who chairs / leads the discussion? o Who sets the agenda? o What are its major functions/mandates? o How is it funded? o Can you describe any achievements / outcomes from these interactions? |  |
| 4.4 INTENDED USE | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data?o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |

KII Guide for other decision makes

Other decision makers

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| POLICY 4.2 | What factors do you think are most important for national policymakers when considering whether AMR is a very severe and urgent problem? PROBE: (Refer to MSA on Indicators/Problem stream, test analysis) § (if need more information on MSA Load) How does AMR compare to other health policy problems? § (if need more information on MSA Feedback / TrACSS suggest links to other plans) Have public policy activities to address other problems started to suggest that AMR is important? § (need more information on MSA Focusing) What has or might focus policymakers’ attention on AMR? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 / Change 3 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 | What were the key change drivers/factors, in order of importance, behind such change ? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes and systems, resourcing, incentives, formal barriers, cooperation, governance, leadership demand, analytical entrepreneurs / champions, other |  |
| EQ4 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ4 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.3 [OH] | We understand the AMRCC is expected to facilitate sharing and joint analysis of AMR data across different sectors. What is the nature of cross-sector collaborations being convened by the AMRCC? Which are the key institutions involved from different ministries? What is the nature of their involvement? In addition to facilitating AMR data use, what have been some of the other achievements of the AMRCC in your country? |  |
| 4.3 [OH] | What are some of the other multisector coordination mechanisms in place to make decisions around AMR at the national and subnational levels? Are there any bodies or platforms or events where people from different sector meet outside the government? (e.g. seminars, AMR awareness week, etc.) Can you recall some examples of collaborations between different sectors in the past, even if these do not specifically revolve around AMR? Probe joint research activities; Training programmes, fellowships, including Fleming Fellows; Joint outbreak response activities, such as Avian Influenza, Ebola, etc. |  |
| 4.3 [OH] | Where are these (formal and informal) coordination mechanisms located? Are these hosted by a ministry, government agency, academic body, think tank? (Probe for each of the collaborating mechanisms identified above, if possible): o Who chairs / leads the discussion? o Who sets the agenda? o What are its major functions/mandates? o How is it funded? o Can you describe any achievements / outcomes from these interactions? |  |
| 4.4 INTENDED USE | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data?o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |

KII Guide for other DPs

Other DPs

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |

KII Guide for Policy Fellows

Policy Fellows

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ2 | To what extent CG, RG, Fellowships and Global Projects have been well coordinated and internally coherent? Probe: Are there any duplications between CG, RG, Fellowships and Global Projects? Probe: How effective have been mechanisms put in place by the MA to ensure internal coherence (such as the Country Coordination mechanisms) in delivering coherence? |  |
| EQ3 | To what extent have you formulated and implemented an exit plan with milestones and shared objectives? If not, why not? Has sustainability received sufficient attention to date? In what ways? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| ACTIONS 4.1 | If there are any examples from your work of surveillance data already being used by other people for taking decisions about actions related to AMR, for example: - Local health professionals in treatment practices or guidelines - Patients or agricultural producers thinking about the way they use antimicrobials Please can we send you our Example of Use template for you to complete and return to us? This will help us communicate this success to Fleming Fund. |  |
| POLICY 4.2 | What factors do you think are most important for national policymakers when considering whether AMR is a very severe and urgent problem? PROBE: (Refer to MSA on Indicators/Problem stream, test analysis) § (if need more information on MSA Load) How does AMR compare to other health policy problems? § (if need more information on MSA Feedback / TrACSS suggest links to other plans) Have public policy activities to address other problems started to suggest that AMR is important? § (need more information on MSA Focusing) What has or might focus policymakers’ attention on AMR? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 / Change 3 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 / Change 3 | What were the key change drivers/factors, in order of importance, behind such change ? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes and systems, resourcing, incentives, formal barriers, cooperation, governance, leadership demand, analytical entrepreneurs / champions, other. |  |
| EQ4 / Change 3 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ4 / Change 3 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.3 [OH] | We understand the AMRCC is expected to facilitate sharing and joint analysis of AMR data across different sectors. What is the nature of cross-sector collaborations being convened by the AMRCC? Which are the key institutions involved from different ministries? What is the nature of their involvement? In addition to facilitating AMR data use, what have been some of the other achievements of the AMRCC in your country? |  |
| 4.3 [OH] | What are some of the other multisector coordination mechanisms in place to make decisions around AMR at the national and subnational levels? Are there any bodies or platforms or events where people from different sector meet outside the government? (e.g. seminars, AMR awareness week, etc.) Can you recall some examples of collaborations between different sectors in the past, even if these do not specifically revolve around AMR? Probe joint research activities; Training programmes, fellowships, including Fleming Fellows; Joint outbreak response activities, such as Avian Influenza, Ebola, etc. |  |
| 4.3 [OH] | Where are these (formal and informal) coordination mechanisms located? Are these hosted by a ministry, government agency, academic body, think tank? (Probe for each of the collaborating mechanisms identified above, if possible): o Who chairs / leads the discussion? o Who sets the agenda? o What are its major functions/mandates? o How is it funded? o Can you describe any achievements / outcomes from these interactions? |  |
| 4.4 INTENDED USE | Would you say that the national AMR effort includes a clear and effective strategy for informing specific national actions using surveillance data?o eg as opposed to international reporting or local clinical practice o If yes, how? What policy initiatives? What regulatory initiatives? What approach has been chosen to address practices and attitudes? (What approaches have been discarded?) o PROBE: are sectoral distinctions important, for example policy for gradual development of guidelines in human health but focused push to regulate certain antimicrobial uses in animal health? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |

KII Guide for WHO

WHO

KII name:

KII date:

KII interviewer(s):

Introduction – please adapt and summarise according to the stakeholder / her knowledge of the evaluation etc – aim to get this intro as short as possible.

• Thank you – Thank you the interviewee for having accepted the meeting and for their time today.

• Introductions –My name is xxxxxxx. On the evaluation of the Fleming Fund I am [specify your role in the evaluation and the country team] and I am joined today by my colleague [name, role and explain if the CL is joining remotely that is because of travel restrictions].

We work for Itad Itad, an UK-based company specialised in Monitoring, Evaluation and Learning that has been commissioned by the UK Department of Health and Social Care to conduct the Independent Evaluation of the Fleming Fund.

[Let others introduce themselves or tell them there will be a chance after you have explained the purpose of the interview]

[Acknowledge whether we have already interviewed the stakeholder during CV1/2]

• Purpose – The evaluation has a global focus and we collect data in a sample of 16 countries among which [name of the country in question]. This is the third and final data collection for now. The focus is to provide a summative judgement to our 6 Evaluation Questions.

• Focus – We are not evaluating the performance of your organisation or that of the CG grantee. We are interested in changes that have been achieved in the AMR surveillance system looking at the country/system level (rather than just those sites supported by the FF). We are interested in analysing to what extent the FF’s outputs, together with interventions by government and other development partners, have contributed to the outcomes of interests of DHSC which are

- More and better AMR/C/U data produced and shared at country level

- More and better AMR/C/U data shared internationally (with GLASS/OIE)

- Regulatory and policy change that can have an impact in reducing AMR

- Changes in practice / attitude towards the use of antimicrobials.

We have also questions relate to coherence of Fleming Fund efforts with those of other actors in country, sustainability of FF results and Value for Money [adapt the list as appropriate].

• Confidentiality / permission to record – Would it be okay if I record this interview, just as a back-up to my notes? We will delete the recordings after we have finished typing and reviewing our notes.  This interview is entirely confidential and if at any time you are uncomfortable with our questions or you want to end the interview, please just tell us. Findings/quotations will not be attributed to any individuals. We can also send you a copy of the report/interview if you request.

• Duration – I expect the interview to take approximately [specify length] – is that okay? If you do not have that much time let me know and I can make sure that I focus on the more important questions. Also, it’s absolutely fine if you do not know the answer to a question or prefer not to answer – just let me know and I’ll adapt the interview accordingly.

• Opportunity for questions – Do you have any questions before we start? Of course you are also welcome to ask questions through the interview if something is not clear.

| EQ | List of questions | Response |
| --- | --- | --- |
| EQ1 (HH) / Change 1a | To what extent and in which ways do you think the quantity of HH AMR/C/U data generated has improved since 2018? Summarise our understanding of changes in data quantity (with a focus on samples) obtained from document review. To what extent your records on quantity of AMR/U/C data generated match with our understanding? |  |
| EQ1 (HH) / Change 1a | What were the key change drivers/factors, in order of importance, behind such change? Probes: number of sites, number of pathogens, human capacity, renovation and equipment, consumable, prioritisation, governance, awareness, clinician/health facility´s engagement, patient numbers etc. |  |
| EQ1 (HH) / Change 1a | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ1 (HH) / Change 1a | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (HH) / Change 1b | To what extent and in which ways do you think the quality of HH AMR data has improved? -some prompts that maybe helpful for this question are (1) SOPs, (2) automated instruments, (3) internal and/or external quality assurance procedures, (4) better supplies of reagents/better quality equipment or infrastructure (eg fridges/freezers), (5) Training and/or supervision, (6) Quality manager, (7) Accreditation processes, (8) Reporting of data to clinicians (for HH). - Would be useful to get a feel for what level the improvements are at (references labs and/or surveillance sites or facility laboratories) |  |
| EQ1 (HH) / Change 1b | What were the key change drivers/factors, in order of importance, behind such change? Probes: investments in human capacity renovation work and improved equipment, reliable supply of reagents, SOP, QA, supervision, prioritisation, governance, other |  |
| EQ1 (HH) / Change 1b | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: -Global Projects (name any active in country) -Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ1 (HH) / Change 1b | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| EQ1 (HH) | To what extent is it plausible that there will be significant additional change in the system (in terms of increases in quantity and quality of AMR data) by end 2022? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with the NAP and other government policies/plans? Probe: Are there any duplications between Fleming Fund's investments and government initiatives? Probe: Through which mechanisms was alignment ensured? |  |
| EQ2 | To what extent have the Fleming Fund's investments been aligned with interventions funded by other DPs? Probe: Are there any duplications between Fleming Fund's investments and DP initiatives? Probe: Through which mechanisms did the Fleming Fund coordinate with other DPs involved in AMR / lab strengthening in country? |  |
| EQ3 | To what extent do you think the required capacity exists to sustain these results (quantity, quality, int. sharing)? PROBES: any concerns about turnover of staff, who conducts refresher training (in absence of FF), is AMR part of pre-service training (eg curriculum), are staff permanent or contactors (paid by whom)? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| EQ3 | To what extent do you think staff are motivated to put new skills / responsibilities required to maintain AMR surveillence? PROBES: Is throughput sufficient? Are consumable supplies assured? Are managers and institutions (eg AMRCC) interested in outputs and providing feedback? Will competing demands crowd in? Are there adequate plans in place to address any concerns? To what extent is FF focused on addressing these conditions? |  |
| ACTIONS 4.1 | Do you think that surveillance data is already being used to inform strong national actions on AMR (policy implementation, regulatory change or change to national clinical guidelines?) If yes, please give examples PROBE: How did Fleming Fund activities contribute to these actions? If no, do you think that the main use so far has been for general awareness-raising in professional and policy networks? PROBE: Do you think that we are still at an early stage of the cycle of AMR data analysis for policy? |  |
| ACTIONS 4.1 | Thinking about the kinds of strong national actions that might be relevant to AMR (for example controls on certain uses of antimicrobials or initiatives to change professional practices), can you think of examples from the past (prior to FF) and/or not motivated by surveillance data? PROBE: (Refer to any examples suggested by MSA analysis or other information gathered) If yes, please give details. PROBE: what is different now / what motivates action if not surveillance data? |  |
| POLICY 4.2 | Has Covid-19 been a distraction, slowing down progress with the national AMR agenda? PROBE: Has AMRCC met regularly since 2020, including at political as well as technical levels? Has it started to take significant decisions? |  |
| POLICY 4.2 | Have NAP plans continued to develop strongly since 2020? (OR, if NAP expires in 2020-22, is there a process underway for its renewal; do you expect any delay in extending the NAP?) PROBE: What factors explain the current situation in relation to the NAP? (if need more information to complete NAP tool, apart from on budgeting) How exactly is the NAP moving from a plan to real action and change? |  |
| POLICY 4.2 | Do you think that it is likely that there will be significant on-budget domestic funding for AMR initiatives in the foreseeable future? If yes, please give reasons (have the reasons for prior budget decisions changed?) If no, will funding from international supporters be sufficient? To what extent is FF focused on addressing these conditions? |  |
| POLICY 4.2 / Change 3 | Does AMRCC (or other national body in charge of the country AMR strategy) receive AMR data reports generated by surveillance sites at least once a year? Is that an improvement compared to 2018 (i.e. Prior to Fleming Fund activities starting)? PROBE if yes: which organisation(s) assembles and submits these reports? What form do they take, what are they called (descriptive summary or analytical)? Is there good sector representation and national coverage? If yes, do you think that the reports are sufficient to amend national AMR strategy and enable effective AMR decision-making? If no, why not? |  |
| EQ4 / Change 3 | What were the key change drivers/factors, in order of importance, behind such change ? Probes: more and better data available from the surveillance system (in which case refer to QUANT & QUAL contribution stories), data sharing processes and systems, resourcing, incentives, formal barriers, cooperation, governance, leadership demand, analytical entrepreneurs / champions, other.. |  |
| EQ4 / Change 3 | What was the Fleming Fund (CG/RG/Fellows) contribution to those drivers? How vital was that it compared to the contribution of: Global Projects (name any active in country) Other influencing factors (could be government activities, interventions by other DPs or exogenous factors such as COVID-19)? |  |
| EQ4 / Change 3 | If there was no or negative change in this area, why was that? And what has the FF and others done to improve the situation? |  |
| POLICY 4.2 | Can you think of any other examples of relevant surveillance data being used to amend national strategy and/or inform decision-making’, apart from through data reports shared with AMRCC? If yes: Details? What data, in what form? Who are the decision-makers? One-off or routine? Current status? |  |
| 4.4 INTENDED USE | What do you think should be the future priorities for the Fleming Fund when supporting national AMR actions using surveillance data? PROBES: o Do you think that it will be more effective to foster local change (‘bottom up’) or to concentrate on motivating national initiatives (‘top down’) o Will the data show a need for action (‘push’) or will intended actions show what data is needed (‘pull’)? o What is more important, Infection Prevention & Control (IPC) or Antimicrobial Use controls (AMU)? o Why? What approaches would be required to address these priorities? |  |

Note that this was not an impact evaluation and results at this level were not expected to be achieved during phase 1 of the Fleming Fund.  See Annex  18 for the Fleming Fund portfolio-level Theory of Change and a description of expected impact and timeframes for achieving this.

Inception Report for the Independent Evaluation of the Fleming Fund Grants Programme – Vol I. and II. Itad (June 2018)

We have asked the MA what would be helpful for the evaluation to focus on and they have indicated that evaluation of the efficiency and effectiveness of the grant making process would be most useful in the first year.

Bangladesh, Bhutan, Indonesia, Nigeria, Senegal, Sierra Leone, Kenya, Vietnam, Nepal, Timor-Leste, Uganda, Ghana, Tanzania, Zambia, Pakistan and Laos.

Snowball sampling is an approach for identifying KIs.  The process begins by asking well situated people “Whom should I talk to?”  By asking a number of people who else to talk with, the snowball gets bigger and bigger as you accumulate new information on relevant KIs.  Patton M Q, (2002) Qualitative Research and Evaluation Options (3rd ed.) Thousand Oaks, California. Sage Publications

The literature often talks about reaching ‘analytic saturation point’ – the point during the analysis of the data where the same themes are recurring, and no new insights are given by additional sources of data.

One Health is the integrative effort of multiple disciplines working together locally, nationally and globally to attain optimal health for people, animals and the environment. https://www.avma.org/onehealth

Snowball sampling is an approach for identifying KIs. The process begins by asking well-situated people “Whom should I talk to?” By asking a number of people who else to talk with, the snowball gets bigger and bigger as you accumulate new information on relevant KIs. Patton M Q, (2002) Qualitative Research and Evaluation Options (3rd ed.) Thousand Oaks, California. Sage Publications

The literature often talks about reaching ‘analytic saturation point’ – the point during the analysis of the data where the same themes are recurring, and no new insights are given by additional sources of data.

Wave 1 (Q1 2022) Bangladesh, Bhutan, Indonesia, Nigeria, Senegal, Sierra Leone, Vietnam and Timor-Leste. Wave 2 (Q2 & 3 2022) Kenya, Nepal, Uganda, Ghana, Tanzania, Zambia, Pakistan and Laos.

Stern, E.; Stame, N.; Mayne, J.; Forss, K.; Davies, R.; Befani, B. (2012). DFID Working Paper 38. Broadening the range of designs and methods for impact evaluations. London: DFID. Available at: https://www.gov.uk/research-for-development-outputs/dfid-working-paper-38-broadening-the-range-of-designs-and-methods-for-impact-evaluations

OECD iLibrary. (2022). 4. Understanding the six criteria: Definitions, elements for analysis and key challenges. Retrieved from OECD iLibrary: https://www.oecd-ilibrary.org/sites/543e84ed-en/1/3/4/index.html?itemId=/content/publication/543e84ed-en&_csp_=535d2f2a848b7727d35502d7f36e4885&itemIGO=oecd&itemContentType=book#chapter-d1e2438

See for example Hassel, A., & Wegrich, K. (2022). How to Set the Agenda. In Hassel, Anke, and Kai Wegrich, 'How to Set the Agenda', How to Do Public Policy (Oxford, 2022; online edn, Oxford Academic, 21 Apr. 2022). Available at: https://doi.org/10.1093/oso/9780198747000.003.0003

Kingdon, J. (2010). Agendas, alternatives, and public policies, updated edition, with an epilogue on health care, 2nd edition. Boston: Pearson.

See for example Bailey, H. (2012). Stories of Change. IDS. https://opendocs.ids.ac.uk/opendocs/bitstream/handle/20.500.12413/7141/GOKH%20Stories%20of%20Change%20FINAL.pdf;sequence=1

See for example Wilson-Grau, R. (2018). Outcome Harvesting: Principles, Steps, and Evaluation Applications. IAP.

See for example Frid-Nielsen, S. S., Rubin, O., & Baekkeskov, E. (2019). The state of social science research on antimicrobial resistance. Social Science & Medicine (1982), 242, 112596. Available at: https://doi.org/10.1016/j.socscimed.2019.112596

DFID. (2011). DFID’s Approach to Value for Money (VfM). London: DFID. Available at: https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/49551/DFID-approach-value-money.pdf

Brown, C., & Shorten, T. (2021, 07 21). Common elements of good practice for sustainability. Retrieved from The Fleming Fund: https://www.flemingfund.org/publications/common-elements-of-good-practice-for-sustainability//

Government resources; Investments in infrastructure, equipment and consumables; Donor funding

Human resource (enough posts, supply); Human resources (training)

Staff are motivated to undertake functions, responsibilities/apply skills learned to maintain AMR surveillance beyond the end of 2022. Note that, to ensure consistency with MA tools, indications of political commitment should be reflected under motivation (this was previously linked to ‘resources’ in our data collection tools).

Snowball is an option for locating information rich KIs and critical cases. The process begins by asking well situated people “Whom should I talk to?” By asking a number of people who else to talk to, the snowball gets bigger and bigger as you accumulate new information-rich cases. Patton M Q, (2002) Qualitative Research and Evaluation Options (3rd ed.) Thousand Oaks, California. Sage Publications

The literature often talks about reaching ‘analytic saturation point’: this is the point during the analysis of the data where the same themes are recurring, and no new insights are given by additional sources of data.

Zambia, Ghana, Kenya, Laos, Nepal, Tanzania, Uganda, Vietnam, Nigeria, Bangladesh, Senegal, Timor-Leste, Pakistan, and Bhutan

OECD. (2010). Quality Standards for Development Evaluation. OECD DAC Evaluation Network

UK Evaluation Society. (2018). Guidelines for Good Practice in Evaluation. Hertfordshire: UK Evaluation Society.

Evaluation Association’s Competencies for International Development Evaluators.

Spencer L, Ritchie J, Lewis J and Dillon L (2003). Quality in Qualitative Evaluation: A framework for assessing research evidence. Government Chief Social Researcher’s Office. London: Cabinet Office

Stern, E.; Stame, N.; Mayne, J.; Forss, K.; Davies, R.; Befani, B. (2012). DFID Working Paper 38. Broadening the range of designs and methods for impact evaluations. London: DFID.

The Review on Antimicrobial Resistance. (2016). Tackling Drug-Resistant Infections Globally: final report and recommendations. London.

National Audit Office. (2022). Successful commissioning toolkit: Assessing value for money. Retrieved from National Audit Office: https://www.nao.org.uk/successful-commissioning/general-principles/value-for-money/assessing-value-for-money/

Source: MA 2nd  VfM Report.

Leveraged resources are those contributed by stakeholders including government and other institutions to implement programme activities. These include in-kind resources, such as consumables and meeting facilities, and cost-sharing.

Literature review of common approaches to VfM in fellowship schemes – Itad Fleming Fund Evaluation.

United Nations. (2010, April 21). Hanoi Declaration Sets Global Framework for Avian Influenza, Pandemic Readiness, Proposes National Steps to Detect Animal-Human Transmission, Control Outbreaks. Retrieved from United Nations Meetings Coverage and Press Releases: https://press.un.org/en/2010/sag433.doc.htm

The other three principles include: country ownership, alignment with other initiatives, and sustainability.

World Health Organisation. (2022). Strengthening WHO preparedness for and response to health emergencies: Strengthening collaboration on One Health. World Health Organisation.

World Health Organisation. (2022). Tripartite Zoonoses Guide: Operational tools and approaches for zoonotic diseases. Retrieved from World Health Organisation: https://www.who.int/initiatives/tripartite-zoonosis-guide

World Health Organisation. Regional Office for the Western Pacific. (2008). Zoonotic diseases: a guide to establishing collaboration between animal and human health sectors at the country level. WHO Regional Office for the Western Pacific.

Seale, A., Gordon, N., & Islam, J. e. (2017). AMR Surveillance in low and middle-income settings - A roadmap for participation in the Global Antimicrobial Surveillance System (GLASS). Wellcome Open Research, 2(92).

Abbas, S. S., Shorten, T., & Rushton, J. (2022). Meanings and mechanisms of One Health partnerships: insights from a critical review of literature on cross-government collaborations. Health Policy and Planning, 37(3), 385-399.

https://pubmed.ncbi.nlm.nih.gov/26604806/

Note that GARP report for Laos was unavailable but process appears to have been undertaken there: One Health Trust. (2022). GARP. Retrieved from One Health Trust: https://onehealthtrust.org/projects/global-antibiotic-resistance-partnership/

These key terms are explained in Vol. 1, Box 1. Patients tested is simply a count of the number of individuals from which samples were taken – recognising that multiple samples Box could be taken from one patient.

World Health Organisation. (2022). GLASS Resource Centre. Retrieved from World Health Organisation: https://www.who.int/initiatives/glass/resource-centre#glassreports

World Health Organisation. (2022). GLASS Resource Centre. Retrieved from World Health Organisation: https://www.who.int/initiatives/glass/resource-centre#glassreports

Point Prevalence Survey

https://doc.woah.org/dyn/portal/listalo.xhtml?page=listalo&req=162

When reporting to WOAH, countries can choose from three reporting options: Reporting Option 1: allows countries to distinguish quantities of antimicrobial agents by type of use (therapeutic or growth promotion);

Reporting Option 2: allows countries to distinguish quantities of antimicrobial agents by type of use and animal groups (food-producing terrestrial and aquatic species and companion animals); Reporting Option 3: allows countries to distinguish quantities of antimicrobial agents by type of use and routes of administration (distinguishing by group of animals is optional)

Note that we have not assessed the quality of the data itself.

In terms of the definition and total number of ‘Fleming Fund supported sites,’ it is important to note that this number may differ from the denominator in a given year KPI calculation because:

- Sites who are being supported but are supported for < 9 months are not included in the KPI calculation.

- Sites who are supported but are in the environmental or food sectors are not included in the KPI calculation.

- Sites reported as ‘supported’ in quarterly monitoring reports do not include sites where support is no longer active (i.e. where grants have stopped like in Ghana), i.e. data monitoring reports are a ‘snapshot’ in time versus the overall cumulative number.

Cairney, P., & Zahariadis, N. (2016). MSA: a flexible metaphor presents an opportunity to operationalise agenda-setting processes. In N. Zahariadis, Handbook of Public Policy Agenda Setting. Cheltenham, UK and Northampton, MA: Edward Elgar.

Jones, D. M., Peterson, H. L., Pierce, J. J., Herweg, N., Bernal, A., Lamberta Raney, H., & Zahariadis, N. (2015). A River Runs Through It: A Multiple Streams Meta-Review. Policy Studies Journal, 44(1), 13-36.

In some cases (e.g. laboratory capacities), this was not feasible within available resources. In many other cases (e.g. data generated, AMRCCs functioning etc) the baseline was zero. We discuss differences between MA and Itad reporting on ‘data sharing’ in Vol. I, section 2.2.6. The quality of the evaluation was not adversely affected by this approach, given the triangulation of reported data that was central to our analysis.

DFID. (2011). Withdrawn - DFID Ethics Principles for Research and Evaluation. Available at: https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/1034125/dfid-ethics-prcpls-rsrch-eval-withdrawn.pdf

Groves Williams, L. (2015). Review of Ethics Principles and Guidance in Evaluation and Research. Available at: https://www.oecd.org/dac/evaluation/DFID-Ethics-Principles-Report.pdf

https://www.gov.uk/government/publications/dfid-ethical-guidance-for-research-evaluation-and-monitoring-activities

The Fleming Fund started in 23 countries but subsequently pulled out of Sri Lanka and Myanmar decreasing the number of focus countries to 21.

For example, Itad produced a series of briefings on key questions in the Millennium Villages Project evaluation https://itad.com/knowledge-and-resources/mveval/

https://www.w3.org/WAI/WCAG21/quickref/

See for example Cooper, J. (2019, May 3). No time to wait: evaluating the fight against ‘Drugmageddon’. Retrieved from Itad: https://www.itad.com/article/no-time-to-wait-evaluating-the-fight-against-drugmageddon/

See One Health Commission. (2022). Resources / Services. Retrieved from One Health Commission: https://www.onehealthcommission.org/en/resources__services/

We note that DHSC is keen to explore the potential for more than one workshop at the Delivery Partners Event (DPE). Depending on how these are configured this may fall under phase 2 support. We remain open and ready for further discussion with the DHSC as plans for the DPE evolve.

https://www.flemingfund.org/wp-content/uploads/d681876608d2adac1c86cb67f1fa15fa.pdf

Contribution to drivers was rated against the following scale: Vital / Important / Some / Limited / None / Negative

We do note the potential role that the Tricycle protocol could play in providing a tried and tested model, but also that this was published in 2021, so not available for Fleming Fund use for the majority of phase 1. https://www.who.int/publications/i/item/who-integrated-global-surveillance-on-esbl-producing-e.-coli-using-a-one-health-approach

DFID. (2020). DFID's Approach to VfM - Guidance for External Partners. London.

ICAI. (2018). DFID's approach to VfM in programme and portfolio management: a performance review. London: ICAI.