Independent Evaluation of the Fleming Fund Grants Programme

Volume I: Summative Report

Date: 24 April 2024

Authors: Tim Shorten, Giada Tu Thanh, Ankur Gupta-Wright, Jennifer Armitage, Abbas Syed, Archie Drake and Paul Balogun

Submitted by Itad

Acknowledgements

This report has been authored by Tim Shorten (evaluation team leader), with important contributions from Giada Tu Thanh, Ankur Gupta-Wright, Jennifer Armitage, Abbas Syed, Archie Drake, Cheryl Brown, and Paul Balogun. Support from Itad was provided by Julie-Anne Darsley, Sarah Lamb, Jon Cooper and Tahmina Begum. Internal quality assurance was conducted by Jon Cooper, Paul Balogun and the Evaluation Expert Advisory Group.

Thanks are also due to the wider evaluation team as detailed in Annex 14 (Vol. II); Department of Health and Social Care Fleming Fund Project team, the Fleming Fund Management Agent team for extensive interactions during the course of data collection and consideration of the implications of the analysis, and to all who took part in our key informant interviews.

Disclaimer

The views expressed in this report are those of the evaluators. They do not represent those of the UK Department of Health and Social Care or of any of the individuals and organisations referred to in the report. ‘Itad’ and the tri-colour triangles icon are a registered trademark of ITAD Limited.

Contents

List of boxes	3

List of figures	3

List of tables	3

Acronyms and abbreviations	4

Executive summary	6

1	Introduction	16

1.1	What is the Fleming Fund	16

1.2	Key features of the MA approach	18

1.3	Context within which the Fleming Fund was implemented	25

1.4	Evaluation approach and methodology	26

1.5	Challenges and limitations	33

2	Findings	35

2.1	Strengthening systems to produce quality data on AMR	35

2.2	Results from the use of data	48

2.3	Findings on how the Fleming Fund has been designed and delivered	62

3	Conclusions	78

4	Recommendations	86

List of boxes

Box 1: Types of surveillance and data	20

Box 2: Country Grants, Fleming Fellows and Regional Grants	21

Box 3: Strategic focus for Fleming Fund phase 2	25

Box 4: Development and delivery of the Use and Influence Plan	32

Box 5: Example of surveillance capacities in Timor-Leste	37

Box 6: COVID-19’s effect on implementation	46

Box 7: One Health and AMR data use: the case for considering informal approaches	61

Box 8: Material differences between AH and HH sectors	66

Box 9: Use of automation to improve quality	68

Box 10: Examples of Fleming Fund efforts to strengthen sustainability	69

Box 11: DHSC systems for managing international ODA programmes	72

List of figures

Figure 1: Pillars or objectives of the Global Action Plan on AMR	16

Figure 2: Organogram of Fleming Fund workstreams (accurate in 2018)	17

Figure 3 Fleming Fund focus countries (Sierra Leone, Ghana, Senegal, Zambia, Tanzania, Kenya, Bhutan, Bangladesh, Indonesia, Laos, Pakistan, Nigeria, Uganda, Nepal, Timor-Leste, Vietnam, Myanmar, Zimbabwe, India, Sri Lanka, Malawi, Eswatini and Papua New Guinea)	18

Figure 4: Overview of how AMR testing works	19

Figure 5: Summary of types of grants to be available under the Fleming Fund (in 2018)	21

Figure 6: Summary of CGs implementation	23

Figure 7: Overview of evaluation approach	27

Figure 8: Six EQs or ‘agreed measures of success’	28

Figure 9: Overall evaluation workplan	30

Figure 10: EQs within the conceptual framework	31

Figure 11: What the Fleming Fund has delivered in phase 1	34

Figure 12: Number of Fleming Fund-supported HH surveillance sites showing progress through the LSHTM roadmap	38

Figure 13: Number of Fleming Fund-supported AH sites showing progress through the LSHTM roadmap	39

Figure 14: Heatmap of quality of human health and animal health data	41

Figure 15: Summary of examples of national action from evaluation focus countries and regions	52

Figure 16: Illustration that some national action in sample countries is based on non-surveillance data, particularly in AH	56

List of tables

Table 1: Targets from Fleming Fund phase 1 Implementation Plan	23

Table 2: Duration of Fleming Fund support	24

Table 3: Changes in quantity of HH AMR data	44

Table 4: Changes in quality of HH AMR data	45

Table 5: Summary of examples of national action from evaluation focus countries and regions	54

Table 6: Changes in data sharing with relevant committees	59

Table 7: Changes in data sharing with GLASS	62

Acronyms and abbreviations

AH	Animal Health

AMC	Antimicrobial Consumption

AMR	Antimicrobial Resistance

AMRCC	Antimicrobial Resistance Coordinating Committee

AMS	Antimicrobial Stewardship

AMU	Antimicrobial Use

ASLM	African Society for Laboratory Medicine

AST	Antimicrobial Susceptibility Testing

CAPTURA	Capturing Data on AMR Patterns and Trends in Use in Regions of Asia

CDC	US Centres for Disease Control

CG	Country Grant

CWPAMS 	The Commonwealth Partnerships for Antimicrobial Stewardship

DFAT	Australian Department of Foreign Affairs and Trade

DFID	Department for International Development

DHSC	Department of Health and Social Care

DP	Delivery Partner

EIC 	Early Investment Country

EQ	Evaluation Question

EQA	External Quality Assurance

FAO	Food and Agriculture Organization

FCDO	Foreign, Commonwealth and Development Office

FIND 	Foundation for Innovative New Diagnostics

GAP	Global Action Plan

GARP	Global Antibiotic Resistance Partnership

GLASS	Global Antimicrobial Resistance Surveillance System

HH	Human Health

HI	Host Institution

HMG	His Majesty’s Government

ICAI	Independent Commission for Aid Impact

IPC	Infection Prevention and Control

KI	Key Informant

KII	Key Informant Interview

KPI	Key Performance Indicator

LMICs	Low and Middle-Income Countries

LSHTM	The London School of Hygiene and Tropical Medicine

MA	Management Agent (Mott MacDonald)

MAAP	Mapping Antimicrobial Resistance and Antimicrobial Use Partnership

NAP	National Action Plan for AMR

NRL	National Reference Laboratory

ODA	Official Development Assistance

ODI	Overseas Development Institute

OECD	Organisation for Economic Co-operation and Development

PEA	Political Economy Analysis

QA	Quality Assurance

RADAAR	Regional Antimicrobial Resistance Data Analysis for Advocacy, Response

RG	Regional Grant

SOP	Standard Operating Procedure

ToC	Theory of Change

ToR	Terms of Reference

TrACSS	Global Database for Tracking AMR Country Self-Assessment Survey

UNEP	United Nations Environment Programme

USAID	United States Agency for International Development

VfM	Value for Money

WHO	World Health Organization

WHONET	Free software for management and analysis of microbiology laboratory (whonet.org)

WOAH	World Organisation for Animal Health (formerly OIE)

Executive summary

The O’Neill report estimated that by 2050, drug-resistant infections or antimicrobial resistance (AMR) could kill 10 million people per year at a potential cost of US$100 trillion in global economic output. In 2019, estimates suggested that globally 4.95 million deaths were associated with bacterial AMR, including the 1.27 million deaths directly attributable to such resistance.

The Fleming Fund was established in 2015 by the UK Government’s Department of Health and Social Care (DHSC) using Official Development Assistance (ODA) funding to tackle the threat of AMR in low and middle-income countries (LMICs) through a One Health approach. The initial phase, for £265 million, ran over a five-year period (2016–2021) and was extended to March 2023. With its focus on improving laboratory capacity and diagnosis as well as data and surveillance of AMR, it contributes directly to one of the five pillars in the 2015 Global Action Plan (GAP) on AMR. Significant impact to address AMR requires progress across all five pillars of the GAP and while the Fleming Fund’s contribution is necessary, it is not expected to be sufficient on its own. Ultimately, achieving the Fleming Fund’s intended impact relies on other actors too. At the country level, this depends on how well One Health AMR National Action Plans (NAPs) are implemented.

In 2016, the DHSC commissioned Itad to provide an independent evaluation function for the Fleming Fund grants programme. This is a summative report on what the Fleming Fund has achieved during its first phase, based on data collected up to July 2022. More detail on the methodology is included at the end of this executive summary.

How has the Fleming Fund been designed, and implications for the evaluation?

The Fleming Fund is delivered through grants to a range of partners across four workstreams (see Figure 2). Two workstreams aim to (a) focus international attention on the need for AMR surveillance; (b) develop and implement guidance and protocols for the standardised collection of data so it can be shared nationally and internationally; and c) support the development of One Health AMR NAPs. Much of this work has been delivered by The Food and Agriculture Organization of the United Nations (FAO), the World Organisation for Animal Health (WOAH) and the World Health Organization (WHO).

The other two workstreams aim to support the generation and analysis of data in a range of LMICs. For these workstreams, the DHSC contracted Mott MacDonald as the Fleming Fund Management Agent (MA). The MA designed a range of grants, based on detailed country needs assessments, to support country priorities for AMR, antimicrobial consumption/use (AMC/U) surveillance as set out in the AMR NAPs. The delivery of these grants was tendered by the MA using a competitive process. As of late 2022, grant support had been delivered in 23 focus countries. Across these focus countries, 81 grants delivered relevant outputs.

Key findings by evaluation question

Even in a challenging context, the Fleming Fund has delivered significant outputs to develop laboratory capacity and enhance surveillance systems across the 23 countries. These outputs have contributed to stronger laboratories and workforces to a varying degree across all of our focus countries. This first phase of Fleming Fund support aimed to build the foundations for AMR surveillance, which is an incremental process and takes time. Achieving strategic outcomes, such as significant use of AMR data and analysis to drive or inform anticipated policy, regulatory and behavioural change was expected to be the focus of subsequent phases of support.

We present below headline findings for each of our evaluation questions (EQs). These focus on the outcomes to which the Fleming Fund-supported capacity contributed, in terms of changes in quantity, quality and use of AMR surveillance data. When assessing results across these 23 countries, the following things are important to note:

There was substantial variation in the status of the laboratories that the Fleming Fund was due to support. For example, sites in some countries did not have reliable water and electricity supplies, which are fundamental for AMR testing whereas in some others laboratories were much more sophisticated (see  Annex 15, Table 47, for more on this variation).

Grant start dates were staggered across countries so that the duration and level of overall support from the Fleming Fund varied across countries.

The pace of implementing many grants was affected by COVID-19 restrictions.

The process of building a surveillance system is incremental and results, in terms of data generation, were not expected before 36 months’ support. By the end of June 2022, 16 of the 23 countries had received 36 or more months’ support, with another seven receiving between 24 and 36 months’ support.

This first phase of Fleming Fund support was mainly intended to build the foundations for AMR surveillance. Achievement of the Fleming Fund’s strategic outcomes, such as significant use of AMR data and analysis to drive or inform anticipated policy, regulatory and behavioural change was expected to be the focus of subsequent phases of support.

(EQ1) What has been the increase in the quantity and/or quality of data on AMR at country level and to what extent has the Fleming Fund contributed to this increase?

The MA achieved the stated aims for data generation as set out in the implementation plan, albeit the targets were neither ambitious nor sector specific. By mid-2022, there was evidence of increases in the quantity of human health (HH) AMR surveillance data in 11 out of 16 (69%) of our focus countries, although the extent of change varied; and of increases in quantity of other types of HH data beyond AMR. There was evidence of increases in the quantity of animal health (AH) AMR surveillance data in 12 out of 16 countries (75%), with the extent of change also varied.

Improvements in internal systems ensuring the quality of AMR testing were seen in HH and AH in a majority of countries, but progress was mixed. However, quality improvements have varied on a site-by-site basis, and it is not clear whether the MA’s aims have been consistently achieved (given the limited delineation of quality goals at the start of phase 1).

Major drivers of increases in quantity and quality were identified as: renovation of sites and provision of equipment, training of the laboratory workforce, supporting laboratory quality management systems, and AMR governance. Overall, the Fleming Fund has made a vital or important contribution to most key drivers of increased quantity and quality in both HH and AH AMR data, albeit to variable extents.

(EQ5) What has been the increase in quality of data shared and reported internationally and has the Fleming Fund contributed to this?

There is evidence of sharing at the international level, and emergent examples of use at the facility level. At the international level, for HH more AMR data has been made available, with the majority of evaluation focus countries (13/16) sharing data to the Global Antimicrobial Resistance Surveillance System (GLASS) since 2018 (of which seven had not previously done so) and a further four across other Fleming Fund countries. In the AH sector, more data on AMC/U has been reported to WOAH; by May 2022, 14 out of 16 of the evaluation focus countries (88%) reported to WOAH, with a reduction in the number reporting the most basic level of data and an increase in the number providing more sophisticated data.

(EQ4) Has, or is it likely that, the increase in AMR data influenced: (a) changes in national policies/regulations? and/or (b) changes in practice and attitudes in-country?

There are initial indications that data from AMR surveillance systems are starting to be collated and shared at the national level, but AMR data is not prominent in decisions on AMR action. Progress on the use of data has been slower and more difficult than anticipated in the Management Agent’s implementation plan, especially at national level. At the national level, data sharing with relevant committees is happening in six out of 16 focus countries. Even where AMR/C/U data is not yet being shared with relevant committees on a routine basis, some progress towards this goal has been realised in most countries. Despite progress on sharing, AMR surveillance data collated from laboratory antimicrobial susceptibility testing (AST) is yet to play a prominent role in relevant decision-making about action on AMR. Over half of the focus countries have nevertheless initiated significant policy and regulatory action on AMR at the national level since 2018.

At the local/facility level, there is emergent evidence that Fleming Fund interventions are stimulating positive changes to practices and attitudes as clinicians and other stakeholders start to interact differently with improved laboratories. However, these are not yet representative of wider system changes within countries.

The Fleming Fund has made very substantial contributions to the main drivers of data sharing at the national level. So far this has been primarily through Country Grants (CGs). It remains to be seen to what extent policy fellowships and other interventions focused on data use will contribute to the intended outcome-level results. The Fleming Fund has also contributed strongly to the drivers of data sharing at the international level, especially sharing with GLASS.

(EQ3) How likely are the Fleming Fund’s country-level results to be sustained?

Based on action to date and current country-level conditions, there are limited prospects for sustaining Fleming Fund results at present. This is linked to a lack of progress in establishing key conditions (resources, capacity, motivation, planning) as identified in published literature. The MA has been clear that prospects for achieving sustainability during phase 1 were limited given the starting points in most countries and limited implementation time of some grants (and this is backed up by broader evidence which underlines that sustainability is hard to achieve and takes time). The MA’s approach to sustainability has focused on (a) hardwiring sustainability prospects in grant design; (b) delivering success in Fleming Fund 1; and (c) increasing focus on sustainability in second CGs. The MA’s sustainability assessments indicate what will be ‘left behind’ but do not set out an explicit strategy or plan for achieving this. Overall this has limited the extent to which realistic expectations and plans have been established with DHSC or key country counterparts (although lack of clarity on future Fleming Fund funding hindered dialogue on sustainability). Sustainability is a shared responsibility between the DHSC, MA team and recipient governments.

(EQ2) To what extent have the Fleming Fund’s investments been aligned and coherent with other relevant investments at country level?

The model has created challenges in terms of delivering internal coherence between CGs, RGs and Fellowships, compounded by several design, management and contextual factors. Over the years, efforts have been made by the DHSC and the MA to increase coherence and coordination among the various partners and funding streams. However, the bases for true coordination and collaboration are still missing. This has likely led to some missed opportunities (in terms of linkages to other relevant agendas) and synergies, and increased transaction costs for country stakeholders.

The MA-managed Fleming Fund investments have generally been well aligned with national priorities. On some occasions, however, alignment with government systems and long-term needs could have been stronger. External coherence between all Fleming Fund grants and other delivery partners’ (DPs) interventions was found to be strong in a majority of the focus countries. External coherence and coordination is difficult to achieve, depending on many factors outside of the control of one programme and ultimately the responsibility of a strong AMRCC, although experience suggests this is not always a realistic assumption.

(EQ6) Did the Fleming Fund’s investments at country level offer value for money?

The Fleming Fund’s experience in delivering value for money (VfM) generally aligns with the Foreign, Commonwealth and Development Office (FCDO) and the Independent Commission for Aid Impact (ICAI) guidance. Overall, there are strong systems in place to manage economy and efficiency. However, the Fleming Fund has been weaker at establishing systems to manage for effectiveness. In spite of some existing and planned adaptations to strengthen this area (and the Fleming Fund experience is not uncommon compared with other equivalent programmes), this is a key strategic requirement for phase 2.

In narrow terms (economy, efficiency) there is evidence of VfM having been delivered. But in terms of effectiveness (as defined by Organisation for Economic Co-operation and Development (OECD)) the case is less clear. There is evidence of significant cost savings (economy) delivered by the MA, underpinned by strong systems to manage budgets and expenditures; performance is comparable to similar programmes. There is some evidence that the value of leveraged resources is reasonably significant in some grants . However, this indicator has not been reported or consistently tracked across all grants. The alignment between Fleming Fund expenditure, contribution and progress in generating quality AMR data is likely to be high, suggesting one positive outcome in terms of VfM.

Conclusions

The focus of phase 1 of the Fleming Fund was mainly to build the foundations for AMR surveillance. Achievement of the Fleming Fund’s strategic outcomes, such as significant use of AMR data and analysis to drive or inform anticipated policy, regulatory and behavioural change was expected to be the focus of subsequent phases of support. Our conclusions therefore significantly focus on the strengths and weaknesses of phase 1 in terms of maximising the contribution to the outcomes and what needs to change in phase 2.

Strengths and weaknesses of the current programme design in terms of supporting LMICs to develop and sustain national programmes for surveillance of AMR and antimicrobial use (AMU)

Progress towards strategic goals

Conclusion 1: During phase 1, the Fleming Fund has made significant progress in supporting countries to develop foundations for national AMR and AMU surveillance programmes. Laboratory functions have been strengthened compared to international norms, the capacities of key members of the laboratory workforce have been increased, and surveillance functions have been established in some countries. Broadly, within this narrow focus on building foundations, phase 1 has achieved what was agreed upon between the MA and the DHSC.

Conclusion 2: Building on these necessary foundations, it is reasonable to expect that the Fleming Fund will be able to make progress towards achieving its higher-level goals for phase 2 (in terms of the use of data for clinical improvement, policy and behaviour change), providing there is a stronger focus on understanding the needs and priorities of decision-makers. However, processes to achieve these goals are inherently political, complex, unpredictable and will take time to work through. In phase 1, the AMR NAPs developed by country governments neither identified prioritised outcomes nor provided a strong framework within which the Fleming Fund could easily engage with key national stakeholders. It cannot be assumed that this will change without support to strengthen NAPs and Antimicrobial Resistance Coordinating Committees (AMRCCs).

Observations on programme design

Conclusion 3: The programme has operated within a challenging context, which will continue into phase 2. However, the Fleming Fund has proven flexible enough to respond effectively, even though some features of the programme design made responding more challenging. Looking forward, the political and economic impacts of COVID-19 and other global factors are still emerging. These include economic disruption (global recession and inflation), supply chain issues, high LMIC indebtedness, high-income country budgetary issues, the impacts of climate and environment change, and the introduction of new technologies. A recent analysis by the World Bank suggests that per capita government health spending will decline annually in many LMICs, remaining lower than 2019 expenditures each year to 2027. The social environment for vaccines is also problematic, with the emergence of strong anti-vaccination movements (vaccines being a comparatively low-cost but effective response to AMR). All will generate significant headwinds for governments seeking to make rapid progress against AMR. The Fleming Fund made a range of changes in response to COVID-19, such as refocusing and extending grants. However, having key MA management and delivery capacity located in regional hubs rather than at the country level meant that it was not possible to implement important activities as originally planned.

Conclusion 4: The MA has successfully operationalised strong and effective procedures to manage economy and efficiency at the activity level. With further use of the laboratory capacity established during phase 1, the overall VfM of the programme will be enhanced. Delivering efficiently in this context has been challenging, and the operational model that has been chosen affects VfM in terms of internal and external coherence, as well as management overheads. It has also been challenging to track efficiency given the focus on reporting implementation rates and the lack of a link between financial reporting and outputs; this seems to be driven by systems and cultures within the DHSC. Notwithstanding these challenges, the evidence suggests the delivery of efficiency and economy. The fact that laboratory functions have been strengthened compared to international norms, and the capacities of key members of the laboratory workforce have been built up means that effectiveness has also been delivered, albeit limited to lower-level or intermediate outcomes at this stage. The effectiveness of outputs delivered under phase 1 will be highly contingent on the success of phase 2 when the priority shifts to the use of AMR evidence.

Conclusion 5: Experience from phase 1 suggests some specific areas in which the Fleming Fund can strengthen its approach through further reflection; in terms of using a stronger and prioritised sustainability lens from the start in deciding what support to provide to laboratories, working at the organisational level to sustain capacity-building results, focusing on other data types as well as AMR, and differentiating more strongly between support provided to AH and HH. Specific areas include:

Laboratory infrastructure enhancement. Specific choices about the nature of support provided and rationale for this, for example in terms of the sustainability implications of automating laboratory processes through the supply of sophisticated and expensive equipment, and the supply of consumables and reagents.

Human resource strengthening and workforce reforms. Working at the organisational/ institutional (rather than individual) level to strengthen the sustainability of capacity building (health workforce training) efforts.

Focus on AMC/U and other types of data. A central assumption of the Fleming Fund is that to ensure AMR is prioritised, key national and local stakeholders need to have evidence of both the trends of resistance and the impact that this is having on the health of their populations. However, since 2018, over half the focus countries have initiated important policy and regulatory action on AMR at the national level without using significant analysis from Fleming Fund investments. This experience suggests that change at country level can have other drivers and, if identified, presents a wider range of opportunities for the Fleming Fund to contribute to its higher-level objectives.

Give greater priority to sustainability from the start. While phase 2 appears set to address some of the challenges noted in section ‎2.3, the detail on how this will happen remains unclear to the evaluation team. Sustainability is a shared responsibility between the DHSC, the MA team and recipient governments. During phase 1, developing an approach to sustainability that might be effective has been constrained by a lack of consensus on what needs to be sustained. At the surveillance system level, the extent to which it is feasible and realistic to expect governments to allocate scarce domestic resources to AMR surveillance functions, particularly where the investment case is not clear, needs to be carefully considered, alongside the question of whether some aspects need to be funded as a global public good. Developing plans and strategies for sustainability should be done based on detailed, context-specific, politically informed analysis similar to that outlined in section 2.2 of the main body of the report.

Differentiation could be strengthened by giving more thought to the A–D categorisation (see Annex 15, Table 47) that the MA presented in phase 1 but which has not been central to targeting change.

Conclusion 6: The Fleming Fund deserves recognition for prioritising One Health and for convening cross-sectoral dialogues. The lack of models on how this can be operationalised at a national scale has impacted the design of the Fleming Fund’s One Health approach. Experience from the joint research aspects of the Fellowship programme, which echoes wider experience in One Health, may help identify informal mechanisms to replicate during phase 2. When the Fleming Fund started, it relied on limited practical guidance around how to successfully operationalise One Health in different country contexts. This is something that the international agencies have only now started to address, as demonstrated in the objectives of the recent World Health Assembly resolution on One Health and with the development of a more structured approach to implementing One Health. However, there are few examples of effective One Health approach implementation on a national scale. During this evaluation, we found that One Health partnerships can assume different forms across different countries, including varying levels of formality, and that formal and informal modes of partnerships often work together. Working with different degrees of formality/informality in One Health structures across Fleming Fund-supported countries is likely to be key during phase 2, and there is potential to draw on the Fleming Fellows’ joint research projects to learn lessons about supporting multisector collaboration.

Observations on programme management and implementation

Conclusion 7: During phase 1, planning by both the MA and DHSC was over-optimistic in terms of the time taken for design and approval and then delivery. It is not clear whether this has been fully addressed for phase 2. Implementation has not met expectations due to a range of factors (some of which were outside MA and the DHSC control) including: two civil service purdahs; delays in contracting the MA and sign-off on the MA’s implementation plan (which was extended from eight to 17 months); country positioning and competitive tendering taking longer than expected (including the approval of key documentation by DHSC) due to COVID-19, and due to the challenges of working in specific country contexts. The competitive tender process required by His Majesty’s Government (HMG) procurement rules was of limited relevance in the context of a highly technical intervention where the pool of qualified suppliers is small. CG implementation, therefore, began two years after the start of the programme, and the Fleming Fund has been catching up since. While these issues are well known by the MA and the DHSC, there is an understandable risk that ambition and realism are not well balanced in setting expectations for what can be delivered in phase 2.

Conclusion 8: The complexity of the programme, with multiple Fund grantees operating at the country level, has made it challenging to deliver coherence across the Fleming Fund’s investments. This has been exacerbated by the DHSC’s decision to expand the number of grantees. The challenge was recognised, and progress was made but focused mainly on avoiding duplication. Less progress has been made in enhancing synergy and greater overall effectiveness. Evidence of external coherence with external partners is strong within limits but reflects the lack of working formal government coordination mechanisms: ultimately, external coherence should be the remit of AMRCCs but these are not always fully functional and do not always include all relevant non-government stakeholders. Nevertheless, the basic mechanisms to deliver internal coordination are now in place, but their remit remains focused on information sharing. Therefore, widening their remit presents an opportunity to enhance internal coherence. While external coherence between all Fleming Fund grants and other DPs interventions was found to be strong in a majority of the focus countries, this does not focus on linkages to wider (non-surveillance) aspects of the AMR response. Progress on addressing external coherence may be key given the aspirations in phase 2 but the experience of phase 1 suggests that several of the contextual conditions that would have facilitated achieving external coherence (in terms of effective AMRCCs) are missing and a feasible solution has not been identified. The assumption is that AMR NAPs identify prioritised actions through a functional multisectoral coordinating mechanism (AMRCC) with clear terms of reference (ToR), a budget, and an accountability framework. The phase 1 experience is that AMR NAPs and AMRCCs have limitations in providing, organising, and driving the framework for action and external coordination. This links to the challenge of ensuring external coherence with other donors that our key informant interviews (KIIs) suggest are investing in the HH AMR sphere. Evidence suggests that, in the absence of prioritisation through AMRCCs, this coordination is happening to some degree in some countries, but ad hoc and based on existing relationships of grantees at the country level.

Strengths and weaknesses of the current programme design in terms of contributing to the overall longer-term objectives of the Fleming Fund as articulated in the Business Case for phase 2.

The previous conclusions include a number of strengths in the phase 1 approach that the Fleming Fund should build upon. Below we highlight a key conclusion that is critical for the Fleming Fund to address, given the evolving context and focus on contributing to the ultimate objectives of the Fleming Fund.

Conclusion 9: The Fleming Fund approach to managing for effectiveness could be strengthened at the country and portfolio levels. There has been progress in this regard during phase 1, in terms of developing a portfolio-level ToC and a core set of indicators; and the challenges observed reflect factors common in many aid programmes. But some are particular to the Fleming Fund and addressing these will be of increasing important in phase 2. The 2015 ICAI review of the UK’s former Department for International Development (DFID) approach to delivering impact notes that ‘…Getting the balance right between direct impact and policy and institutional change emerges as a critical factor for successful impact. It calls for clear, long-term goals, combined with considerable flexibility as to the steps required to achieve them’. This is true for the Fleming Fund which also faces programme delivery challenges. Managing for effectiveness requires both clarity of where the balance is to be struck, between impact at the individual facility level and the policy/ regulatory level, and flexibility through adaptive management that can achieve effectiveness.

The Fleming Fund did not start with clear and realistic goals on what could be achieved during phase 1. This is a common challenge. The lack of clarity on expected results may have been due to the innovative nature of the programme, or to the uncertainty of the purpose of the Fleming Fund at the outset. Either way, it has undermined the clarity of strategic focus and effectiveness of implementation in terms of higher-level outcomes during phase 1. As discussed above, fundamental questions about the purpose of the Fleming Fund should have been addressed upfront – such as whether national policy, regulatory and/or behaviour change (and of which target audiences) were the priority and how AMR surveillance was expected to contribute to that. We note that in the original ToR that the MA responded to, the DHSC prioritised generating additional data. Establishing clear, long-term goals and mechanisms to track and adapt the steps required to achieve them is standard practice in developing programmatic interventions of this kind, although not routinely implemented. There has been progress in this regard during phase 1, in terms of developing a portfolio-level ToC and a core set of indicators. Note the following, related to establishing clear expectations:

Establishing goals at a strategic level will help manage the risk of rigidly maintaining focus on operational plans at the cost of strategic adaptation. The extent to which DHSC systems and culture allow for this kind of adaptation needs careful consideration during phase 2.

Establishing expectations needs to be done with country counterparts. The country investment strategy process provides a good opportunity to do this. However, given expectations for how phase 2 will shift, there is a risk that country investment strategy processes are overloaded. In this scenario ‘delivering’ key strategic shifts will be more challenging and so the importance of establishing clear, shared expectations cannot be overstated.

Defining success for phase 2 in ambitious but realistic terms. This will be essential because phase 2 is short, and tackling AMR requires a long-term response. Experience from phase 1 provides a clear basis for calibrating ambition appropriately.

Recommendations

The recommendations presented below follow the findings and conclusions of the evaluation team, as set out in Annex 21. Under each, more detailed recommendations on their operationalisation can be found in section 4. They are of equal priority and should be implemented as a package for the best results.

1

Five recommendations:

The DHSC and the MA should ensure that clear, ambitious, realistic goals for phase 2 are in place from the outset, with targets to track progress. These should be established at the country and portfolio levels, based on understanding the current status of AMR surveillance systems and their use as developed during phase 1.

2 The DHSC and MA should ensure systems and processes for establishing expectations and tracking progress are proportionate, timely, and sufficiently flexible to deal with uncertainty and the need for strategic adaptation. These must strike the right balance between strategic reflection and accountability and avoid focusing too heavily on tracking the implementation of inputs and activities.

3 The process of establishing goals at the country level should be focused on understanding the priorities and needs of key decision-makers on AMR, recognising inter alia that: (a) AMR action will take place through multiple policy processes and that differentiation between HH and AH is of fundamental importance; (b) that achieving higher-level goals requires action by other actors and therefore effective collaboration with key stakeholder groups.

4 The Fleming Fund should make adaptations to or emphasise specific aspects of its technical approach for phase 2, that are supported by experience from phase 1. These should include focusing on AMU and other data sources, identifying informal approaches to One Health multisector collaboration, and maximising the prospects for sustaining laboratory functions.

5 The Fleming Fund should place greater emphasis on internal and external coherence and coordination from the outset of phase 2, including strengthening AMRCCs and NAPs to play this role and their linkages to institutional homes.

Evaluation scope and methodology

As noted above, the DHSC commissioned Itad in 2016 to provide an independent evaluation function for the Fleming Fund grants programme – focusing on workstreams 3 (portfolio of One Health country and regional projects) and 4 (Fleming Fellows) (see Figure 2). The evaluation has been undertaken by a multidisciplinary team as described in Vol. II, Annex 14 (Figure 26 and Table 46). As agreed, we have not evaluated the performance of individual grants within these two workstreams. Rather, the focus of the evaluation has been on how far the outputs of the grants developed and managed through the MA have, or are likely to have, contributed to the outcomes and impact identified by the DHSC.

Previous evaluation outputs were focused on and timed to ensure the utility of evaluation processes, e.g. through supporting adaptation by the Fleming Fund based on emerging evidence from implementation (see Vol. II, Annex 23 for summary examples of where this has happened). The purpose of this report is to provide an independent summative judgement of the Fleming Fund’s results for accountability purposes using six EQs(Figure 8) that reflect DHSC’s priorities. Our focus is on the country- as opposed to regional- or global-level results across the human, animal, and environment sectors. Our primary target audience is senior management within DHSC and His Majesty’s Treasury (HMT), as well as the MA and other donors and DPs.

The timing of the evaluation was set at the request of the DHSC, to maximise utility through feeding into detailed planning of the second phase of the Fleming Fund, starting in April 2023. One consequence was having a July 2022 data collection cut-off point, which was nine months before the end of phase 1 implementation. We recognise that further implementation and progress, not reflected in this report but in the MA’s reporting, is likely to have occurred following the completion of our data collection.

To address the EQs we have collected data in 16 case study countries, resulting in the review of more than 1,900 documents and the completion of more than 400 KIIs over the period September 2021 to July 2022. Grants included in our assessment as operating in our 16 sample countries are listed in Vol. II, Annex 25. We do not believe that evidence from the remaining seven countries would significantly alter our conclusions and recommendations. A range of analytical methods including contribution analysis, benchmarking against broader evidence and experience, and triangulation were used in analysing the evidence and developing our conclusions.

Introduction

This report provides a summative judgement on the results achieved by the Fleming Fund grants programme during its first phase of operation (phase 1); a second phase of the Fleming Fund, with £193.5 million investment over a three-year period (FY2023/24 to 2025/26) was approved in late 2021. The report has been produced by Itad, the independent evaluation supplier for the Fleming Fund. In this section, we provide an overview of the Fleming Fund (1.1) and the evaluation methodology (1.4). In section 2 we present findings for six evaluation questions (EQs) () that have framed the data collection and analysis, focused on three main areas of interest strengthening systems to produce quality data on antimicrobial resistance (AMR) (2.1), use of data for AMR surveillance (2.2) and findings on how the Fleming Fund has been designed and delivered (2.3). Based on these findings, we present conclusions and recommendations in sections 3 and 4 respectively.

What is the Fleming Fund

The UK Government established the Fleming Fund to the value of £265 million over an initial five-year period (2016/2017–2020/2021) to improve laboratory capacity and diagnosis, as well as data and surveillance of AMR in low and middle-income countries (LMICs) through a One Health approach. This includes building capacity to collect drug resistance data, enabling the sharing of drug resistance data locally, regionally and internationally, and collating data on AMR, and encouraging the application of this data to promote the rational use of antimicrobials.

Figure 1: Pillars or objectives of the Global Action Plan on AMR

The rationale for the Fleming Fund was clear. By 2050, drug-resistant infections could kill 10 million people per year at a potential cost of US$100 trillion in global economic output and with significant impact expected in LMICs. The Fleming Fund’s specific focus on surveillance was noted in key government documentation from 2015 onwards, and DHSC decided to focus on lack of data as a fundamental obstacle to understanding and making the case for action to tackle this ‘silent epidemic’. This was done in the context of the Global Action Plan (GAP) on AMR (2015) which includes knowledge and evidence through surveillance and research as one of five key pillars (Figure 1). Ultimately, achieving the impact that the Fleming Fund seeks to influence is linked to action in other pillars by other international, regional and country-level actors.

The Fleming Fund initially included five workstreams, including the independent evaluation as workstream 5 (Figure 2); as highlighted in section 1.2. Additional workstream(s) were added during phase 1. The entire programme was underpinned in phase 1 by a set of five core principles including Country Ownership, One Health, Alignment, Sustainability, and Value for Money.

Figure 2: Organogram of Fleming Fund workstreams (accurate in 2018)

DHSC contracted Mott MacDonald, as the Fleming Fund Management Agent (MA), to deliver a series of programme outputs under a portfolio of One Health Country and Regional Grants (workstream 3) and a Fleming Fellowship Scheme (workstream 4). Contractually, the MA was not accountable for associated programme outcomes, but for the financial, operation and technical management of the Fleming Fund Grants Programme from offices in London and four regional hubs in Bangkok, New Delhi, Kampala and Accra. A portfolio-level results framework and theory of change (ToC), with impact and outcome-level indicators, was neither set out at the start of the programme nor used to manage impact and outcome-level results. Given the principal aim of phase 1 was the generation of AMR data, in line with the GAP (Figure 1), direct population-level beneficiaries were not defined during this phase and no specific issues relating to poverty or equity (including gender and inclusion) were addressed either by the grants programme or by the evaluation.

Twenty-four countries in four regions (East and West Africa, South and South-East Asia) were initially selected for support, based on the criteria set out in the DHSC’s ToR and assessments of the capability, risks and context in each region and country carried out by the MA. Some focus countries changed during phase 1 as the feasibility of working in certain countries came into question. A total of 23 countries received some form of support during phase 1 (see Vol. II, Annex 25 for overview) although activity was stopped in Sri Lanka and Myanmar due to changes in each country context that prevented implementation as planned, decreasing the final number of countries to 21. Each country had different starting points in terms of what surveillance systems were already in place, as reflected in their assignment by the MA to one of four broad categories (see Vol. II, Annex 15, Table 47). 65% (15/23) of the countries selected were in category B. In these countries, there was an AMR NAP in place and the MA believed, based on a review of desk material and key informants’ views, that there was political will to move on the AMR surveillance agenda. However, while aspects of a basic surveillance system were in place in these countries, an operational surveillance system was not.

Figure 3 Fleming Fund focus countries (Sierra Leone, Ghana, Senegal, Zambia, Tanzania, Kenya, Bhutan, Bangladesh, Indonesia, Laos, Pakistan, Nigeria, Uganda, Nepal, Timor-Leste, Vietnam, Myanmar, Zimbabwe, India, Sri Lanka, Malawi, Eswatini and Papua New Guinea)

Key features of the MA approach

What is required to produce quality data on AMR?

The development of AMR surveillance is a highly technical process that relies on establishing specific capabilities and processes to ensure that laboratory testing of samples for AMR is done in a standardised way. As described in The London School of Hygiene and Tropical Medicine (LSHTM) roadmap, which has provided a key framing for the Fleming Fund during phase 1, processes need to be quality assured for data reported locally, nationally, or internationally (to GLASS) to be of use. The scope and direction of the surveillance system should be guided by relevant surveillance strategies and governance mechanisms, such as AMR NAPs, Antimicrobial Resistance Coordinating Committees (AMRCCs), and associated technical working groups. These should specify which organisms are the focus of surveillance efforts, which sites will provide AMR testing (i.e. surveillance sites) and more sophisticated confirmatory testing and support (reference laboratories), how data will be managed, analysed and reported, and the mechanisms through which these analyses can feed into decision-making at national, sub-national and facility level (recognising that ultimately, practitioners and patients demand AMR testing services, without which AMR surveillance cannot play the role it is required to play). Figure 4 provides a high-level summary of how AMR testing works, to assist with the interpretation of the findings in this report.

Figure 4: Overview of how AMR testing works

The goals, structures and requirements of national AMR surveillance systems are highly varied and dependent on a range of contextual factors (political, economic, cultural and historic). Variation also exists between sectors. HH primarily uses passive surveillance, whereas AH primarily uses active surveillance. These differences reflect that the priority bacteria in animals are commensal so do not necessarily cause illness, and farmers rarely bring sick animals to a facility (as in passive surveillance), hence the need for active surveillance in AH. See Box 1 for more on this.

National AMR surveillance is one type of data, among others, which policymakers can use to make decisions on changes to regulation, policies, resource allocation, behaviour change campaigns, etc. to tackle AMR. Surveillance data is useful for the planning, implementation and evaluation of public health practice. Other types and sources of data can be useful depending on the needs and objectives of decisions makers (see Box 1). For example, AMC/U is useful for understanding the availability and use of antibiotics. Economic data is important to contextualise. Research data can be easier and cheaper to obtain but is often less representative, systematic, and sustainable. As discussed in section 2.2, AMR-relevant action does not always necessarily rely on the availability of AMR surveillance data.

Box 1: Types of surveillance and data

- Surveillance (in public health context): This is the continuous, systematic collection, analysis and interpretation of health-related data for the planning, implementation and evaluation of public health practice (WHO).

- Passive surveillance: This is the AMR data based on patients (or animals) presenting to healthcare providers and where microbiological samples have been taken as part of routine care. This is the main focus of Fleming Fund support in the HH sector.

- Active surveillance: This is AMR data based on the sampling of populations (human or animal), not dependent upon their presentation to healthcare providers or routine medical care. It is the main focus of Fleming Fund support in the AH sector – initially focused on collecting samples from poultry production systems.

Example of a ‘good’ AMR surveillance system in HH:

- A good AMR surveillance system would collect data from healthcare providers on a range of key syndromic infection diagnoses (e.g. ‘sepsis’, urinary tract infections, sexually transmitted infections), including clinical, demographic and laboratory data which would be linked using anonymised alphanumeric IDs. AMR data would include all key antibiotics for priority pathogens.

- Laboratory AMR data would be quality assured, with AST performed according to standard operating procedures (SOPs) based on internationally accepted standards. Procedures and reagents would be quality assured, and the laboratory would participate in an external quality assurance programme.

- Patient results would be efficiently fed back to clinicians to inform patient care, while laboratory or health facility-level data will be collated, cleaned, duplicates removed, and analysed/summarised to inform local policies and guidelines. The key AMR metrics presented would include the number of samples, the proportion that was positive, and the proportion of each pathogen that has resistance to various antibiotics, linked to demographic data (e.g. age and sex) as well as clinical data (e.g. source of infection, clinical syndrome and diagnosis). Some general site-level data (e.g. episodes of care) would also be available for context. The data would be collated nationally and aggregated for reporting to GLASS.

- AMU data will be collected using point prevalence surveys of antimicrobial prescriptions of key clinical syndromes at repeated intervals and inform policy and guidelines.

Data types:

- Sample (or specimen): blood, bodily fluid, or tissue is taken from an individual patient or animal for diagnostic testing.

- Culture: a sample or specimen, if meeting quality criteria, will be processed and placed in appropriate media to allow microbial growth. A single specimen may be processed for one or more cultures.

- Isolate: a bacteriological strain (i.e. a microbe) identified from a culture of a sample. There may be more than one isolate identified from a single culture or sample.

Antimicrobial susceptibility testing: once an isolate has been identified, AST is performed to identify if the isolate is resistant to any antibiotics (i.e. if AMR is present). Commonly, multiple AST is performed on a single isolate, although the exact number and combinations of antibiotics tested for resistance will depend on the organism and setting.

How does the MA’s approach address these requirements?

In this section we describe the approach taken to deliver Fleming Fund support under workstreams 3 and 4 as shown in Figure 2 above.

Fleming Fund country-level support was designed (from 2018) to respond to different needs and contexts through a mixture of different grants, including those designed and tendered by the MA using a competitive process based on detailed country needs assessments. Figure 5 below sets out the six types of grant that were administered and managed by the MA, with most support delivered through the CGs and RGs and the Fleming Fellowship Scheme (Box 2). Competitive tendering was stipulated by the DHSC in line with cabinet office guidelines and standards for grant programmes, as well as general HMG’s public procurement best practice, to ensure transparent tendering, and deliver VfM in procuring services. Requirements for each CG tender were identified through a detailed needs and capability assessment in each country. These assessments were intended to support alignment with country priorities for AMR/C/U surveillance as set out in the AMR NAPs which were often unclear on key goals or aspects of the surveillance system.

Fleming Fund support was expected to fall within five pre-defined parameters of support, or areas of investment, designed to put in place the building blocks for sustainable development:

Laboratory infrastructure enhancement.

Human resource strengthening and workforce reforms.

Surveillance systems strengthening.

Building foundations for AMR surveillance data use.

Rational use of antimicrobial medicines.

Figure 5: Summary of types of grants to be available under the Fleming Fund (in 2018)

Box 2: Country Grants, Fleming Fellows and Regional Grants

- CGs are designed to improve the collection and use of AMR data, including AMU, in target countries using a One Health approach. Each CG was implemented by a grantee selected through a competitive tendering process, managed by MA regional teams. Initially, CGs were intended to be split into a shorter (12–18 months) CG1 with a smaller budget, and a longer (24–40 months) CG2s with a bigger budget. CG1s were broadly intended to focus on input and process activities in order to be in a position to generate the outputs of quality-assured AMR and AMU surveillance data over 36–48 months, including through CG2s. In practice CG2s, were only implemented in 10 of our 16 focus countries; in some cases, this was due to CG1s being extended, and we note that fewer CG2s do not necessarily imply reduced funding overall.

- Fleming Fellows. The MA’s implementation plan describes the objectives of the Fleming Fellowship Scheme in terms of enhancing investments made through CGs and RGs for the improved surveillance of AMR and AMU, supporting the professional development of key practitioners and changemakers, through participation in One Health communities of practice that contribute to the global dialogue on combatting resistance. Three types of fellowships were offered to focus on (1) AMR testing in laboratories; (2) AMR surveillance; and (3) the use of AMR data for policy change. Host Institutions (HIs) provide long-term mentorship and career enhancement for four to eight Fellows per country, with an initial focus on microbiology and epidemiology on relevant technical capabilities. The scheme was managed by the MA’s team in London, with support from Fellowship officers in each regional office. More detail on Fellows implementation can be found in sections 2.1. 2.2 and 2.3.

- Regional Grants (RGs) were designed to support regional One Health approaches to the improved surveillance of AMR. A first round of RGs focused on the retrospective collection of data. Round two focused on a range of thematic issues including external quality assurance (EQA), common protocols, specialised training in epidemiology and microbiology, the use of data for policy, barriers to procurement, and whole genome sequencing. The RGs were managed by the MA’s team in London. The contribution of RGs was not simple to identify at the country level, partly due to the short (about two years) duration of RGs – there has been limited time to demonstrate progress at the country level; and to the timing of our data collection, e.g. it is clear that work undertaken through the Capturing Data on AMR Patterns and Trends in Use in Regions of Asia (CAPTURA) and MAAP RGs has potential for use by policymakers at the country level. However, final country-specific reports from both grants were still being finalised which likely constrained informants’ ability to refer to this work.

- Strategic alignment grants: the strategic alignment grants are intended to provide synergistic funding which furthers the objectives of the Fleming Fund in producing high-quality data; and to interact and collaborate with other funding partners to enhance investments in AMR surveillance and control. Three grants started implementation in late 2021/early 2022: (1) to support countries’ use of WHONET software to manage laboratory microbiology data and analysis; (2) to support the Foundation for Innovative New Diagnostics (FIND) to enhance common quality approaches to laboratory quality management systems; and (3) to support the Commonwealth Pharmaceutical Association to provide assistance with AMU surveillance and use of surveillance data to improve antimicrobial prescribing. Given the recent start of these grants, limited evidence on their contribution is available by the data collection cut-off in mid-2022.

Implementation of the CGs and Fleming Fellowships portfolio was designed to be staggered, with some countries receiving less support than others by the end of phase 1. RGs were managed separately from CGs, intended to be implemented separately (with no co-dependencies), and not staggered to the same extent. The duration of CGs differed across countries, with the maximum time available about 48 months in early investment countries . An overview of CG implementation is set out in Figure 6. A similar implementation was planned for Fleming Fellowships; RGs were commissioned in two rounds (Box 2), with challenges experienced in placing second-round RGs due to the timing of tenders and availability of qualified suppliers to deliver the specialised requirements.

Figure 6: Summary of CGs implementation

The phase 1 implementation plan noted that the process of building a surveillance system is incremental, and data generation results were not expected before 36 months of support. The initial 24 months of a typical Fleming Fund CG were expected ‘to focus on input and process activities (e.g. building systems) in order to be in a position to generate the outputs of quality-assured AMR and AMU surveillance data over 36–48 months’. Expectations for what would be achieved within phase 1 are set out in Table 1. Further stratification of expected results was made using the A-D categorisation described above.

Table 1: Targets from Fleming Fund phase 1 Implementation Plan

| Fleming Fund Grants ​ Programme Length ​ | Input phase​ Capacity building and establishment of systems​ |  | Output phase​ Quality-assured data starts to flow​ |  |
| --- | --- | --- | --- | --- |
|  | 12 months​ | 24 months​ | 36 months​ | 48 months​ |
| Number of countries with active grants​ | 12​ | 24​ | 24​ | 24​ |
| Primary data generated and used for policy and improving guidelines​ | 3​ | 8​ | 16​ | 18​ |
| Number of countries where primary data is generated and shared internationally​ | 2​ | 4​ | 8​ | 12​ |
| Number of countries with active surveillance of AMU in health and agriculture sectors​ | 4​ | 12​ | 18​ | 20​ |

In practice, less than half of the 23 Fleming Fund countries had received 36 months or more support through CGs by June 2022, which was less than originally expected, due to a range of factors that were not necessarily within the control of the DHSC and MA teams. Table 2 summarises the duration of support received by Fleming Fund countries, which shows that less than half (10/23) had received at least 36 months’ support by June 2022. This is substantially less than the originally planned 16, even with the 15-month extension. Programme progress was more limited than expected due to a range of factors (some of which were outside MA and DHSC control). There were two civil service purdahs, delays in contracting the MA (partly due to the length of negotiations between the DHSC and the MA during the inception phase), and a delay in sign-off on the MA’s implementation plan (which was extended from 8 to 17 months) due to country positioning and competitive tendering taking longer than expected (including in the approval of key documentation by the DHSC). Two other factors were COVID-19, and the challenges of working in specific country contexts. CG implementation, therefore, began two years after the start of the programme, and the Fleming Fund has been trying to catch up from that point onwards. However, the experience provides important learning – in terms of setting realistic expectations for planning, MA capacity to deliver grant sequencing as initially planned, and DHSC oversight of MA implementation – which needs to be captured in the design and expectations for phase 2 if similar delays are to be avoided. This is discussed more in section 2.3 and Box 3 (below).

Table 2: Duration of Fleming Fund support

| Duration of Fleming Fund support | Planned (in IP) | # Countries in June ’22 | Countries (Jun ’22) | # Countries in Dec ’22 | Countries (Dec ’22) |
| --- | --- | --- | --- | --- | --- |
| 13–24 months implementation | 0 | 3 | India, Senegal, Sierra Leone* | 1 | India |
| 25–35 months implementation | 8 | 10 | Bangladesh, Eswatini, Indonesia, Kenya, Malawi, Myanmar, PNG, Sri Lanka, Zambia, Zimbabwe | 5 | Eswatini, Malawi, Senegal, Sierra Leone, Zimbabwe |
| 36–47 months implementation | 12 | 10 | Bhutan, Ghana, Laos, Nepal, Nigeria, Pakistan, Tanzania, Timor-Leste, Uganda, Vietnam | 14 | Bangladesh, Bhutan, Indonesia, Kenya, Laos, Myanmar, Nigeria, Pakistan, PNG, Sri Lanka, Tanzania, Timor-Leste, Vietnam, Zambia. |
| 48+ months implementation | 4 | 0 |  | 3 | Ghana, Nepal, Uganda |

* Countries highlighted in bold were focus countries for the evaluation.

Consequently, it was always clear to DHSC that the achievement of strategic outcomes during phase 1 would be varied at best (in particular in relation to generation of AMR data) and limited in terms of sharing and use of AMR data for policy, regulation and behaviour change. Given the starting point of AMR surveillance systems in most countries it was unrealistic to expect to see use of AMR surveillance data for policy, regulation and behaviour change within five years; nor was the programme expected to or set up to achieve this. During phase 1, the DHSC articulated a portfolio-level ToC in mid-2019, which sets a time frame of 10–30 years for achieving an impact on reducing AMR (Vol. II, Annex 18). Phase 1 was intended to establish the foundations for data generation and evidence for action.

This was compounded by the major assumption that NAPs were an effective vehicle for broader implementation. Figure 1 above underlines that achieving progress on AMR requires action across the five objectives of the Global Action Plan, of which AMR surveillance (knowledge and evidence) is one. As discussed in section 2.2, the lack of NAP implementation in most countries has undermined the prospects for surveillance data sharing to lead to national actions on AMR. Fleming Fund has invested in the surveillance aspects of NAPs, but other important pillars have remained unfunded/underinvested. These shortfalls have exacerbated Fleming Fund sustainability and VfM challenges over the longer term.

The Fleming Fund has also learned and adapted substantially during phase 1 to respond to emerging implementation (albeit with scope for further changes, as discussed in section 2). The anticipated first and second CGs were not implemented in all countries; many/all CGs were subject to (multiple) extensions, whether on a no-cost or costed basis; Fleming Policy Fellows were established in 14 countries with limited time to deliver. The DHSC also introduced a series of direct grants (e.g. to support the Commonwealth Partnership for Antimicrobial Stewardship (CWPAMS), to FIND, and the South Centre) during 2018/19, which served to complicate an already confusing delivery model. The DHSC and MA teams have also placed increasing emphasis on specific themes, including use at the clinical level and the quality of microbiology processes.

Context within which the Fleming Fund was implemented

As noted above, major contextual factors have influenced the Fleming Fund phase 1 implementation.

COVID-19 had a major impact on the Fleming Fund in terms of implementation at the country level. As can be seen in Figure 6, the majority of grants were starting to come onstream in late 2019. The COVID-19 global pandemic was announced in March 2020, with significant implications for the MA’s ability to implement the grants programme as intended. A major constraint was the MA regional teams’ inability to travel for discussions with country counterparts (country grantees and stakeholders responsible for AMR surveillance), affecting regional teams’ ability to provide oversight and take new initiatives (such as CG2s) forward. Fleming Fellows Host Institutions (HI)s and other RGs experienced similar travel constraints and consequently had to rework business processes (e.g. virtual meetings, virtual training) which took time to implement and came with pros and cons. Fleming Fund procurement was delayed in many instances. Country counterparts’ – especially Fleming Fellows and other laboratory staff – ability to focus on AMR surveillance in the face of the pandemic was also affected, as discussed in sections 2.1, 2.2 and 2.3.

Box 3: Strategic focus for Fleming Fund phase 2

A second phase of the Fleming Fund, worth up to £193.5 million over three years (FY2022/23 to FY2024/25) has been approved. There is a high degree of continuity in the Fleming Fund’s purpose and focus activities for phase 2 – i.e. continued investment in AMR surveillance systems in order to consolidate gains made during phase 1.

A number of strategic and programmatic shifts have also been defined for phase 2, to maximise the effectiveness and value of Fleming Fund investments in the following areas: (1) Data use and clinical engagement; (2) The Economic Case for AMR; (3) Regional Animal Health Approach; (4) One Health Environment; and (5) Substandard and falsified medicines. Gender and Equity has also been added as an underpinning principle.

Important adaptations to Fleming Fund processes have also been proposed – in particular the introduction of country investment strategies which will establish agreed country-specific goals, as the basis for stronger coordination with country partners and review of expected results and the Fleming Fund’s contribution to these.

Responding to COVID-19 also created additional transaction costs for the DHSC and the MA, as well as financial uncertainty for the Fleming Fund which impacted on planned delivery. The UK government’s response to the challenges brought about by COVID-19 included a temporary reduction in its commitment to Official Development Assistance (ODA), from 0.7% to 0.5% gross national income. This initiated a series of cuts to existing UK aid programmes, and the MA had to reduce budgets for existing grants by up to 30% during 2021/22. This was time-consuming, diverting attention from grant implementation, and limited the extent to which original plans could be implemented. Financial uncertainty continued through this period with several spending reviews either completed, postponed or positioned as one-year extensions instead of the usual three-year cycle. This affected the extent to which the Fleming Fund and MA were able to make medium-term plans, including on sustainability (as discussed in section 2.3).

At the same time, AMR has continued to feature prominently on the global agenda, receiving support within HMG and from country governments, and creating opportunities for the Fleming Fund to build on. Building on the 2015 AMR GAP and United Nations General Assembly political declaration (2016), the World Health Organization (WHO) subsequently declared AMR as one of the top 10 global public health threats facing humanity, the tripartite has continued to work to promote action on AMR – including through establishing the Multi-Partner Trust Fund, establishing the global leaders’ group, and incorporating United Nations Environment Programme (UNEP) to become the ‘quadripartite’. COVID-19 has created a clear and pressing case for investment in AMR-relevant capabilities under the framework of global health security. As noted above, a second phase of funding for the Fleming Fund was approved in late 2021.

Evaluation approach and methodology

Figure 7: Overview of evaluation approach

In 2016, during the design phase of the Fleming Fund, the DHSC commissioned Itad to work alongside its portfolio of country and regional projects and undertake an independent evaluation of the Fleming Fund grants programme (workstream 5 – Figure 2). As shown in the overview diagram below, the primary objective of the evaluation was to establish how far the outputs of the portfolio of CGs and RGs, and the Fleming Fellowships have contributed to the outcomes identified by the DHSC. As such, the results from workstreams 3 and 4 in the overall Fleming Fund (Figure 2) are within scope; outputs from workstreams 1 and 2 are out of scope and not directly evaluated, except to the extent that they are identified as contributing to changes in quantity and quality of data generated and of shared nationally and internationally in our sample countries. The geographical scope of the evaluation is the 23 focus countries where the MA implemented grants (see below for more on the country sample that the evaluation looked at), and the temporal scope is the entirety of phase 1 (from 2016/17 to March 2023).

Over the six years of its implementation, the evaluation has fulfilled both learning and accountability objectives. The evaluation has fulfilled its learning objectives (see Figure 7) through producing three unpublished formative deliverables (2018, 2020, 2021), which identified:

- instances of good practice to inform course correction and adaptation (see Vol. II, Annex 23).

- challenges to the achievement of the Fleming Fund’s objectives under workstreams 3 and 4 (Figure 2).

In 2021, the evaluation outputs were used to inform the decision by the DHSC and His Majesty’s Treasury (HMT) on whether to fund another phase of work under the Fleming Fund and how the approach might be strengthened based on experience to date.

In 2021, after the delivery of its third formative deliverable in January, the evaluation focus shifted to provide an independent summative judgement of the Fleming Fund’s results and achievements for accountability purposes. The timing of the summative phase of the evaluation was set at the request of DHSC, to maximise utility through feeding into detailed planning of the second phase of the Fleming Fund, starting in April 2023.

The entire evaluation has been guided by six EQs (or ‘agreed measures of success’) which reflect the priorities of both Ministers and the Chief Medical Officer within the DHSC (see Figure 8 below). EQs are focused on whether Fleming Fund outputs contribute to outcomes of interest to the DHSC in terms of the use of AMR surveillance data for policy, regulation and behaviour change at the national and international level. At the level of inputs and outputs, the Fleming Fund has delivered a substantial amount of renovation, procurement, training, and technical assistance. These activities have contributed to strengthening laboratory capacity and workforce to a varying degree across all of our sample countries (see Figure 10).

Figure 8: Six EQs or ‘agreed measures of success’

To address these EQs, we have collected data in 16 case study countries (out of the 23 where Fleming Fund has implemented activities during phase 1) selected to maximise the extent of implementation evidence. As described in section 1.3, the duration of CGs varied according to a programme of staggered start dates. Our data collection sample included countries that were due, at the time of finalising our inception report in mid-2018, to receive at least six months’ support under second CGs (as described in section 1.2). Therefore, those countries had the greatest prospect of substantive results and were the countries that were most relevant to answering our EQs.

In each country we conducted three separate rounds of KIIs, each corresponding to a specific evaluation deliverable (see Figure 9 below); we also visited a number of surveillance sites. Data collection used standard interviewing techniques for qualitative work and standardised data collection ana analysis tools (to facilitate cross-country analysis). Key informants (KIs) and surveillance sites were purposively sampled in each country, starting with a list of KIs/sites agreed with the MA on the basis of our document review, the categories of KIs relevant for each round based on our information needs and KIs interviewed in previous rounds for round 2 and 3. For KIIs, we then applied snowballing once KIIs started by including additional KIs suggested by other KIs when deemed relevant. Technically, we looked to stop interviewing people when we reached analytical saturation; however, in reality we snowballed to the degree possible within the available time and resources. For more details on sampling see Vol. II, Annex 3, Table 2. For sites, our objective was to generate a more granular understanding of how Fleming Fund support worked in practice, albeit on an illustrative rather than representative basis (see Annex 3, Table 2 for more details).

|  | 2018 |  |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Data collection & analysis | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Round 1 (formative) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Country visits | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analysis & reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deliverable 1 submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Round 2 (formative) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Country visits |  |  |  |  |  | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analysis & reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deliverable 2 submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Revision due to COVID-19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Remote data collection |  |  |  |  |  |  |  | 2 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| Analysis & reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deliverable 3 submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Round 3 (summative) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Country visits & global KIIs |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3 | 3 |  |  |  |  |  |  |
| Analysis & reporting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deliverable 4 submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Revisions & dissemination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Key |  |
| --- | --- |
| Round 1 |  |
| Round 2 |  |
| Round 3 |  |
| Country visits |  |

Figure 9: Overall evaluation workplan

Our overall evaluation framework is reflected in Figure 7. It shows an evaluation of Fleming Fund outcomes and performance, designed to explore agreed EQs using a range of data sources and analytical methods to answer each EQ. Our overall approach is case based (focusing on 16 sample countries), using mixed methods and some elements of theory-based evaluation (see below). Our primary analytical methods are contribution analysis and thematic/sectoral analysis, complemented with aspects of process, synthesis, and value for money (VfM) evaluation techniques. We have applied these to support adaptive management at the portfolio level within the Fleming Fund. Our evaluation approach is described and justified in more detail in Vol. II, Annex 3. The specific application of methods and data sources to each EQ is set out in an evaluation matrix in Vol. II, Annex 2. Challenges and limitations are summarised in section 1.5 and in Vol. II, Annex 13 with mitigating strategies.

It is not a theory-based evaluation as such, but we supported the DHSC in early 2019 to articulate a portfolio-level ToC as set out in Vol. II, Annex 18, which has informed our data collection and analysis.

Our framework also highlights the evaluation’s twin objectives around learning and accountability, as described above; and our commitment to the utility of evaluation products and processes (Vol. II, Annex 17). We note that this report was not expected to draw out lessons learned.

Figure 10: EQs within the conceptual framework

Our focus is on the country as opposed to regional or global-level changes at three distinct levels across the human, animal and environment sectors:

At the level of the surveillance system (EQ2, EQ3 and EQ6), to see if changes are sustainable and have been delivered with economy, efficiency and effectiveness – including the extent to which interventions are aligned with the work of others (section ‎2.3 and Vol. II, Annex 6).

At the level of availability of more and better data (section ‎2.1), where our focus is on what has been the increase in the quantity and/or quality of data on AMR at the country level and to what extent has the Fleming Fund contributed to this increase (EQ1).

At the outcome level – whether the availability of more and better data leads to a significant change in the country or the availability of more and better data internationally (EQ2, EQ3, EQ4, EQ5 and EQ6) (section 2.2).

The Fleming Fund has adopted a One Health approach to improving the capacity of LMICs to collect data, and enable its sharing, collation and use to encourage the appropriate use of antibiotics. As such, the evaluation has primarily focused on HH and AH surveillance systems. The broader international context within which the Fleming Fund was implemented was considered, when relevant, in the country-specific analyses undertaken by the evaluation team – where the main implications were in terms of support from other donors (albeit limited) and the role of regional and global-level actors such as the tripartite (WHO, FAO and WOAH).

The evaluation has been conducted by a multidisciplinary evaluation team over the period 2018–2022; however, the data collection and analysis for this summative report started in September 2021 and concluded in July 2022. The evaluation has been undertaken by a multidisciplinary team as described in Vol. II, Annex 14. Tools were piloted in two of our 16 focus countries (Zambia and Pakistan) and revisions were made to rationalise and ensure that they are fit for purpose. The evaluation was conducted to ensure ethical and safeguarding principles were adhered to; our approach was informed by FCDO Ethical Guidance for Research, Evaluation and Monitoring Activities as set out in Vol. II, Annex 12. Data collection was completed in two waves, with the identification of preliminary findings and further rationalisation of tools completed in March 2022. In total, our analysis reflected on an evidence base of over 1,900 documents (Vol. II, Annex 4) and over 400 KIIs (Vol. II, Annex 20), plus work completed in the period 2018–2021. Our sampling approach is set out in Vol. II, Annex 3, which underlines that the evaluation team was able to independently identify relevant KIs and data sources. Although it was not part of the approved design to assess the strength of evidence for significant findings, the volume and type of evidence generated provided a strong base for our analysis. Data analysis was completed by the evaluation team thematic leads for each EQ, including at a cross-theme workshop in September 2022. (See Vol. II, Annex 4 for more details on data collection and analysis.)

The evaluation process was designed to ensure the participation of key stakeholder groups. For example, a draft report was reviewed by our Evaluation Advisory Group and checked for factual accuracy by the MA in November 2022; emerging headlines were discussed with the DHSC before submission. A summary overview of interactions with key stakeholder groups and plans to support the use and dissemination of evaluation deliverables are set out in our Use and Influence Plan (see Box 4 and Vol. II, Annex 17) some of which we have implemented already and the remainder of which we will implement throughout 2023 to promote the use of evaluation findings. There was little need to interact with other partners to avoid duplication as we did not identify any similar evaluative processes that we needed to align with. These interactions in no way influenced or compromised our ability to work freely and without interference in producing an independent assessment of the Fleming Fund’s achievements. Conflicts of interest were reviewed quarterly with the DHSC and MA according to an explicit Conflict of Interest policy; however, none were identified.

Box 4: Development and delivery of the Use and Influence Plan

Itad consults DHSC regularly on how the Use and Influence Plan for phase 1 is delivered. The plan in Annex 17 reflects what was anticipated for delivery at the time of writing this summative report. Activities are designed in line with a set of guiding principles:

- Making evaluation findings as useful as possible to key stakeholders – using appropriate language, medium, format, level of detail, etc.

- Sharing learning in time to inform the MA and DHSC’s planning and decisions

- Using resources wisely – activities capitalise on Fleming Fund events, and use existing digital channels, where appropriate.

- Continuously improving – monitoring dissemination, asking for feedback from the MA and DHSC, and regularly reviewing the work plan.

This report presents findings, conclusions and recommendations of the summative phase of the evaluation. It does not cover work completed under previous phases that has already been fed back to DHSC and the MA through three separate deliverables in 2018, 2020 and 2021 (as shown in Figure 9 above). Its primary target audiences are senior management within DHSC and HMT, as well as the MA and other donors and DPs. The six EQs have been used to structure data collection and analysis (as set out in Vol. II, Annex 2), but not to structure this report because ordering by EQ risked disjointed and duplicative presentation of findings; a mapping of EQs to report sections is included in Vol. II, Annex 5.

Challenges and limitations

Departures from the evaluation ToR are set out in Vol. II, Annex 11 with any implications for the credibility and robustness of our findings. We summarise some key challenges and limitations here.

The MA was not contracted to deliver outcomes, so monitoring data is weaker at that level.

Challenge in identifying the specific contribution of some grants (RGs, Strategic Alignment Grants) to country-level outcomes (see Box 2).

The evidence base is not complete in some areas, e.g. in terms of data on AMR testing, or on Fleming Fund expenditure (as part of the VfM analysis).

Limited information on plans for the Fleming Fund phase 2 constraining the extent to which our recommendations are focused on the most relevant issue.

The Fleming Fund has evolved during phase 1, both in response to the changing context and to implementation experience (as noted in sections 1.1 and 2.2), which makes it challenging to undertake a summative evaluation. We also note that the evaluation data collection was also impacted by COVID-19 but not with a significant effect on the evidence generated.

EQs are focused on whether Fleming Fund outputs contribute to outcomes of interest to the DHSC in terms of the use of AMR surveillance data for policy, regulation, and behaviour change at the national and international level. The bulk of this report addresses the EQs, which risks overlooking foundational work that has been delivered by the Fleming Fund grants programme. To mitigate this risk we take note of Fleming Fund outputs in Figure 11, and draw on Fleming Fund key performance monitoring data in the following sections

A comprehensive list of challenges and risks, e.g. relating to bias in the selection of KIs and other evidence sources, are discussed in more detail in Vol. II, Annex 13, with mitigating strategies. We note above those that are most salient in terms of limitations to the overall evaluation approach which the reader should bear in mind when reading this report.

Figure 11: What the Fleming Fund has delivered in phase 1

Findings

Strengthening systems to produce quality data on AMR

In this section we examine the extent to which there have been changes in the quantity and quality of AMR data. We then look at the drivers of observed changes and the Fleming Fund’s contribution to these drivers. Our focus is on AMR data, reflecting the emphasis of the Fleming Fund on this type of data. However, we also consider other data types where appropriate and feasible. For quantity, we primarily look at data on the number of samples (see for an explanation of the types of data that can be produced through AMR surveillance systems), rating performance on changes compared to baseline (2018), and consider both changes in volume and in proportion. Our information is primarily drawn from national-level secondary sources as described in Box 1 (e.g. obtained through interactions with staff in national reference laboratories (NRLs) because databases did not necessarily exist in all countries), and as such is intended to reflect the performance of the entire surveillance system not just performance in Fleming Fund-supported sites (see Vol. II, Annex 8.1 for more details and supporting data). For quality, we derive a ‘quality score’ for each laboratory which is based on the relevant components of the LSHTM roadmap and assessed using self-reported data from the MA’s quarterly reports (see Vol. II, Annex 8.2 for more details and supporting data).

Key findings

2.1.1 AMR was a known problem in 2018. NAPs were in place in most countries but were not being prioritised and implemented. There were varying degrees of commitment to the agenda across Fleming Fund countries on which to build. 2.1.2 Just over half of the 16 countries had a formal HH surveillance system in place, but less than half had a formal AH surveillance system in place. On the other hand, HH AMR data existed in all countries but not necessarily due to the presence of a formal surveillance system 2.1.3 Few laboratories, subsequently supported by the Fleming Fund, had the processes in place needed to generate high-quality AMR data. There is no evidence suggesting that other government supported laboratories were better situated. 2.1.4 The MA’s assessment of the status of surveillance systems (in 2017 and 2018) indicated significant variation in countries’ surveillance systems; although, in broad terms, HH systems were stronger than AH systems. Subsequent experience suggests overestimation of the actual status of surveillance systems across the portfolio of countries from this original analysis. 2.1.5 By December 2022, 14 out of the 16 focus countries had received 36 months or more of Fleming Fund support and so the underlying assumption is that increased data generation should be seen. The MA’s reporting on the number of Fleming Fund-supported HH and AH sites showing progress through the LSHTM roadmap suggests that significant implementation failure was not to be expected. 2.1.6 There is solid evidence that the quantity of HH AMR surveillance data available from government-funded laboratories supported through the Fleming Fund has increased in 11 out of 16 (69%) of the focus countries. Of the five countries not demonstrating increased AMR data availability in HH, two had not received 36 months of support and three lacked firm evidence of increases. 2.1.7 There is evidence of increases in the quantity of AH AMR surveillance data in 13 out of 16 countries (81%), with variation across the Fleming Fund country portfolio, although less confidence in the exact extent of change. Of the three countries not demonstrating increased AMR data availability in AH, two had not received 36 months of support and one lacked firm evidence of increases. 2.1.8 Improvements in internal systems ensuring the quality of AMR testing were seen in HH and AH in a majority of countries, but progress was mixed. 2.1.9 With performance to date, it is clear that the Fleming Fund achieved its stated aims for AMR data generation as set out in the implementation plan, albeit targets that were not ambitious and not sector specific. However, quality improvements have varied on a site-by-site basis, and it is not clear whether the MA’s aims have been consistently achieved (given the limited delineation of goals on quality at the start of phase 1). 2.1.10 Major drivers of increases in quantity (and quality) were identified as the renovation of sites and provision of equipment, investment in the capacity of the workforce, AMR governance, and supporting laboratory quality assurance (QA) systems and processes. In some countries, increases in the quantity of data at the national level were driven, to some extent, by the increases in the number of reporting sites or the number of pathogens reported but these were not necessarily from within the surveillance system. 2.1.11 Where no progress or reversals in quantity and quality were observed, we identified constraints to progress. In many cases, these were expressed in terms of ‘absence of’ or ‘delays with’ factors that were drivers of progress when present. 2.1.12 Overall, the Fleming Fund has made a vital or important contribution to most key drivers of increased quantity and quality in both HH and AH AMR data, albeit to variable extents.

What was in place in 2018?

Finding 2.1.1: AMR was a known problem in 2018. NAPs were in place in most countries but were not being prioritised and implemented. There were varying degrees of commitment to the agenda across Fleming Fund countries on which to build. NAPs were in place in 13 of the 16 focus countries (see Vol. II, Annex 8, Table 25), which indicates that AMR was a known problem, albeit one of these NAPs had not been approved at the cabinet level. Implementation and use of these NAPs was more problematic. The story was less positive if the allocation of funding is used as a measure of commitment and prioritisation towards addressing the problem. Government budgets for NAP implementation were only found in three out of 13 countries in 2018.

Finding 2.1.2: Just over half of the 16 countries had a formal HH surveillance system in place, but less than half had a formal AH surveillance system in place. On the other hand, HH AMR data existed in all countries but not necessarily due to the presence of a formal surveillance system. Baseline data collected by the evaluation team from AMR focal points and NRLs (as part of formal AMR surveillance systems) suggested that nine out of 16 countries had some form of HH AMR surveillance in place in 2018 (compared with six out of 16 in AH). However, NAPs suggested that some AMR data was available in all countries. This was confirmed by the retrospective data collection under the CAPTURA and Mapping Antimicrobial Resistance and Antimicrobial Use Partnership (MAAP) RGs (see Box 2 for more details). These RGs identified relevant AMR data in all 16 focus countries. This was also indicated in Global Antibiotic Resistance Partnership (GARP) reports for seven of the eight countries where GARP reports were available. In the main, existing data was derived from either research or testing in non-government health facilities. Given the focus on active surveillance for AH within the Fleming Fund, one should note that where formal AH systems existed, they relied on passive surveillance approaches drawing on samples taken as part of general AH support delivered through government systems.

Finding 2.1.3: Few laboratories subsequently supported by the Fleming Fund had the processes in place needed to generate high-quality AMR data. There is no evidence suggesting that other government supported laboratories were better situated. Direct assessment of the quality of data produced is challenging in the absence of a working and credible EQA system that verifies procedures used in the testing of samples. MA quarterly reporting, which relied on self-reports on the presence of internal laboratory QA systems, suggests that there was probably a high degree of variability in the quality of AMR data produced in government-funded laboratories. Variability existed between Fleming Fund countries, between Fleming Fund-supported laboratories within a country, and between HH and AH, with HH laboratories being more capable of undertaking internally quality-assured AMR testing (see Figure 3 ). Only 20% of the focus countries initially achieved the ‘core’ level for quality indicators (the minimum required for reliable testing) on the LSHTM roadmap for HH, with only one country achieving this in AH. This meant that few laboratories were able to process AST for all priority pathogens according to updated SOPs. In general, reference laboratories provided better quality AMR testing than surveillance sites or facility-level laboratories and our KIs did not suggest that the situation was different in government-funded facilities not supported through the Fleming Fund. In general, country-level KIs stated that other donors’ funding to increase laboratories’ capacity focused on testing for tuberculosis (TB) (through the Global Fund or the US PEPFAR programme to support AIDS programmes) or virology testing (such as for Avian Influenza in AH laboratories).

Box 5: Example of surveillance capacities in Timor-Leste

Prior to the Fleming Fund, Timor-Leste had no functioning AMR surveillance system. In general, laboratory infrastructure was poor, requiring the Fleming Fund to address underlying issues with electricity outages and flooding. Problems with electricity outages at the National Health Laboratory (NHL), which acts as AMR NRL, have been addressed thanks to a back-up generator that now supports the whole laboratory. This generator was previously only used for the TB laboratory as it was procured by the Korea International Cooperation Agency (KOICA). However, thanks to the Fleming Fund investment, the whole NHL is now connected to the back-up generator. The NHL was also vulnerable to seasonal floodings, causing frequent interruptions of laboratory services and damage to infrastructure. The Fleming Fund has funded critical flood protection work which was completed in Q1 2022. Aside from general renovation and refurbishment of the NHL, the Fleming Fund also found the need to strengthen the specimen transport system and Laboratory Information Systems, and through the CG hired a procurement consultant to improve national systems for procurement which continue to be a major hindrance for the NHL.

Finding 2.1.4: The MA’s assessment of the status of surveillance systems ( in 2017 and 2018) indicated significant variation in countries’ surveillance systems; although, in broad terms, HH systems were stronger than AH systems. Subsequent experience suggests overestimation of the actual status of surveillance systems across the portfolio of countries from this original analysis. The assessments followed the MA’s document based on the A–D categorisation of the status of surveillance systems in 2017 and initial in-country assessments in 2017 and 2018. The MA’s initial implementation plan was informed by experience within the team, a review of relevant and accessible documentation, and engagement in four countries where work started in 2018. During phase 1, staggered completion of MA assessments of laboratories’ actual capacity, as the MA engaged with more countries, revealed the expected extent of variation in both the status of laboratories that the Fleming Fund was due to support and governments’ level of ambition for AMR surveillance development. For example, sites in some countries were found to lack reliable water and electricity supplies that are fundamental in undertaking AMR testing. Better information highlighted potential overestimation of the actual status of surveillance systems across the portfolio of countries. This, in turn, has implications for assessing actual performance against expectations that were initially unrealistic in terms of the development of surveillance systems. This challenge was exacerbated by COVID-19 as described in section 1.5 and Box 6).

Had the quantity and quality of data on AMR changed by mid-2022?

Finding 2.1.5: By December 2022, 14 out of the 16 focus countries had received 36 months or more of Fleming Fund support and so the underlying assumption is that increased data generation should be seen. The MA’s reporting, on the number of Fleming Fund-supported HH and AH sites showing progress through the LSHTM roadmap, suggests that significant implementation failure was not expected. The initial assumption was that increased quantities of data would be found after 36 months of support. In practice, by June 2022 there is some evidence that data availability increased in 11 out of the 16 countries where the evaluation collected data . Recognising that our data collection took place in the first half of 2022 – generally with six to nine months of implementation remaining – we asked KIs whether further progress was expected in generating AMR data by the end of 2022. This was particularly relevant where countries had not yet completed laboratory renovation or received Fleming Fund-procured equipment ). Further progress was expected in nine out of 16 (57%) HH systems, and in six out of 16 (38%) AH systems by the end of 2022 when most phase 1 implementation ceased.

The MA’s reporting (shown in Figure 12 and Figure 13) suggests that despite probably initially overestimating the actual status of surveillance systems across the portfolio of countries, significant progress was made and in fact, exceeded the targets agreed upon with DHSC (as described below). This suggests that significant implementation failure should not be a significant explanatory factor for the lack of data observed.

Figure 12: Number of Fleming Fund-supported HH surveillance sites showing progress through the LSHTM roadmap

Figure 13: Number of Fleming Fund-supported AH sites showing progress through the LSHTM roadmap

Finding 2.1.6: There is solid evidence that the quantity of HH AMR surveillance data available from government-funded laboratories supported through the Fleming Fund has increased in 11 out of 16 (69%) of the focus countries. Of the five countries not demonstrating increased AMR data availability in HH, two had not received 36 months of support and three lacked firm evidence of increases. Quantifying the actual amount of new data has not been feasible. What is less clear is whether the full range of information is being recorded at the facility level and then collated at the national level as required to carry out solid analysis (see Box 1) at a national level. The MA did not consistently track and report the increase in AMR found (it instead reported data on the number of samples generated in each supported site and the number of these that resulted in the identification of a pathogen of interest), and neither did the governments. To fill this gap, in our data collection, we tried to collate data from various sources on patients tested, samples and isolates; we did not try to gather data on the number of ASTs completed, or on their results. We were unable to routinely gather comparable data for all of these types of data, even through conversations with laboratory staff and AMR focal points in each country. Even where data on several samples was available for multiple years, it was not clear to what extent it was comparable (i.e. more sites, more pathogens), increasing the challenge of interpretation. We used a range of sources to triangulate data from NRLs to form a picture of the changes in the quantity of data. Additional sources included:

MA quarterly reporting: data on the number of samples generated in each supported site and the number of these samples that resulted in the identification of a pathogen of interest; it does not report on the number of isolates or ASTs.

Other relevant documentation (where available): such as country-level reporting or reports from RGs (MAAP and CAPTURA).

Data from GLASS: using publicly available data from annual GLASS reports. This is objectively verifiable data but takes time to reach the public domain (the 2022 GLASS report published in December 2022 includes countries’ data from 2020). The 2022 GLASS report shows that more than 70% of our focus countries have shared data compared with around 6% in 2018 (see Vol. II, Annex 8, Table 29 for details).

KIIs: including during site visits; we asked KIs whether more data on AMR was available. Annex 20 lists KIIs completed in each country.

Based on this range of data, there is evidence that the quantity of data has increased (albeit with variation across Fleming Fund countries) but with less certainty on the extent of the increase (see Vol. II, Annex 8.1, Table 26 and 27 for supporting evidence).

Of the five countries not demonstrating increased AMR data availability in HH, two had not received 36 months of support and three lacked firm evidence of increases. As noted above, data availability increased in 11 out of the 16 countries where the evaluation collected data. Of the five exceptions, two  did not receive 36 months’ support and based on the underlying assumptions of Fleming Fund support, this may have been expected. This included one of only two category A countries from the entire Fleming Fund portfolio . Three remaining countries did not demonstrate increased data availability. In one, a reduction in data was noted but KIIs indicate that this was linked to the timing of the data’s collection and the impact of COVID-19 on demand and capacity within the AMR surveillance system. In the two others, we experienced challenges in obtaining data from country-level sources to confirm trends in data availability so we could not draw firm conclusions.

It proved harder to obtain reliable and relevant information on progress towards data sharing and use (see section 2.2). The issue of data quantity necessarily raises questions about data sharing and use processes in surveillance systems. We note, as described in Box 1, that healthcare providers furnish a useful set of surveillance data from on a range of key syndromic infection diagnoses (e.g. ‘sepsis’, urinary tract infections, and sexually transmitted infections). It would also provide information on the number of cases where AMR is not found and link clinical, demographic and laboratory data. Ideally, all of these types of data should be available for each case, as interpretation is challenging if key data points are missing. By implication, even if the data on increased reported instances of AMR is easily accessible, its utility above the level of the facility in which the test was carried out would be limited without being linked with the other required information.

Finding 2.1.7: There is evidence of increases in the quantity of AH AMR surveillance data in 13 out of 16 countries (81%), with variation across the Fleming Fund country portfolio, although less confidence in the exact extent of change. Of the three countries not demonstrating increased AMR data availability in AH, two had not received 36 months’ support and one lacked firm evidence of any increases. Similar to HH, we attempted to collate data on samples and isolates but instead of patients tested, we looked for data on animals tested. Unlike in HH we also asked for information on the number of sampling rounds completed as part of active surveillance (see Box 1 and Box 8), given the intent of the Fleming Fund was to increase evidence drawn from active rather than passive surveillance methods. In 2018, there was no active ongoing AH surveillance in three out of 16 countries. From a low baseline, there is evidence of increases in the quantity of data in most countries, which is corroborated through KIIs and triangulated through other documentation. See Annex 8.1, Table 28 for more information.

Of the three countries not demonstrating increased AMR data availability in AH, two had not received support for 36 months and one lacked firm evidence of any increases. As noted above, data availability increased in 13 out of the 16 countries where the evaluation collected data.. Of the three exceptions, two did not receive 36 months’ support in the AH sector. As with HH, in Pakistan we experienced challenges in obtaining data from country-level sources to confirm trends in data availability, making it difficult to see if there were any increases.

For the AH sector, it is important to note that increases in data derived from active surveillance have been modest at this stage. We note that, reflecting practice in 2018, a significant amount of AMR data reported is derived from passive surveillance and not the active surveillance approach proposed by the Fleming Fund. It is not clear whether these datasets are generated from production systems that are the most relevant for analysing AMR; the risk is that data from passive systems is driven by the dynamics in the AH sector rather than focusing on sampling where the risk of AMR is thought to be more significant.

Finding 2.1.8: Improvements in internal systems ensuring the quality of AMR testing were seen in HH and AH in a majority of countries but progress was mixed. As stated above, in 2018, only three out of 16 of the focus countries reached the ‘core’ level for quality indicators (the minimum required for reliable testing) on the LSHTM roadmap for HH, with only one country achieving this in AH (see Annex 8.2 Tables 34 and 35 for more details). This meant that few laboratories were able to process AST for all priority pathogens according to updated SOPs. Evidence reported by the MA suggests that by 2022 progress had been highly variable (Figure 14), with some countries only showing progress in some sites, and others showing progress across all sites for HH facilities. Variation in performance across the 16 countries appears more marked in AH than HH, where despite significant progress in some countries , progress overall has been limited. Reasons given in KIIs for this variation include a poorer than anticipated baseline situation, fewer government resources and infrastructure available in the AH sector, and less demand for laboratory testing than in HH facilities. We were unable to assess whether the number of countries reaching the ‘core’ level had increased because this was not reported through the MA systems and was not feasible for the evaluation team to generate within available resources.

Figure 14: Heatmap of quality of human health and animal health data

Note that for Figure 14, as described in Vol. II, Annex 8.2, Table 33 ‘Quality Score’ reflects a scale of 0–8 using MA reporting on whether eight key markers of quality processes were in place. When a marker was in place, a score of 1 was recorded so each site could score a maximum of 8. The ‘Sites’ graph in Figure 14 shows how many sites that the Fleming Fund supported in each country.

Comparing performance with targets from the MA’s implementation plan

Finding 2.1.9: With performance to date, it is clear that the Fleming Fund achieved its stated aims for AMR data generation as set out in the implementation plan, albeit targets that were not ambitious and not sector specific. However, quality improvements have varied on a site-by-site basis, and it is not clear whether the MA’s aims have been consistently achieved (given the limited delineation of goals on quality at the start of phase 1). The MA’s implementation plan set out targets for data generation that could be expected at different stages of Fleming Fund implementation (see Table 1), including a target of 18 out of 24 countries generating data after 48 months of implementation. By December 2022, 19 out of 23 countries (83%) had either reported data to GLASS or there is evidence from evaluation data collection that data is being generated. This surpasses the MA’s target of 18, although it is important to note that 12 out of 23 countries (52%) were generating some HH AMR data already before the Fleming Fund started (see Annex 8.1, Table 28). We also note that the target is simply tracking whether data is generated, not whether the quantity of data has increased (which is different from the EQ and explains any difference in figures shown here). Detail on the Fleming Fund contribution to this progress is provided in the following sub-section.

However, quality improvements have varied on a site-by-site basis, and it is not clear whether the MA’s aims have been consistently achieved (given the limited delineation of goals on quality at the start of phase 1). For category B countries (the majority included in the Fleming Fund and this evaluation), the MA aimed for laboratories to have established capabilities for automated blood culture, biochemical methods to identify bacterial species, the ability to perform quality-assured and appropriate AST at surveillance sites, and evidence of use of AMR data locally at surveillance sites. Data on quality indicators and from KIIs support that these aims have not been consistently met. For example, only two out of 10 category B countries had blood culture equipment installed and under maintenance contracts at all HH surveillance sites. However, the impact on progress is expected to continue in the short term due to delays in laboratory refurbishment, instrument delivery/ installation, and procurement of consumables which has often been linked to the effects of COVID-19 (see Box 6 and section ‎1.5).

The implementation plan also describes expected progress using it’s A–D categorisation of countries, but it is too early to make a judgement against these. As set out in section 1.1, the MA categorised laboratories using A–D categories (see Vol. II, Annex 15, Table 46 for detail). The aim was for countries to ‘move up a category’ after 48 months of Fleming Fund support. By December 2022, 3/23 (13%) countries had received 48 months of support, therefore, it is difficult to judge against these targets, nor is it clear what criteria were used to assess movement between categories.

What was the Fleming Fund contribution to changes in quantity and quality of HH and AH data?

We identified a range of drivers that contributed to or constrained progress, over which the Fleming Fund had varying degrees of potential influence and contribution to change through its grants portfolio. Our analysis suggests that these drivers were similar in the HH and AH sectors, and as such we present a combined set of findings covering both sectors.

Drivers of progress in increased quantity and quality of HH and AH AMR data

Finding 2.1.10: Major drivers of increases in quantity (and quality) were identified as the renovation of sites and provision of equipment, investment in the capacity of the workforce, AMR governance, and supporting laboratory QA systems and processes. In some countries, increases in the quantity of data at the national level were driven, to a degree, by the increases in the number of reporting sites or the number of pathogens reported but these were not necessarily from within the surveillance system. We briefly discuss each below and is summarised in Table 3 and Table 4 below. See also Vol. II, Annex 22 (tables C1a, C1b, C2a and C2b) for more details.

Renovation and equipment (cited as one of the key drivers of increased quantity of AMR data in 14 out of 16 countries in HH and 10 out of 16 in AH). Clean and functional laboratory space, with reliable electricity and water supplies, functioning basic equipment (e.g. refrigerators, incubators), and a reliable supply of consumables are vital prerequisites for generating quality AMR data. As described in section 2.3, a substantial part of Fleming Fund’s investment has been on establishing these requirements in NRLs and at surveillance site laboratories to ensure they are fit for purpose. Key performance indicator (KPI) data shows steady progress in the number of Fleming Fund-supported HH and AH surveillance sites showing progress through the LSHTM roadmap functions/stage. In 2019, 23 HH sites were making progress, which had increased to 118 by mid-2022; equivalent figures for AH sites were 47 in 2020 up to 51 by mid-2022 (see Figure 12 and Figure 13 for details). This capacity building was noted as an important driver for improvements in both quantity and quality in both sectors and the Fleming Fund grants made the main contribution as there was no significant investment by either the governments or other donors in these facilities in the reported period. In those two countries where renovation and equipment was not explicitly highlighted as a key driver in HH, one was a category D country (reflecting a high degree of existing laboratory capacity as described in Vol. II, Annex 15, Table 47) and the other noted the contribution of renovation and equipment in a different way (i.e. conflating with increases in the number of surveillance sites). For the six countries not reporting renovation and equipment as key drivers in AH, it seems that the focus on active surveillance (and implications in terms of Fleming Fund support provided to support this surveillance approach) is an explanatory factor.

Human resources (cited as a driver in nine out of 11 countries with positive progress in HH and in 12 out of 14 countries in AH). Alongside renovation and procurement of equipment, the Fleming Fund provides substantial investment into the capacity of the workforce that is responsible for delivering AMR surveillance and related functions. This has taken the form of both direct training of staff and support/mentorship through the Fleming Fellowship Scheme. Human capacity was noted as the most important driver in increasing the quantity of data in the AH sector (for HH it was noted as the third most important driver). Training of staff has also been fundamental to improvements in quality, through improving the availability of appropriately trained staff to generate AMR data. For the Fellowship scheme, KPI data for cohort 1 Professional Fellows show that 100% (20 out of 20) of Fellows in 2021 had made substantial progress in developing AMR-relevant competencies. This capacity development was also a major driver in the improvement of ‘quality scores’ in most countries. Similar statistics on outcomes of non-Fellowships training provided by the Fund are not available, but data on the number of training attendances and mentorships provided are summarised in Figure 11. Where human resources capacity building was not reported as a key driver, our analysis and data from KIIs suggest this is either linked to pre-existing capacity (i.e. status of surveillance system at the start of Fleming Fund support) or to KIs’ choices to emphasise certain Fleming Fund support (i.e. lack of reporting on human resource capacity building as a key driver did not necessarily mean that it did not contribute to progress).

Governance (cited as a driver in six out of 11 countries with positive progress in HH and four out of 13 in AH). The Fleming Fund has also provided strategic support to help strengthen the governance of AMR surveillance, under the auspices of AMRCCs as often set out in AMR NAPs. This recognised that, in addition to renovation and equipment or training of key staff, AMR surveillance systems need to be strategically designed and managed to contribute to key policy objectives and create signals about the importance of AMR surveillance functions.  This kind of governance support was noted as one of the top three most important drivers of progress in both sectors for quantity improvements. Governance was also noted as a constraining factor in both sectors in countries where progress has been slower.

Specific to improvements in quality (rather than quantity) were the development of and support for QA programmes and SOPs. Ensuring laboratories have SOPs based on internationally recognised standards that are followed and having a process of independently checking performance through EQA is also vital in improving quality, and through RGs and CGs, the Fleming Fund contributed to SOP development and EQA. This was an important driver of increases in quality.

Other factors that were noted, albeit less frequently, across the focus countries included the availability of good quality consumables in sufficient quantity (in HH) although with sustainability implications as discussed in section ‎1.3. Additionally, increased demand for AST by HH clinicians’ was noted (although this was not necessarily due to Fleming Fund support). In AH, the number of active sampling exercises conducted was noted as a driver, as well as the availability of consumables in sufficient quantity – similar to HH.

In some countries, increases in the quantity of data at the national level were driven, to some extent, by the increases in the number of reporting sites or the number of pathogens reported but these were not necessarily from within the surveillance system. In 14 of the 16 countries (88%), the number of sites reporting to GLASS increased between 2018 and 2022 as shown in Vol. II, Annex 8.1 (Table 29). In three of the 10 countries where we have trend data, increases in the quantity of data appear to have been driven by increases in the number of sites reporting, and KIIs in five countries noted this driver as vital or important in increasing the quantity of data. This suggests that drivers other than changes in laboratory capability (e.g. the drive to report data internationally and to collect available evidence including from surveillance sites) were important in some countries. A further factor was identified in analysing the data of six of the 16 countries (38%) where it appears that increases in the number of GLASS pathogens that countries’ surveillance systems could test for drove, to some extent, increases in the quantity of data available.

Table 3: Changes in quantity of HH AMR data

| Countries | Extent. of change | Renovation & equipment | Human capacity | Governance/ prioritisation | Consumables | Number of sites | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Indonesia |  |  |  |  |  |  |  |
| Kenya |  |  |  |  |  |  |  |
| Nepal |  |  |  |  |  |  |  |
| Tanzania |  |  |  |  |  |  |  |
| Uganda |  |  |  |  |  |  |  |
| Vietnam |  |  |  |  |  |  |  |
| Zambia |  |  |  |  |  |  |  |
| Bangladesh |  |  |  |  |  |  |  |
| Ghana |  |  |  |  |  |  |  |
| Laos |  |  |  |  |  |  |  |
| Timor-Leste |  |  |  |  |  |  |  |
| Pakistan |  |  |  |  |  |  |  |
| Nigeria |  |  |  |  |  |  |  |
| Senegal |  |  |  |  |  |  |  |
| Sierra Leone |  |  |  |  |  |  |  |
| Bhutan |  |  |  |  |  |  |  |

| Key: Extent of change | Key: Fleming Fund contribution |
| --- | --- |
| Considerable | Vital |
| Negative | Important |
| Limited | Limited |
| Unclear | Some |
| None yet | None |

Table 4: Changes in quality of HH AMR data

| Countries | Extent of change | Human capacity | Renovation & equipment | QA | SOPs | Consumables | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Bhutan |  |  |  |  |  |  |  |
| Ghana |  |  |  |  |  |  |  |
| Kenya |  |  |  |  |  |  |  |
| Tanzania |  |  |  |  |  |  |  |
| Timor-Leste |  |  |  |  |  |  |  |
| Vietnam |  |  |  |  |  |  |  |
| Bangladesh |  |  |  |  |  |  |  |
| Indonesia |  |  |  |  |  |  |  |
| Laos |  |  |  |  |  |  |  |
| Nepal |  |  |  |  |  |  |  |
| Pakistan |  |  |  |  |  |  |  |
| Zambia |  |  |  |  |  |  |  |
| Nigeria |  |  |  |  |  |  |  |
| Uganda |  |  |  |  |  |  |  |
| Senegal |  |  |  |  |  |  |  |
| Sierra Leone |  |  |  |  |  |  |  |

| Key: Extent of change | Key: Fleming Fund contribution |
| --- | --- |
| Considerable | Vital |
| Some | Important |
| Limited | Limited |
| Unclear | Some |
| None yet | None |

Constraints to increasing quantity and quality of HH and AH AMR data

Finding 2.1.11: Where no progress or reversals in quantity and quality were observed, we identified constraints to progress. In many cases, these were expressed in terms of ‘absence of’ or ‘delays with’ factors that were drivers of progress when present. For example, given the Fleming Fund’s emphasis on providing equipment that automates many processes in generating quality AMR data, KIs commonly described challenges in getting automated equipment installed and functioning, implementing service contracts, and obtaining reliable supplies of (often expensive) consumables as reasons for the lack of progress. Similarly, delays in the refurbishment of laboratories were cited as a common reason. This links to the duration of support, as identified in section ‎1.4. The lack of human resources was also identified as a constraint in the AH sector. It is important to note that, at the time of data collection, the renovation and provision of equipment was ongoing in some countries which would have impacted performance on generating data. We also note that training was impacted by COVID-19 (Box 6), and a high turnover of staff in laboratories, without locally sustainable ways of training, has impeded progress in some countries . Finally, the lack of adequate governance (effective oversight, attention to system design, and focus by policymakers and senior staff), was noted in both HH and AH.

Box 6: COVID-19’s effect on implementation

In many countries, COVID-19 had substantial impacts on the countries’ ability to continue with a programme of AMR surveillance, largely due to COVID-19 absorbing available bandwidth (or operating capacity) within country laboratory systems. Most countries cited COVID-19 as a factor impeding progress with the AMR agenda, consistent with the Global Database for Tracking AMR Country Self-Assessment Survey (TrACSS), 2021 reporting that the pandemic had negative administrative and operational impacts. Impacts were noted inter alia on the renovation of laboratories, delivery of equipment, and provision of training (whether direct or through the Fleming Fellows scheme). It is logical to ask whether better performance could have been achieved in the absence of COVID-19, and by implication whether the Fleming Fund’s response to COVID-19 was effective. This is not straightforward to assess. The Fund’s primary goals were broadly achieved in terms of strengthening laboratories and generating AMR data. This seems to be due to a combination of Fleming Fund support, and the duration of that support. Many countries were only able to receive 36+ months of support due to phase 1 extensions, which were necessitated by COVID-19, and associated spending reviews by HMG. We cannot say whether these extensions would have happened in the absence of COVID-19, although it is feasible that some would have been granted given the number of no-cost extensions approved (described in section ‎2.3). If implementation had finished in March 2021, no countries would have received the 36 months’ support by the end of phase 1 but the renovation of laboratories, delivery of equipment, training of Fleming Fellows etc. could have been delivered without any delays. We can say that the Fleming Fund appears to have managed to keep implementation on track with adaptations to ways of delivery and workplans/budgets where needed. It is therefore plausible to believe that COVID-19 had an impact on delivery, but that this appears to have been mitigated by how the Fleming Fund responded. We also note that the impact of COVID-19 was not entirely negative. KIs also commonly reported that COVID-19 ended to raise general awareness of the importance of taking public health threats seriously. Increased attention to infection prevention and control (IPC) was cited as a positive opportunity for national AMR agendas going forward. The case for investment in laboratory services and health security was made clearly and forcefully by the experience of responding to the pandemic, and the associated policy initiatives in dimensions such as health security tended to reinforce AMR governance structures in some countries. The Fleming Fund was also able to leverage its investments to support the COVID-19 response – for example, through aspects of the RG on whole genome sequencing being repurposed to support COVID-19 testing.

Fleming Fund contribution to these drivers

Finding 2.1.12: Overall, the Fleming Fund has made a vital or important contribution to most key drivers of increased quantity and quality in both HH and AH AMR data, albeit to variable extents. For HH, in all 16 countries, the Fleming Fund has made a vital or important contribution to at least two of the key drivers of change. In eight out of 16 countries (50%), the Fleming Fund has contributed in a vital or important way to over three of the key drivers of change. In addition to contributions to renovation and equipment and human capacity already mentioned, the Fleming Fund has contributed to QA (as a driver of increased quality of HH AMR data generated) and to SOPs (as a driver of increased quality of HH AMR data generated) in five countries respectively. The Fleming Fund’s level of contribution to the key drivers does not correlate clearly with the extent of change – i.e. a higher Fleming Fund contribution to results did not necessarily lead to stronger results/change. Category B countries seem to have performed better than other categories. The only category A country  has not yet shown progress in this area (see Annex 8.1 for more details). For AH, in all 16 countries (100%) the Fleming Fund has made a vital or important contribution to at least two of the top three drivers of change. In nine out of 16 countries (56%), the Fleming Fund has contributed in a vital or important way to over three of the key drivers of change. For example, Fleming Fund has made a vital or important contribution to renovation (as a driver of increased quantity of AH AMR data generated) in 10 out of 16 countries (62%), human capacity (as a driver of increased quantity of AH AMR data generated) in 12 countries (75%) and several active sampling exercises in eight (50%). Specifically for improvements in quality, in addition to the contribution to renovation and human capacity already mentioned, the Fleming Fund has made a vital or important contribution to SOPs in four out of 16 countries, QA in four out of 16, and governance in three out of 16. Contribution appears to be less strong in countries that have registered no progress in this area than in the countries that have experienced more significant change (see Annex 8.1 for details).

Examples of Fleming Fund contribution to quality improvements

Fleming Fellows. Fellowships helped strengthen the capability of laboratory staff across a range of competences relevant to conducting quality ASTs through mentorships by host institution mentors.

Regional Grants. The Fleming Fund funded the provision of EQA services through RGs in Africa and Asia, implemented by ASLM and the Technical University of Denmark (DTU) respectively. These two-year grants have set the foundation for proficiency testing for participating laboratories in both Fleming Fund focus countries and beyond.

Examples of Fleming Fund contribution to human capacity development

Fleming Fellows: Overall, our analysis confirms that professional fellowships contributed to increased human capacity in a majority of the focus countries. Although it is not possible to unpick their exact contribution compared to other Fleming Fund grant schemes, 71% of Fellows (for whom data was available) self-reported significant improvements in their competency.

Regional Grants: Fleming Fund contributed to improving the training of epidemiologists and microbiologists through its RG to ASLM which provided training in 14 African and two Asian countries.

The Fleming Fund’s contribution to system-focused drivers (increases in the number of sites and number of pathogens tested) is relatively limited, when compared with the drivers described above, given that decisions on the scope of country AMR surveillance were normally taken in the AMR NAPs or equivalent documents, to which the Fleming Fund had no input in most countries. One should also note that the Fleming Fund supports a subset of surveillance sites in most countries (with a range of 38–100% surveillance sites supported).

Results from the use of data

In this section we explore whether data generated through the efforts described above has been used to inform decision-making. We consider ‘data use’ from a variety of perspectives in terms of (1) assorted forms of ‘data sharing’; (2) country decision-making, considering the extent to which data is used in relevant processes; and (3) resulting national action and other country behaviour change, in line with our EQ and the Fleming Fund ToC’s emphasis on concrete change at the outcome level (see Vol. II, Annex 18). We look specifically at three levels of ‘data use’ – national, international and facility.

Data use is central to the overarching goals of the Fleming Fund policy; regulatory and other behavioural outcomes are ultimately the intended pathway for pursuing the reduced prevalence of AMR and associated morbidity and mortality. Given the low starting capacity of AMR surveillance systems in most Fleming Fund countries, the DHSC did not expect to see substantial use of AMR surveillance data during phase 1. It was expected that the actual use of data would advance only gradually over the third and fourth years of support to a country. Our evaluation approach is therefore more contingent and exploratory on questions of data use. The use of AMR data was not well-defined in the Fleming Fund monitoring architecture, and the basis for our evaluation is less firm because the Fleming Fund’s articulation of intended use has evolved during phase 1. In addition, our EQ is partly predictive in nature, including seeking to assess prospects for future use of AMR surveillance data at the national level.

It is also important to appreciate that assessment frameworks and performance indicators focused attention on the output level of the grants; outcome-level indicators and targets were not set at the country level, and formal systems to transparently assess progress towards outcomes at both country- and programme-level were not in place.

Key findings

2.2.1 In summary, for phase 1 overall, there are initial indications that data from AMR surveillance systems are starting to be collated and shared at the national level. However, progress has been slower than anticipated. 2.2.2 At the national level, data sharing with relevant committees is happening in six of the 16 focus countries. Even where AMR/C/U data is not yet being routinely shared with relevant committees, some progress towards this goal has been realised in most countries. Despite progress, Fleming Fund’s performance on AMR data sharing at the national level falls short of the targets set out in the MA’s implementation plan, although this assessment differs from MA reporting because it is undertaken on a different basis. Despite progress with sharing, AMR surveillance data from laboratory AST is not yet playing a prominent role in relevant decision-making at the national level. Some countries are taking action using different data. 2.2.3 At the international level, for HH more AMR data has been made available, with nearly three quarters of Fleming Fund countries sharing data to GLASS since 2018. In the AH sector: by May 2022, 14 out of 16 of the evaluation focus countries (88%) reported internationally to WOAH, with a reduction in the number reporting the most basic level of data and an increase in the number providing more sophisticated data. 2.2.4 At the facility level, there is emergent evidence that Fleming Fund interventions are stimulating positive changes to practices and attitudes as clinicians and other stakeholders start to interact differently with improved laboratories. Emergent evidence from this evaluation about facility-level changes is subject to methodological limitations. Many examples across both HH and AH involved the use of AMC/U data rather than laboratory-derived AST data of the type prioritised in Fleming Fund phase 1. 2.2.5 We have identified several factors that have driven examples of data sharing noted above. For data sharing at the national level these include increases in the quantity of data, development of surveillance functions to link data to governance structures, and formal governance structures (albeit with important limitations observed). 2.2.6 A wider range of drivers are relevant to the actual use of data (i.e. beyond data sharing) at the national level, recognising the limits of surveillance data itself and the complexity of non-linear policy processes. Key drivers include the availability of other forms of information and broader conditions for prioritisation of AMR being in place. 2.2.7 Similar drivers for data sharing at the international level were identified to those described at the national level – in terms of quantity of data and development of surveillance functions, with some differences in emphasis (e.g. governance structures were less important for international sharing). 2.2.8 Facility-level drivers are less clear so far, although there is some indication that an increased quantity of data is important and clinical engagement feedback loops have the potential to drive use. 2.2.9 The Fleming Fund has made very substantial contributions to the main drivers of data sharing at the national level, primarily through CGs’ engagement with AMRCCs or equivalent committees. 2.2.10 Fleming Fund’s approach in phase 1, especially emphasising One Health and Fellowships, has contributed positively to the prospects for data use. However, limitations in the MA’s conceptual frameworks currently limit the prospects for Fleming Fund contributions to data use as part of a sustainable, aligned, country-owned approach. As a result, the Fleming Fund has so far only made a limited contribution to advancing the prospects for sustainable country-owned data use. 2.2.11 For changes in reporting to GLASS, the Fleming Fund has contributed to most but not all key drivers of data sharing in all countries, albeit with less significance than the Fleming Fund’s contribution to changes in data availability. 2.2.12 For reporting to WOAH, the Fleming Fund has contributed to some drivers of data sharing in some countries, with limited contribution understandable given that this was not an area of focus for phase 1.

Data use baseline – the position in 2018

Data existed in-country in 2018, but AMR surveillance systems, even when formally in place, were lacking in the sense of mobilising data for national decision-making purposes. At the second Call to Action event in 2018 in Accra, a ‘lack of data’ was identified as a major constraint to the optimised use of antimicrobials. Implicit was the assumption that this gap would be filled through the development of effective surveillance systems. In practice, in 2018, a significant challenge was the lack of common understanding of what constitutes a country’s surveillance system across stakeholders and agreement on what data the surveillance system should prioritise the collection of (see Box 1 discussion of this). A review of NAP documents showed that the surveillance system and how it was expected to develop was not well specified in these documents. Even if formally in place, KIIs revealed significant differences in opinion between in-country stakeholders on which facilities were and were not within the surveillance system and should be prioritised for capacity development. Agreement on what data the systems were expected to collect, and hence implications for what needed to be in place, had also not been thoroughly discussed and agreed upon. Irrespective of whether formal surveillance systems were, or were not, in place, across all 16 focus countries a system to regularly and systematically collate quality-assured AST, and other, data needed for strong analysis was not in place for use at the national level in most countries. The Fleming Fund did not attempt to directly address these ambiguities, but rather accepted them as the then working context that would be addressed through strengthened governance.

Governance issues in the form of NAP implementation challenges were recognised by the Fleming Fund as crucial contexts for surveillance efforts and associated data use. As noted above (section 2.1), most Fleming Fund countries had developed NAPs by 2018; but attention internationally had already started to shift to their implementation challenges (including considerations of ‘political will’, financing, coordination, and technical capacity as well as data). The Fleming Fund 2019 Annual Review emphasised that ‘we are unlikely to see evidence of the use of AMR analysis/data at a country level before 2021’; although some specific examples of intended/emergent use were identified, especially in HH.

In 2018, evidence suggested a willingness of some governments to act but there was no track record of acting in response to AMR analysis drawing on data from their own surveillance system. KIIs identified that some countries had started to take national action on AMR by the start of phase 1, notably on import regulations in the AH sector  but driven by international initiatives. Thus showing that action might be taken. But there were no examples yet of AMR analysis drawing on data from a surveillance system influencing any change in national policy/ regulation or practice and attitude in-country. It was anticipated that any such results would be difficult to achieve during phase 1.

The gap in terms of collating AMR evidence for national use was echoed in international reporting, at least for HH (although better in AH). In 2018, only one  of the 16 countries (6%) reported some HH AMR data to GLASS, despite our finding that relevant HH data existed in all 16 countries. A further four out of 16 countries (25%) provided information about the status of their surveillance systems. See Annex 8.1, Table 29 for details. For AH, AMR data are not collated internationally, but WOAH (formerly OIE) collates the reporting of AMU. Evidence reported by countries to WOAH is confidential (commercially sensitive), not reported by country in WOAH compilations and can be difficult to obtain from countries. Nevertheless, our understanding data supplied by WOAH is that in 2018, 19 out of the 23 Fleming Fund countries (82%) reported to WOAH using one of three reporting options.

No baseline is available for facility-level data use in 2018 to enhance clinical practice. The use of data for decision-making at the facility level, especially in terms of the potential impact on clinical practice, was understood to be relevant from the outset of phase 1. However, no information was gathered to set a baseline at this level through either of the two main causal pathways – directly through treatment of an individual patient or through revision of the treatment guidelines issued nationally.

Changes in data use at national, international and local levels

Finding 2.2.1: In Summary, for phase 1 overall, there are initial indications that data from AMR surveillance systems are starting to be collated and shared at the national level. However, progress has been slower than anticipated. Data is starting to be shared with AMRCCs for national decision-making purposes, but as discussed under findings related to the quantity of data and initial overestimation of the status of facilities, later than initially assumed. The Fleming Fund’s assumptions that data, once shared, will be used for decision-making and then motivate action have not yet, based on KIIs, proven to be valid. For phase 1, there have been forward steps with international reporting and signs of use at the facility level. We present below, a detailed analysis for national, international and facility-level use.

Data use: progress at the national level

Finding 2.2.2: At the national level, data sharing with relevant committees is happening in six of the 16 focus countries. Even where AMR/C/U data is not yet being shared with relevant committees on a routine basis, some progress towards this goal has been realised in most countries. Despite progress, Fleming Fund’s performance on AMR data sharing at the national level falls short of the targets set out in the MA’s implementation plan, although this assessment differs from MA reporting because it is undertaken on a different basis. Despite progress with sharing, AMR surveillance data from laboratory AST is not yet playing a prominent role in relevant decision-making at the national level. Some countries are taking action using different data.

At the national level, data sharing with relevant committees is happening in six of the 16 focus countries. Even where AMR/C/U data is not yet being shared with relevant committees on a routine basis, some progress towards this goal has been realised in most countries. Our assessment, based on KIIs, was that data sharing has been established to date in six of the 16 focus countries, including evidence from documents and KIs on the use of applicable data for decision-making in four of those countries  and substantial progress towards future use of data in the remaining two . Applicable data is now being systematically collated and analysed for intended routine sharing in a further four Fleming Fund countries . In addition, there have been some concrete steps forward in relevant national collation and analysis processes in another three countries . Currently, only three countries from the 16 considered do not exhibit substantial progress towards programme national data sharing objectives . Note that data sharing reported here may reflect broader data than AMR from surveillance sites, and is separate from the consideration of whether the quantity of data is increasing as discussed in section 2.1.2.

Despite progress, the Fleming Fund’s performance on AMR data sharing at the national level falls short of the targets set out in the MA’s implementation plan, although this assessment differs from MA reporting because it is undertaken on a different basis. Six out of 16 achieved against an initial Fleming Fund target of 11 of 16 countries for ‘primary data generated… and used for policymaking’ [emphasis added]. This assessment differs from MA’s reporting which tracks the sharing of data, and in mid-2022 reported sharing of data in 13 out of the 16 countries, but does not track use.

Despite progress with sharing, AMR surveillance data from laboratory AST is not yet playing a prominent role in relevant decision-making at the national level. Some countries are taking action using different data (see Figure 15 below). Evidence from KIIs and document review suggests that over half (9/16) of the focus countries have initiated significant policy and regulatory action on AMR at the national level since 2018. Typically, this comprised both HH policy changes to treatment and other Antimicrobial Stewardship (AMS) related guidelines plus national essential medicines lists, and AH regulatory adjustments prohibiting certain uses of specific antimicrobial products. The latter type of action in AH regulation was more common, and applied in eight countries, whereas the former type of action in HH regulation only applied in five countries. Notwithstanding action, only two countries have so far used AMR surveillance data from laboratory AST directly in national decision-making leading to concrete national action (both in HH policy). In general, AMC/U data appears more commonly used for national decision-making , including through existing sectoral rather than AMR-specific committee processes .

Figure 15: Summary of examples of national action from evaluation focus countries and regions

Data use: changes in quantity of data at international level

Finding 2.2.3: At the international level, for HH more AMR data has been made available, with nearly three quarters of Fleming Fund countries sharing data to GLASS since 2018. In the AH sector: by May 2022, 14 out of 16 of the evaluation focus countries (88%) reported internationally to WOAH, with a reduction in the number reporting the most basic level of data and an increase in the number providing more sophisticated data.

At the international level, for HH, more AMR data has been made available, with nearly three quarters of Fleming Fund countries sharing data to GLASS since 2018. International reporting in the HH sector is to WHO’s GLASS database. By December 2022, publicly available data showed that 17 of the 23 countries (73%) had reported data to GLASS. Within the 16 evaluation focus countries, 13 countries reported in the GLASS 2022 report; all of these increased the number of sites reporting to GLASS, and nine out of 13 either increased the number of pathogens reported or maintained a high level of capability to test GLASS priority pathogens., This exceeds the goal for international data sharing set out in the MA’s implementation plan. However, as with data generation, the capacity that existed before the start of Fleming Fund implementation should be noted; nine of 17 reporting countries contributed to the 2020 report.

In the AH sector: by May 2022, 14 out of 16 of the evaluation focus countries (88%) reported internationally to WOAH, with a reduction in the number reporting the most basic level of data and an increase in the number providing more sophisticated data. For the AH sector, countries report to WOAH on AMC/U using one of three reporting options. Data obtained from the WOAH secretariat indicated that, by May 2022, 20 out of 23 Fleming Fund countries (87%) reported to WOAH compared to 82% in 2018 (our baseline). In the evaluation focus countries, 14 out of 16 of the evaluation focus countries (88%) reported that they had reported to WOAH and these countries reflected a reduction in the number of countries reporting the most basic level of data (6% compared to 23% in 2015 when WOAH reporting began), and an increase in the number providing more sophisticated data, i.e. option 3 (44% compared with 8% in 2015 when WOAH reporting began). The MA implementation plan does not appear to have set an explicit goal for sharing AH data internationally. This reflects well compared with global averages for 155 WOAH member states, which have a greater proportion of countries that reported only qualitative data (21% compared to 6% in the evaluation focus countries) and fewer using option 1 (21% compared with 38%); reporting for option 3 was broadly comparable (49% compared with 44%).

Data use: progress in data use at the facility level

Finding 2.2.4: At the facility level, there is emergent evidence that Fleming Fund interventions are stimulating positive changes to practices and attitudes as clinicians and other stakeholders start to interact differently with improved laboratories. Many examples across both HH and AH involved the use of AMC/U data rather than laboratory-derived AST data of the type prioritised in Fleming Fund phase 1.

At the facility level, there is emergent evidence that Fleming Fund interventions are stimulating positive changes to practices and attitudes as clinicians and other stakeholders start to interact differently with improved laboratories. Emergent evidence from this evaluation about facility-level changes is subject to methodological limitations. A substantial number of examples were confirmed in specific facilities across countries (35 examples from 13 of the 16 countries) through KIIs. Despite extensive efforts, it was not possible to identify any examples in three countries . See Annex 9.1, Tables 36–38 – Examples of use at the facility level for further evidence and discussion. These examples suggest an encouraging picture of local data use dynamics in specific facilities in many Fleming Fund countries. But the examples are not necessarily representative of overall local change dynamics at the overall system level within a particular country. Examples were typically difficult to obtain; they were specific to local circumstances and implicitly described activities that resulted from extraordinary initiative and effort, often apparently cutting against norms in wider systems. See examples of use in Table 5.

Emergent evidence from this evaluation about facility-level changes is subject to methodological limitations. It is important to note that examples of data use collected at facility level are not necessarily representative of overall local change dynamics at the overall system level within a particular country. First, examples were sought as indications of specific programmatic effect rather than general system dynamics. Examples described particular local circumstances and implicitly described activities that resulted from extraordinary initiative and effort, often apparently cutting against norms in wider systems. Second, practical data collection considerations contingent on resourcing constraints and data collection time windows meant that this evidence-generation effort was undertaken as an impressionistic observational effort. Accordingly, the evidence generated is subject to methodological limitations including probable selection, reporting and confirmation bias. For example, the data collected does not allow for analysis of situations in which change did not occur or disappointed expectations. Third, evidential value is also limited by the lack of quasi-experimental comparison, for example with a control group within Fund scope or possibly with corresponding information from non-Fund countries.

Table 5: Summary of examples of national action from evaluation focus countries and regions

|  | Human Health | Animal Health |
| --- | --- | --- |
| A ‘typical’ example | #21–- Eastern Regional Hospital, Koforidua, Ghana. Over 2020–21, Fleming Fund’s supply of an automated blood culture machine and consumables to the hospital Bacteriology Unit enabled it to supply improved data on the resistance pattern of blood culture isolates to the Antibiotic Committee. Work is ongoing to review the hospital drug formulary using this insight into current local AMR patterns. | #27–- Tanzania Veterinary Laboratory Agency Mwanza Zonal Lab, Mwanza, Tanzania. Over 2021–22, Fleming Fund’s provision of equipment, reagents, and training enabled the laboratory to undertake AST for poultry and cattle farmers facing morbidity and mortality due to ineffective treatment of typhoid and mastitis. Test results were used as evidence to adjust treatment, improve outcomes, and protect investments. |
| A remarkable example | #17–- The Indus Hospital and Health Network (IHHN), Sindh, Punjab, and Khyber Pakhtunkhwa, Pakistan. Over 2021, Fleming Fund CG2s worked with six hospitals across the IHHN to develop a clinical engagement programme using laboratory reports in combination with a new facility planning tool. This has enabled the development of a broad AMS programme in each site, including teaching and training, IPC function links, and improved procurement planning. Initial observations suggested improved prescription practices as well as increased demand for AST. | #16–- Microbiology Department of the National Centre for Veterinary Hygiene Inspection Nos. 1 and 2, Hanoi and Ho Chi Minh City, Vietnam. As things stand in 2022, Fleming Fund’s support, to process and sample collection in these laboratories, has helped boost the data that they provide to relevant functions in the Ministry of Agriculture and Rural Development, the sector regulator. In addition to use for SOP development, this data has helped inform the development of budget allocation requests that have been submitted to the Provincial People’s Committees to fund ongoing surveillance. |

Many examples across both HH and AH involved the use of AMC/U data rather than laboratory-derived AST data of the type prioritised in Fleming Fund phase 1. As discussed in Annex 9.1, the majority of examples offered focused on AMS as the objective of relevant data use (20/35 or ~57%). Otherwise, a significant proportion targeted awareness-raising objectives (8/35 or ~23%). A further significant proportion pursued IPC objectives (7/35 or 20%), mostly in combination with AMS goals (4/35 or ~11%).

What were the drivers of changes to the use of AMR data

Drivers of progress on data sharing at the national level

Finding 2.2.5: We have identified several factors that have driven the examples of data sharing noted above (see Table 6 below, and Vol. II, Annex 22, Table C3 for more details). For data sharing at the national level, these include increases in quantity of data, development of surveillance functions to link data to governance structures, and formal governance structures (albeit with the important limitations observed):

Increased quantity of data led to data sharing in some, but not all, countries. Data sharing improved markedly in some countries in which the quantity of data also improved significantly, and key informant respondents noted limited progress with data sharing in others where there was no increase in data . But data sharing gains were made in other countries despite relatively muted changes in the quantity of data  and it was more common to see limited data sharing taking place despite increases in quantity of data – suggesting other important factors were delaying and complicating data use . It is worth noting that ensuring availability/quantity of data is more of a challenge in the passive systems that are predominant in HH – insofar as it relies on demand from patients and practitioners/ clinicians. In AH, where active surveillance has been the focus, this is more within the control of NRLs and the drivers of data sharing are likely to be different.

The development of national AMR surveillance functions (i.e. those that linked the generation of data to national governance structures) was also relevant to data sharing in HH (as set out in Figure 4). In all Fleming Fund countries in which data sharing was found to have progressed well, stakeholders identified that at least one aspect of surveillance was relevant. Staff incentives to take responsibility for surveillance work were pivotal in countries showing the greatest progress with data sharing and associated decision-making . In other countries, stakeholders identified effective human and financial resourcing as an important factor . Conversely, surveillance system deficiencies were frequently raised as issues by stakeholders in countries not making good progress on data sharing – the outstanding issue highlighted was a lack of sufficient systems and processes for reporting and collation (including IT) .

Stakeholders emphasised formal AMR governance structures around AMR NAPs as vital enablers of data sharing; however, there are also persistent limits to the scope for AMR NAPs to act as drivers of sustainable data sharing. Ongoing work on NAPs, especially identifying AMRCC or equivalent national functions for One Health decision-making on AMR, helped establish the coordinating functions with which data should be shared. Where strong AMRCC operations existed, this helped explain progress with data sharing including where data availability changes have been less pronounced . Where data sharing progress has been relatively poor relative to changes in data availability, stakeholders often offered explanations that included issues with how AMRCCs are set up or operate – especially in South-East Asian countries (. This underlines the limitations of AMR NAPs and associated governance (see sub-section  ‘data use: progress at the national level’ above); AMR NAPs establish AMR in national governance, but do not assure its prioritisation as an issue.

Finding 2.2.6: A wider range of drivers is relevant to the actual use of data (i.e. beyond data sharing) on a national level, recognising the limits of surveillance data itself and the complexity of non-linear policy processes. Key drivers include the availability of other forms of information and broader conditions for prioritisation of AMR being in place.

The types of data being used are different in HH and AH, indicating that AMR surveillance data is not always what is needed. See Figure 16, which breaks down the types of data found to be relevant in the four instances of national action to date across Fleming Fund countries in HH alongside the seven instances in AH. Although the instances of AH action were more numerous overall, there are not yet any examples of such action being motivated with reference to AST-based surveillance data. Decisions on AH action have so far referred to AMR data more generally, typically AMC/U data (which often falls short of surveillance data in terms of being less granular, often cross-sectional and non-representative). Instances of action are less common in HH, but they do already include examples of decisions being taken using AST-based surveillance data. To date, the potential for surveillance data to impact on decision-making leading to action has only been proven in practice in the HH sector. This raises an important consideration around what AMR analysis is needed for which purposes. For example, if potential use is in the development and revision of AMS-related guidelines and/or national essential medicines lists, to what extent is relevant data and analysis from AMR/C/U surveillance shared with the right committees and what can AMRCCs do to ensure relevant stakeholders are engaged? This is distinct from AMR analysis that signals the importance of action where solutions are already known (e.g. in IPC).

Figure 16: Illustration that some national action in sample countries is based on non-surveillance data, particularly in AH

Data use so far has followed on from the use of other forms of information including international standards and research. In many of the countries taking action (4/9), AMR data was not a significant input to most relevant decision-making processes . There were no examples of AMR surveillance data inputs influencing national decision-making in the absence of other inputs. Key stakeholders instead highlighted the influence of international standards as motivating action and research (typically on some aspect of AMR in the relevant country). It is worth noting that AMR surveillance data only has a modest influence on national policy, even in countries that are known to be better resourced and implementing stronger formal evidence review processes. Phase 1 remained focused on surveillance systems and the DHSC deprioritised planned operational research which may have generated policy solutions based on advanced data use. However, moving into phase 2 there have been renewed discussions between the MA and the DHSC over appropriate approaches to outcome-level results.

The use of data happens where key conditions are in place for the prioritisation of an agenda in the broader policy context, but this is generally not the case in Fleming Fund focus countries. When considering the prospects for data use it is important to look at the bigger picture in terms of how AMR-related information is used in countries’ political and economic contexts. Prioritisation of an agenda happens when policymakers concurrently understand the problem, have a viable solution available, and are convinced of the need to act (see Vol. II, Annex 9.2  for more details. This concurrent understanding happens in ways that are difficult to predict, take time, do not necessarily progress in a linear fashion, and are sometimes facilitated by a policy entrepreneur. Evidence from published literature and KIIs suggests that the necessary conditions for the prioritisation of AMR NAPs are generally not in place in Fleming Fund countries (see Annex 9.2, Table 41 for more detail). This is not unexpected in light of the broader agenda-setting experience. A key implication is that timelines for use in policy and regulatory processes are driven outside AMRCCs. Even if the right analysis is being generated, it needs to be available when the process of revision happens. This is further complicated where solutions are already known (e.g. in relation to AMS and IPC) but not prioritised; it is a question both of ensuring timeliness and relevance of analysis that will lead to greater prioritisation and implementation of solutions. Given that Fleming Fund-supported data generation was gathering pace mostly in 2022, there has only been a limited window of opportunity for this to influence national processes.

Drivers of progress at the international and facility levels

Finding 2.2.7: Similar drivers for data sharing at the international level were identified to those described at the national level – in terms of quantity of data and development of surveillance functions, with some differences in emphasis (e.g. less importance given to governance structures):

Increases in quantity of data had a more direct influence on data sharing at the international level than at the national level. In countries where we have observed considerable or some change in data sharing with GLASS and/or WOAH, the presence of some/more AMR surveillance data was indicated as a key driver. Where limited change in this area was reported and in countries where we have observed no change in this area , the most commonly cited reasons were (insufficient) data supply.

The development of actual surveillance functions for data sharing proved decisive for success at the international level as well as at the national level. Stakeholders consistently raised data sharing processes as a key driver for international reporting. In countries showing considerable change, this tended to include IT systems such as a new user-interface database platform, in place and functioning. For countries showing some change, the availability of skilled personnel and/or availability of financing were also mentioned as key factors in the majority of cases. We note that there was limited scope for the surveillance systems supported by the Fleming Fund to drive international use.

There is also some evidence that data was collated through discrete exercises (outside of surveillance systems). For example in Pakistan and Nepal data was made available through a donor-funded (Centres for Disease Control (CDC) and Fleming Fund respectively) exercise to collect data from facilities and report to GLASS. This is consistent with the baseline picture and findings from the MAAP and CAPTURA RGs, that data existed before Fleming Fund implementation began but was not easily accessible. Stakeholders tended to refer directly to the availability (or lack) of technical assistance/proactive engagements of external partners in driving international data sharing, especially where limited or no change .

Finding 2.2.8: Facility-level drivers are less clear so far, although there is some indication that an increased quantity of data is important and clinical engagement feedback loops have the potential to drive use. Drivers of use at the facility level are emergent. The evaluation was not initially tasked to focus on understanding use at the facility level, nor was it a core focus of what the MA set out in its implementation plan. Consequently we did not have time or resources to understand the drivers of use at this level. We have identified some factors that appear to drive facility-level use. At least in some examples of use, data use was directly enabled by increased supply; data was typically shared with expert audiences capable of understanding AST results and other relevant content without interpretation. There are signs that facility-level data use has the potential to be driven by clinical engagement feedback loops with professional and industry groups concerned to improve treatment practices, especially in HH with the local hospital committee (see Annex 9.3). Other indications of facility-level drivers include clinical demand for AST – potentially linked to decision-making on laboratory resourcing. However, these cannot be considered representative of wider systems and there was wide variation in the sources of the examples obtained.

Constraints to progress with data use

As with changes in data quantity and quality, we identified constraints to data use where no progress was observed. Again, these were often expressed in terms of ‘absence of’ or ‘delays with’ – the same factors that were drivers of progress when present. At the national level, the most serious and pervasive constraints were governance issues (including lack of resourcing and insufficient prioritisation and, less frequently, lack of formal structures). Constraints in terms of the quantity of data or relating to surveillance systems themselves were more often discussed by stakeholders in terms of delays (i.e. constraints to timing but not to change generally). At the international level, governance was not a major constraint; the leading constraining factors where international reporting did not progress were the lack of surveillance systems for reporting and the lack of data generally. Constraints to data use at the facility level were not investigated in detail but certainly included some governance aspects (e.g. a lack of clinical committee functions for engagement in some hospitals and/or laboratory difficulties in securing local allocations for equipment or consumables).

Fleming Fund contribution to drivers at national and international levels

Fleming Fund contribution to drivers at the national level

Examples of Fleming Fund contribution to national-level use

The following elements of Fleming Fund design were intended to contribute to sharing of data:

- Fellowships: Policy and Surveillance Fellows

- Regional Grants: RADAAR, CAPTURA and MAAP on historical data use

- Global grants (including ODI Fellowships and CWPAMS)

Implementation progress (especially for the Fellowships) as described in section 1.4.2 and Box 2, and the duration and visibility of some of these efforts (especially RGs) appear to have limited the extent to which KIs noted the contribution to data use.

Examples of Fleming Fund contribution to national-level use

The following elements of Fleming Fund design were intended to contribute to sharing of data:

- Fellowships: Policy and Surveillance Fellows

- Regional Grants: RADAAR, CAPTURA and MAAP on historical data use

- Global grants (including ODI Fellowships and CWPAMS)

Implementation progress (especially for the Fellowships) as described in section 1.4.2 and Box 2, and the duration and visibility of some of these efforts (especially RGs) appear to have limited the extent to which KIs noted the contribution to data use.

Finding 2.2.9: The Fleming Fund has made very substantial contributions to the main drivers of data sharing at the national level, primarily through CGs’ engagement with AMRCCs or equivalent committees (as shown in Table 6). The Fleming Fund CGs were reported to have made vital or important contributions to the quantity of data, governance, and/or AMR surveillance systems in a majority of the focus countries. Where data sharing is already taking place (see section 2.2 – Bangladesh, Kenya, Tanzania, Nepal, Bhutan and Uganda), CGs were normally reported to have made important or vital contributions to all three of these drivers.

The Fleming Fund CGs’ engagement with AMRCCs or equivalent committees was cited by relevant key informants as a vital or important contribution to data sharing in all countries where this is already taking place or where relatively good progress has been achieved to date (see preceding sub-section on ‘what were the drivers of change to the use of AMR data’). CGs often played a secretarial role, helping set dates, developing paperwork, and producing minutes for meetings on behalf of counterparts’ official AMRCC secretariats. But Fleming Fund contributions in terms of CGs’ activities to strengthen data availability and surveillance systems were less consistently recognised by relevant key informants as important to data sharing.

Based on the programme design, we expected stakeholders to attribute changes in national data use to a range of Fleming Fund investments including follow-on CGs focused on data use (CG2s), Fellowships (notably policy, but also professional/surveillance), RGs (including RADAAR on policy as well as CAPTURA/MAAP on historical data use) and global grants (including ODI, Fellowships and CWPAMS). However, these investments were rarely raised in connection with data use efforts, and seldom as making a direct contribution to national data sharing. The most frequently mentioned contribution was Professional Fellows as an analytical resource for surveillance system development (in four out of the 16 focus countries ). Stakeholders tended not to distinguish between CG1s and CG2s (likely because CG2s mostly continued CG1 activities, as discussed in section 1.4). In some cases, contributions were described as a work in progress towards the end of phase 1 (Policy Fellowships, CAPTURA/MAAP), but it was too early to say at the time of data collection for this evaluation.

Table 6: Changes in data sharing with relevant committees

| Countries | Extent of change | Governance /demand | Data supply | Data sharing processes | Incentives | Resourcing | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Bangladesh |  |  |  |  |  |  |  |
| Nepal |  |  |  |  |  |  |  |
| Kenya |  |  |  |  |  |  |  |
| Tanzania |  |  |  |  |  |  |  |
| Uganda |  |  |  |  |  |  |  |
| Bhutan |  |  |  |  |  |  |  |
| Pakistan |  |  |  |  |  |  |  |
| Vietnam |  |  |  |  |  |  |  |
| Laos |  |  |  |  |  |  |  |
| Zambia |  |  |  |  |  |  |  |
| Ghana |  |  |  |  |  |  |  |
| Sierra Leone |  |  |  |  |  |  |  |
| Timor-Leste |  |  |  |  |  |  |  |
| Indonesia |  |  |  |  |  |  |  |
| Nigeria |  |  |  |  |  |  |  |
| Senegal |  |  |  |  |  |  |  |

Key: Fleming Fund contribution

Vital

Important

Limited

Some

None

Key: Extent of change

Considerable

Some

Limited

Unclear

None yet

Finding 2.2.10: Fleming Fund’s approach in phase 1, especially emphasising One Health and Fellowships and some RGs, has contributed positively to the prospects for data use. However, limitation in the MA’s conceptual frameworks currently limit the prospects for Fleming Fund contributions to data use as part of a sustainable, aligned, country-owned approach. As a result, the Fleming Fund has so far only made a limited contribution to advance the prospects for sustainable country-owned data use.

Fleming Fund has accorded visibility to the One Health approach in all its countries of operation. This was done by encouraging the development of formal partnership mechanisms, especially CG governance-related work, as well as by encouraging interactions between sectoral actors through events such as World AMR Awareness Week. In addition, the Fleming Fund Fellowships’ contribution to data use extends far beyond simple direct contributions to national data sharing (see Annex 9.2). The positive contribution being made by the Fellowships is best understood in terms of their role in forming communities around AMR, increasing the chances of AMR being prioritised. Phase 1 RGs activities have also helped to build consensus on data use issues and to equip stakeholders for future initiatives. Notably, the RADAAR RG aimed to catalyse a sustained demand among decision-makers for high-quality information and data sharing for use in global AMR planning, policy and advocacy; first through a series of data gathering and consultative workshop exercises in 2021–22 then through pilot training sessions in the Basic Principles of Translating Evidence to Policy. CAPTURA and MAAP RGs have also generated policy brief material which will be available to inform national policy efforts going forward.

However, limitations in the MA’s conceptual frameworks (on One Health, categorising country capabilities, and on understanding the political economy) currently limit the prospects for the Fleming Fund’s contributions to data use as part of a sustainable, aligned, country-owned approach.

The MA’s approach to One Health is characterised as an institutional mechanism for encouraging data sharing. However, as discussed in Box 7 below and in Vol. II, Annex 7, the drivers and mechanisms for multisector partnerships are not restricted to AMRCCs or technical working groups. Cross-sector partnerships require navigating local institutional and interpersonal political dynamics. Although the One Health emphasis has been positive in phase 1, the form and function of One Health partnerships needs to be thought out better, grounded within the institutional context of each country, incorporating flexible and informal cross-sector collaborations such as research networks.

MA frameworks for justifying and assessing Fleming Fund investments tend to focus exclusively on surveillance systems. Under phase 1, the MA classified countries according to broad descriptions of the successive stages of idealised surveillance systems (see the MA A-D categories in Annex 15, Table 47). This tended to exclude other reference points that could inform strategic orientation, notably an assessment of the prospects for advancing data use in a particular country (for example, the categorisation could reflect on historical data trends from CAPTURA/MAAP, policy reflections from RADAAR, research or other inputs from Fellows).

Political economy analysis (PEA) plays a minor role in programme management. While the MA chose to deprioritise formal PEA processes during phase 1, MA teams are certainly aware of relevant political economy considerations. However, the lack of formal PEAs makes it difficult to see how the MA’s knowledge is explicitly used in prioritisation and positioning. It is important that it is explicit so that HMG can understand how it is used, and can then use to leverage broader UK networks. Multiple streams approach analysis of the drivers of data use in the wider context (see Box 7) suggests the value of working more opportunistically and entrepreneurially. PEAs were undertaken in some, but we are unaware of, for example, any systematic efforts to reflect on similarities or differences between countries involving significant decentralisation of health system decision-making or financing. This falls short of the state of the art in relevant development practice, which the UK has helped to pioneer.

Box 7: One Health and AMR data use: the case for considering informal approaches

As discussed in Vol. II, Annex 7, we found that One Health partnerships can assume different forms across different countries, including varying levels of formality. Often formal institutional partnerships can arise from informal networks. For example, in Indonesia, the Antimicrobial Resistance Control Committee under the Ministry of Health (KPRA) borrows its leadership from a professional network of AMR researchers. Similarly, countries such as Bangladesh have been home to active professional networks around One Health, such as One Health Bangladesh, that are able to mobilise research as well as policy action. On the other hand, countries with more formalised administrative cultures, such as Senegal, might find cross-sectoral institutional collaborations more difficult to convene because of the presence of strong bureaucracies with demarcated jurisdictions.

As a result, the Fleming Fund has so far only made a limited contribution to advancing the prospects for sustainable country-owned data use. In particular, the Fleming Fund was unable to make much progress over phase 1 in the key dimension of resources for AMR surveillance (see section 2.3 on sustainability). Increasing emphasis on use at the facility level (see above sub-section on ‘data use: progress in data use at the facility level’) could offer alternative pathways to secure resources for AMR functions, for example circumventing national budget allocations and focusing instead on the facility-level resource allocation decisions. But there are complications involved in mobilising any such solutions consistently at scale. The politics of local health system distribution in resource-constrained settings are notoriously challenging. The Fleming Fund’s contribution to sustainability is likely to remain limited without significant improvement in terms of demand-led institutional partnership for AMR surveillance with genuine national government counterpart institutional prioritisation of the AMR agenda.

Fleming Fund contribution to these drivers at the international level

Finding 2.2.11: For changes in reporting to GLASS, the Fleming Fund has contributed to most but not all key drivers of data sharing in all countries, albeit with less significance than Fleming Fund’s contribution to changes in data availability (as shown in Table 7). The Fleming Fund has made a more significant contribution to progress in countries that reported some change, and less in countries where limited or no change has been reported so far. It also appears that the Fleming Fund’s contribution to international data sharing has been less significant than its contribution to increasing the quantity and quality of AMR data. Nonetheless, the Fleming Fund has made a vital or important contribution to data supply in nine out of 16 countries (56%).

Finding 2.2.12: For reporting to WOAH, the Fleming Fund has contributed to some drivers of data sharing in some countries, with the limited contribution understandable given that this was not an area of focus for phase 1. The Fleming Fund appears to have made a vital or important contribution to data sharing processes and systems for AMU reporting (as a driver of reporting to WOAH) in at least eight out of 16 countries (50%) and to the availability of more and better AMU AH data in six of the 16

Examples of the Fleming Fund’s contribution to international-level use

Fellowships: All countries had Fellowships focused on AMC/U. In some countries, Fellows were able to support efforts to ensure the availability and analysis of relevant data for reporting to WOAH, e.g. in Zambia.

Regional Grants on retrospective data collection (CAPTURA and MAAP) were intended to contribute to use through:

- ensuring dissemination of data

- improving local capacity to collect and use data

- improving awareness, advocacy and policy.

The RADAAR grant was expected to:

- identify bottlenecks around data sharing for regional analysis

- develop plans to improve data sharing and analysis, increase the demand for data and promote uptake of regional policy analysis.

countries (37.5%) all of which have shown some positive change in reporting to WOAH.

Table 7: Changes in data sharing with GLASS

| Countries | Extent of change | Data supply | TA | Data sharing processes | Resourcing / human capacity | Incentives | Other |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Bhutan |  |  |  |  |  |  |  |
| Indonesia |  |  |  |  |  |  |  |
| Nepal |  |  |  |  |  |  |  |
| Pakistan |  |  |  |  |  |  |  |
| Tanzania |  |  |  |  |  |  |  |
| Timor-Leste |  |  |  |  |  |  |  |
| Uganda |  |  |  |  |  |  |  |
| Bangladesh |  |  |  |  |  |  |  |
| Kenya |  |  |  |  |  |  |  |
| Laos |  |  |  |  |  |  |  |
| Zambia |  |  |  |  |  |  |  |
| Ghana |  |  |  |  |  |  |  |
| Nigeria |  |  |  |  |  |  |  |
| Senegal |  |  |  |  |  |  |  |
| Sierra Leone |  |  |  |  |  |  |  |
| Vietnam |  |  |  |  |  |  |  |

| Key: Extent of change | Key: Fleming Fund contribution |
| --- | --- |
| Considerable | Vital |
| Some | Important |
| Limited | Limited |
| Unclear | Some |
| None yet | None |

Findings on how the Fleming Fund has been designed and delivered

In the context of the decision to continue into phase 2 (see Box 3), and the emphasis placed on strategic shifts which include VfM and sustainability, in this section, we highlight the findings related to how the Fleming Fund has been implemented, with a more operational focus.

Sustainability

Key findings

2.3.1 The MA has been clear that prospects for achieving sustainability during phase 1 were limited given the starting points in most countries and limited implementation time of some grants (this is backed up by broader evidence which underlines that sustainability is hard to achieve and takes time). 2.3.2 The MA’s approach to sustainability has focused on (a) hardwiring sustainability prospects in grant design; (b) delivering success in Fleming Fund 1; and (c) increasing the focus on sustainability in CG2s. 2.3.3 This approach has limited the extent to which realistic expectations and plans have been established and actively discussed with key counterparts. 2.3.4 Based on action to date and the current status of country-level conditions, there are limited prospects for achieving sustainability in phase 1, albeit the MA’s assumption that there would be a second phase of Fleming Fund support has proven correct. Nevertheless, experience in phase 1 confirms the challenges in establishing key conditions for sustainability as identified in published literature: resources, capacity, motivation and planning. 2.3.5 For the drivers of progress on quantity and quality, the prospects for sustainability appear limited. Allocation of resources to AMR surveillance is key to sustainability but has not been a strong focus for phase 1. Some aspects of the Fleming Fund design could make securing resources more challenging – in terms of affordability, the relevance of data, and focus on the demand for AMR testing, could make prospects for resourcing more challenging in terms of equipment supply and maintenance, differentiation between HH and AH, the strength of focus on AMR data, and lack of focus on demand. Sustaining progress with capacity building and governance is challenging, relying on work at organisational and institutional levels. The MA has not focused strongly on this during phase 1.

Finding 2.3.1: The MA has been clear that prospects for achieving sustainability during phase 1 were limited given the starting points in most countries and limited implementation time of some grants (this is backed up by broader evidence which underlines that sustainability is hard to achieve and takes time). The MA set out its approach to achieving sustainability early in phase 1 and has refined and strengthened emphasis on this as implementation has progressed, including emphasising that sustainability relies on actions by a range of actors (the Fleming Fund and HMG, recipient country governments, and other donors). Given the status of AMR country surveillance systems in 2018 and the relatively short duration of most grants (particularly for RGs), the MA expressed caution about the prospects for achieving sustainability during Fleming Fund. The need to be realistic about what can be achieved and the challenges of achieving sustainability are supported by broader evidence (i.e. that it takes significant time to achieve and is challenging to do so). Furthermore, the operating context has presented some challenges – in terms of (a) the impact of COVID-19 on delivering phase 1 objectives, and (b) uncertainty around phase 2 funding (impacting the ability to make a clear case for investing in AMR surveillance). This underlines the importance of establishing clear, realistic expectations on what can be achieved.

Finding 2.3.2: The MA’s approach to sustainability has focused on (a) hardwiring sustainability prospects in grant design; (b) delivering success in Fleming Fund 1; and (c) increasing focus on sustainability in CG2s. Hardwiring sustainability in grant design, was done through a combination of (i) understanding country needs and priorities; (ii) tailoring levels of Fleming Fund support to respond to these (including available resources); and (iii) using existing country systems. The early stages of grant development (country scoping and needs assessment) helped define country needs. Grants were then designed to meet these needs, affordable within domestic resources and using country systems such as NRLs and surveillance sites. As described in section 1.4, we found that grants have generally been well aligned with national priorities, albeit with the scope for this to have been stronger. However, there is some evidence to suggest that the provision of equipment and supply of consumables has been problematic in some countries (from a sustainability perspective), as discussed in this section (2.3). Second CGs (CG2s) were initially intended to have a more explicit focus on sustainability but in practice were used to get grants back on track following disruptions due to COVID-19; however, the MA team noted that a sustainability focus was evident in some countries .

Finding 2.3.3: This approach to sustainability has limited the extent to which realistic expectations and plans have been established and to which the issue has been actively discussed with key counterparts (grantees, recipients). The MA’s operational definition of sustainability is broad and leaves open, at the portfolio level, the specification of sustainability goals. This is supplemented through the articulation of country-level sustainability assessments which inter alia indicate what will be ‘left behind’ and identify risks to sustainability and exit plans. The MA decided to take this approach on the basis that delivering success in phase 1 was the first plank in the sustainability strategy (i.e. failure to deliver would both limit what needed to be sustained and undermine relationships that are key to delivering sustainability). Sustainability assessments were intended to be revised on an annual basis. During evaluation data collection in mid-2022, we found neither evidence that updates of the sustainability plans had affected what was delivered, nor that they had been used to engage with country level stakeholders on sustainability and how it might be achieved. Furthermore, sustainability/exit plans were either not in place or were under development in all countries, with less progress in this regard in the AH sector (as set out in Vol. II, Annex 10, Tables 42–44). This raises questions on their utility given that most grants had less than six months of implementation left and so had limited time to both identify key issues and agree on solutions with in-country partners. Limitations in the degree to which the MA implemented its own approach are therefore evident albeit progress has been made in developing capacity and motivation. Less progress has been made in terms of securing the necessary future resources, and in AH, than in HH.

Finding 2.3.4: Based on action to date and the current status of country-level conditions, there are limited prospects for achieving sustainability in phase 1, albeit the MA’s assumption that there would be a second phase of Fleming Fund support has proven correct. Nevertheless, experience in phase 1 confirms the challenges in establishing key conditions for sustainability as identified in published literature: resources, capacity, motivation, and planning. Leaving aside questions on the degree to which the MA implemented its intended approach to sustainability, the MA’s approach diverged from what is generally seen as good practice in delivering sustainability. The consistent message in the broader literature is that sustainability needs to be a priority focus from the start and managed for actively through implementation to ensure key conditions are in place. We discuss three of these key conditions in turn below:

The prospects for putting in place sufficient (non-Fleming Fund) resources to sustain Fleming Fund results seem limited – although the situation is marginally better in HH than AH. Assessing prospects for resourcing is not easy, as decisions to allocate resources to laboratory services are often made by facility management rather than by ministries of health; further, in those countries with decentralised systems  the financing of healthcare is often devolved, and in other countries, the costs may (or may not) be covered by health insurance schemes . This has implications for Fleming Fund’s sustainability strategies. As set out in Vol. II, Annex 10, Table 43, in HH there is evidence of partial resourcing of relevant functions in 10 out of 16 countries (63%), but with limited expectations for change during 2022; in AH currently six out of 16 (38%) countries are providing partial support, and this is expected to increase to eight out of 16 (50%) by the end of 2022.

Sufficient capacity appears to be in place in some countries for HH (but none for AH) and partially in place for more countries in HH and AH. Respondents reported that in three out of the 16 countries (18%) there is sufficient capacity in HH in place, and partially in place in 10 of the 16 countries (63%). For AH, no countries reported having sufficient capacity in place, but 11 out of 16 (69%) reported having partial capacity in place. Several countries expect reverses in capacity, potentially linked to staff turnover and or staff not being on permanent contracts, which highlights the challenge (discussed below) that establishing capacity to maintain either AMR functions or the benefits delivered through AMR surveillance is a dynamic challenge and requires consideration of upstream (e.g. supply) issues relating to capacity.

Staff motivation to continue functions related to AMR is currently fair, although with some concerns about future trends in both HH and AH. Respondents reported that, for HH, five out of 16 countries (31%) noted that staff were sufficiently motivated to undertake their AMR functions, with 10 out of 16 (63%) partially motivated and one highlighting concerns around a lack of motivation. In AH, three out of 16 countries (18%) noted adequate motivation, eight out of 16 (50%) partially sufficient motivation, and four out of 16 (25%) with concerns. This could reflect the status of Fleming Fund implementation, with staff feeling positive following the recent renovation of laboratories and provision of new equipment. In one country, respondents expected motivation to increase in HH, and six countries reported that motivation looked set to lessen over time; for AH, four countries expected progress and seven expected challenges. Similar to capacity, it is important to see motivation as dynamic and requiring the consideration of upstream issues to ensure motivation is sustained.

Finding 2.3.5: For the drivers of progress on quantity and quality, the prospects for sustainability appear limited. Allocation of resources to AMR surveillance is key to sustainability but has not been a strong focus for phase 1. Some aspects of the Fleming Fund design could make securing resources more challenging – in terms of affordability, the relevance of data, and focus on the demand for AMR testing, could make prospects for resourcing more challenging in terms of equipment supply and maintenance, differentiation between HH and AH, the strength of focus on AMR data, and lack of focus on demand. Sustaining progress with capacity building and governance is challenging, relying on work at organisational and institutional levels. The MA has not focused strongly on this during phase 1.

Renovation, equipment and consumables

A significant focus of the Fleming Fund has been the renovation of a large number of laboratories and ensuring they are appropriately equipped. Whether laboratories are maintained to the standards that the Fleming Fund has refurbished them, and equipment procured by the Fleming Fund is maintained, depends on a combination of resources and management. The challenge is that relevant budget holders lie at multiple levels ranging from within an individual facility to the national level, so resource sustainability relies on prioritisation from multiple managers and committees that each have their own priorities, budget constraints and priorities. Securing financial commitments to maintain these investments across the range of relevant budget holders has not been a strong focus for phase 1, while some aspects of the Fleming Fund design could make prospects for resourcing more challenging.

Some aspects of the Fleming Fund design, in terms of affordability, the relevance of data, and focus on the demand for AMR testing, could make prospects for resourcing more challenging:

Affordability of both maintenance services and consumables needed to run the equipment. The Fleming Fund approach was to put in place maintenance contracts for five of the eight main pieces of equipment and cover the cost of reagents, media and consumables (which were assumed to be in the region of 20% of the cost of laboratory requirements). Some countries  have allocated resources to cover (some of) these costs but indications in other countries  are that this could be a challenge for countries to pay for. For example, KIIs in Laos reported that yearly servicing for MALDI-toff equipment is around US$35,000, compared with a total NRL annual budget of US$26,000. The Fleming Fund’s emphasis on the automation of microbiology processes, particularly where adequate, less expensive alternatives exist, is also a potential risk to sustainability (see Box 8). Financing of consumables, reagents and equipment is also a sustainability risk that needs further consideration going forward, including for example, whether co-financing agreements could be put in place, and whether it is realistic to expect governments to pay for AMR services in resource-constrained settings, particularly if the benefits are essentially a global public good.

Box 8: Material differences between AH and HH sectors

The main driver for incorporating AH and other non-HH sectors into the Fleming Fund is to address AMR as a HH problem. This is underlined by the focus in AH on (GLASS) pathogens that are more important in terms of human rather than AH. The HH-focused goals of the Fleming Fund are clear in the ToC but the implications of these have not been sufficiently understood and articulated. There are key elements of AH that have a material impact on how surveillance is structured: Priority pathogens differ in AH: focusing on GLASS pathogens reduces incentives for farmers and vets to use laboratory services. Demand or throughput are also affected by commercial sensitivities which are not (less of) an issue in the HH sector. Access to diagnostic services differs: in AH, farmers bring vets to animals which is different from HH where patients come to visit doctors. This means that passive surveillance in AH is not used. Private sector provision is more important than government provision: in many countries, there are few government vets, and private sector provision is significant. The implication is that any data on AMR is not necessarily shared in national surveillance systems. AH surveillance focuses on active surveillance, yet this is more expensive per isolate than passive surveillance, and challenging to sustain. The strategy on AH surveillance and One Health requires more detailed thought and discussion between the MA and DHSC, yet the Fleming Fund team does not have specific expertise on AH to engage on this topic. The key strategic questions are: What is the purpose of One Health? Is this best advanced through surveillance or research? How to incentivise farmers to use the laboratory services required? What pathogens should AH focus on? Does the current AH approach maximise VfM?

Limited differentiation in the support provided to HH and AH sectors. While the MA has appropriately focused on active surveillance within the AH sector, it is not clear that the strategy is sufficiently tailored to AH and active surveillance. Box 1 described the requirements for active and passive surveillance; in principle, less laboratory capacity is needed for active than for passive surveillance because the throughput of data in active surveillance is predictable by design. There is some logic to establishing multiple sites to support active surveillance, e.g. where the national strategy combines active and passive surveillance  or where country size and governance structures require it (i.e. decentralised or not), or where geography makes transportation of samples to NRLs challenging. In the majority of countries, the Fleming Fund is supporting fewer sites in AH than in HH. However, substantially fewer surveillance sites are needed in the AH sector. The MA approach risks that the cost of sustaining AMR surveillance in AH is higher than it needs to be. As described in Box 9, if the logic is to build capacity that can be used as the basis for future passive surveillance, there is a separate risk that the Fleming Fund builds capacity in the government system when there is more demand/throughput through private sector laboratories, which are not compelled to share data as a basis for national surveillance. The approach in phase 1 has built foundations in AH, and there is a gap in a more explicit, differentiated approach for AH (including specifying how risk factors would be managed for active surveillance).

Limited focus on AMC/U, especially in AH. The rationale for the creation of the Fleming Fund emphasises the generation of AMR surveillance data as the basis for increasing awareness, understanding and action on AMR. The MA noted that, at the time of the launch of the Fleming Fund, limited agreement existed on protocols for AMC/U and consequently there was less focus on AMC/U in the Fleming Fund MA ToR. And yet, as discussed in section 2.2, emerging examples of data use in AH rely more on AMC/U data. The risk is that this creates inefficiencies in the system, prioritising the generation of types of data that are ultimately not needed or valued by decision-makers in the AH sector.

Lack of focus on demand. Linked to the above, there is the risk that the laboratory capacity built/strengthened is not aligned with demand or use. The Fleming Fund has, in the earlier stages of phase 1, placed limited emphasis on strengthening demand for AST testing. It is plausible that the MA has identified the capacity to deliver credible AST testing (supply) as the primary obstacle at this stage, or a prerequisite before focusing on demand, but this was not made explicit and underpinned by evidence. This risked missing opportunities to increase throughput at the facility level further; although we note that the Fleming Fund has supported the provision of free testing, and removed cost as a key obstacle to demand.

Box 9: Use of automation to improve quality

The Fleming Fund has made substantial investments in procuring hi-tech laboratory equipment to support routine, standardised AMR testing, as a key pathway to improve quality. This has been complemented by investment in the training of laboratory staff. The MA has made efforts to supply equipment that meets identified needs at competitive prices (see section 2.3).

Automation can play an important role in improving the quantity and quality of AMR testing, particularly for blood cultures. However, creating dependencies on automated equipment comes with risks to sustainability that can be challenging to manage. Ongoing costs associated with equipment include maintenance, cost of consumables, and depreciation/cost of replacement. The Fleming Fund has, during phase 1, taken steps to mitigate against these risks but there are examples, particularly at the transition between Fleming Fund grants, where countries have been unable or unwilling to pick up associated costs.

For some of the microbiology processes that the Fleming Fund is supporting, there are alternative (manual) methods that do not rely on equipment and do not create contingent liabilities. Examples from phase 1 of equipment not being used as intended underline the importance of careful consideration in the supply of equipment as part of an agreed, sustainability strategy.

Capacity building and governance

Finding 2.3.6: Sustaining progress with capacity building and governance is also challenging, relying on work at organisational and institutional levels. The MA has not focused strongly on this during phase 1. Many countries and MA sustainability assessments have identified staff turnover as a threat to the sustainability of capacity within the laboratory workforce. The MA seeks to address this partly through using the Fleming Fellows to cascade training throughout the system in each country (see Box 10). However, the MA has had limited engagement with the upstream supply of training through national systems, with suggestions that it is outside its remit to work at organisational/institutional levels. As such, turnover remains a risk to the sustainability of Fleming Fund’s capacity-building results and the results that rely on this capacity. There are some ongoing examples of attempts to address this at the country and regional level (e.g. the ASLM grant).

Box 10: Examples of Fleming Fund efforts to strengthen sustainability

CGs were designed with sustainability in mind, although as discussed in this section (2.3), have focused more during phase 1 on delivering results that can be sustained in due course. RGs provide a range of examples of how sustainability has been actively pursued: - The RG1 grant on retrospective data collection (CAPTURA) has approached WHO Collaborating Centre for Drug Statistics and Methodology in Oslo. RG1 could leverage discussions to get a formal endorsement by WHO South-East Asia Regional Office/Western Pacific Regional Office; the MAAP project identified nodal persons or champions who can cascade within the country, based in ministries of Health – one for pharmacy for AMC, one for laboratories for AMR. - The RG2 grant on whole genome sequencing (SEQAfrica) focused on establishing its reputation, building relationships with Africa Centres for Disease Control and Prevention, African Society for Laboratory Medicine and Pasteur Institute, developing differentiation within its laboratory networks (e.g. regional sites as referrals, sentinel sites to focus on specific pathogens) and seeking funds from other donors. - EQA grants in Africa and Asia have identified the importance of advocacy to encourage laboratories to pay for EQA services; and worked with regional EQA providers to develop business plans with short, medium and long-term goals, although considering that EQA is not sustainable within next five years. - The RG2 grant on regional training has used a range of approaches, including incorporating their training material in the existing curriculum , running a master-trainer course to deliver the same materials to others, setting up mentorship at regional and country levels. The Fleming Fellowships Scheme’s main aim was to build the individual capacity of Fellows with an expectation that this would equate to increased capacity for their institutions. The extent to which Fellows transferred their knowledge to their colleagues or even saw that as one of their responsibilities, however, was variable. A train-the-trainer model was not systematically applied across the board. Moreover, data to assess the scheme’s contribution to results beyond the implementation of their Fellowship activity is scarce.

Similarly, for AMR governance, experience suggests that the routine functioning of AMRCCs cannot be assumed, and yet governance structures decide on important drivers of AMR data quantity and quality, such as the purpose and scope of surveillance systems (number of sites, priority pathogens). Maintaining newly established AMR governance structures is influenced by political commitment. AMRCCs are not institutionalised and often lack a clear ‘home’ within the government system due to their cross-sectoral composition. The Fleming Fund has, during phase 1, maintained a technical focus, and engaging in political concerns was not the focus of the MA (although less so for HMG and its broader diplomatic network, even if the DHSC’s lack of in-country presence and relatively small UK-based team is limited in its capacity for country-level influence). However, the lack of emphasis on politics represents an ongoing risk to the sustainability of Fleming Fund results.

Value for money

In this section we present a summary analysis of the extent to which Fleming Fund results offer VfM. We look first at whether VfM has been delivered in terms of economy, efficiency and effectiveness. Next, we look at the systems that the MA has put in place to manage VfM. Detailed analysis is presented in Vol. II, Annex 6.

Key findings

2.3.7 In narrow terms (economy, efficiency) there is evidence of VfM having been delivered. But in terms of effectiveness (as defined by OECD) the case is less clear. 2.3.8 Economy: There is evidence of significant cost savings delivered by the MA, underpinned by strong systems to manage budgets and expenditures; performance is comparable to similar programmes. 2.3.9 Efficiency: delivering efficiently has been challenging in the context, and with the operational model that has been chosen, which affects VfM in terms of internal and external coherence, as well as management overheads. Efficiency has also been challenging to track given the focus on reporting implementation rates and the lack of a link between financial reporting and outputs; this seems to be driven by systems and cultures within DHSC. There is some evidence that the value of leveraged resources is reasonably significant in some grants (>5% of grant value in Timor-Leste and Laos). However, this indicator has not been reported or consistently tracked across all grants. The alignment between Fleming Fund expenditure, contribution, and progress in generating quality AMR data was found to be high, suggesting a positive outcome in terms of VfM. 2.3.10 Effectiveness: Overall there is evidence across the 16 countries in our sample that the Fleming Fund has contributed to improvements in establishing surveillance systems and data use. The headline finding varies slightly when we look at HH, AH, and data use separately. The category of the country (level of surveillance system in place at the start of the grant) does not seem to be related to performance. However, there is alignment between the length of grant implementation and performance – i.e. the longer the grant has been running the more change and contribution seen 2.3.11 Coherence: The model has created challenges in terms of delivering internal coherence between CGs, RGs, and Fellowships. External coherence between all Fleming Fund grants and other DPs interventions was found to be strong in a majority of the focus countries but does not focus on linkages to wider (non-surveillance) aspects of the AMR response 2.3.12 The approach taken by DHSC and the MA to VfM generally aligns with FCDO and ICAI guidance. Overall, there are strong systems in place to manage economy and efficiency. However, the Fleming Fund has been weaker at establishing systems managing for effectiveness. In spite of some existing and planned adaptations to strengthen in this area, and Fleming Fund experience is not uncommon compared with other equivalent programmes, this is a key strategic requirement for phase 2.

Measuring VfM

Finding 2.3.7: In narrow terms (economy, efficiency) there is evidence of VfM having been delivered. But in terms of effectiveness (as defined by the OECD) the case is less clear. Applying a framework to measure VfM based on the 3Es (Economy, Efficiency and Effectiveness), there is evidence of VfM being achieved at the country level to varying degrees across the grants.

##### Economy

Finding 2.3.8: Economy: There is evidence of significant cost savings delivered by the MA, underpinned by strong systems to manage budgets and expenditures; performance is comparable to similar programmes. Savings of around £2.3 million were made on negotiating central procurement. The DHSC and MA reviewed detailed budgets and negotiated savings during the set-up of the grants’ contracts; during implementation, 19 out of 25 CGs and RGs in our sample reported savings. 11 grants reported savings of between 2% and 10% of the total spend, a level that benchmarks well to similar programmes. There is evidence that where higher levels of savings were reported (RG F55 and Kenya CG savings were over 25%), which may have been due to initial over-budgeting.

##### Efficiency

Finding 2.3.9: Efficiency: Delivering efficiently has been challenging in the context, and with the operational model that has been chosen, which affects VfM in terms of internal and external coherence, as well as management overheads. Efficiency has also been challenging to track given the focus on reporting implementation rates and the lack of a link between financial reporting and outputs; this seems to be driven by systems and cultures within DHSC. There is some evidence that the value of leveraged resources is reasonably significant in some grants . However, this indicator has not been reported or consistently tracked across all grants. The alignment between Fleming Fund expenditure, contribution and progress in generating quality AMR data was found to be high, suggesting a positive outcome in terms of VfM.

Delivering efficiently has been challenging in this context, and with the operational model that has been chosen, which affects VfM in terms of internal and external coherence, as well as management overheads. The Fleming Fund’s operational model and ecosystem are complex. The Fleming Fund is by design a complex multi-country, multi-partners grant-based programme with an extensive network of grantees at global, regional and country levels. On top of the three streams managed by the MA and directly in the scope of this evaluation, DHSC has directly funded a multitude of other organisations/ projects such as WHO, FAO, WOAH, ODI, South Centre, FIND, Global Research on Antimicrobial Resistance and CWPAMS among others. Virtually all these grantees have sought to establish relationships at the country level, increasing the risk of high transaction costs for national stakeholders as well as potential fragmentation and duplication. The MA has recognised that, ‘In some instances, there were five or more Fleming-funded projects working in any given country, which led to confusion on the part of government and recipient counterparts and had the potential for duplication of effort’. This model results in overheads (budget and actual) that are higher than in similar grant programmes. This may be due to the way overheads are being defined which includes both indirect costs, and management and overheads. In terms of actual overheads, these can be higher than expected due to implementation delays (as discussed in section 1.4). However, there is also evidence that even budgeted overhead costs are high in some countries . Across CGs and RGs, average overheads were 27% during the implementation phase, which is higher than similar grant programmes, but within the 30% threshold agreed upon for the programme.

Efficiency has also been challenging to track given the focus on reporting implementation rates and the lack of a link between financial reporting and outputs; this seems to be driven by systems and cultures within the DHSC. Grant reporting is set up to track budget and activity implementation rates. Monitoring grant performance of activity and budget implementation rates does not facilitate tracking efficiency at the output level. Financial reporting has been set up to record expenditure by investment area; however, this has not been used routinely to track progress. Placing performance measures at the activity level, some of which are linked to payment by DHSC, also risks prioritising the implementation of activities rather than the achievement of results. It may also explain why the MA adaptive management approaches tend to focus on workplan adaptations to improve budget absorption rather than adapting activities and outputs to lead to improved outcomes. As discussed in , a combination of systems-related and contextual factors appear to have driven the DHSC’s focus at this level.

There is evidence that the value of leveraged resources is reasonably significant in some grants . However, this indicator has not been reported or consistently tracked across all grants in the MA’s VfM grant reviews. This indicator helps to demonstrate alignment with existing resources and whether the grants set-up take into account other programmes operating in the same area. It may also indicate sustainability if the resources leveraged are from the country’s existing health budgets. Designed well, this indicator could have been a good measure of coherence and sustainability.

In general, we found there was a high degree of alignment between the profile of Fleming Fund investments and the strength of drivers, i.e. that the Fleming Fund had invested in areas that evidence suggests were important drivers of the progress reported in sections 2.1 and 2.2. We looked at investments compared with changes presented in sections 2.1 and 2.2. In practice, there are some limitations to this analysis: (1) a high proportion (45%) of CG investments recorded as cross-cutting and not assigned to a specific investment area (ranges from 10% to 70% across CGs); 2) not all contribution drivers can be mapped to the investment area, so we look only at the main drivers, i.e. Human capacity; Renovation and Equipment; and Governance which can be mapped to investment areas; and 3) there is no expectation of a linear relationship between the level of investment and observed changes.

In general, this analysis showed a high degree of alignment between the level of investments and the strength of drivers, as shown in Vol. II, Annex 6. For example, in countries where there was a higher level of investment in Laboratory infrastructure, renovation was one of the stronger drivers.

In general, investments in building foundations for the use of data are aligned with performance i.e. there was a lower investment in countries reporting a lower level of progress and Fleming Fund’s contribution, and higher performing countries had a relatively higher investment in this area.

Box 11: DHSC systems for managing international ODA programmes

Government departments have different cultures and systems that have evolved to work in specific contexts and meet specific objectives. The DHSC systems are primarily designed to ensure the effective design and implementation of UK domestic health policy. Since 2015, the DHSC has also managed ODA which has introduced new DHSC requirements in terms of working internationally and managing associated risks. Key challenges that come from the application of domestically focused systems include: Budgeting: DHSC budgeting is done on a three-year rather than a longer-term basis. This limits the extent to which long-term plans can be made. Financial expenditure: DHSC budgets for each financial year need to be spent as fully as possible or funds are ‘lost’ – i.e. they cannot be rolled over into subsequent years. Incentives are for the DHSC to be a good ‘spender’ which means ‘savings’ have to be reprogrammed. This is distinct from FCDO which has derogation to carry over expenditure from year to year. Risk appetite: DHSC systems are set up to work in the UK domestic context where risks are different and, on the whole, lower than in international contexts. This has implications for contracting and limits the scope for strategic adaptive management that is needed for novel programmes like the Fleming Fund, and in particular when working in uncertain environments. Contracting: DHSC contracting is more used to procuring the supply of specific services or outputs which can be easily defined and less likely to change during implementation. Systems do not appear sufficiently agile to facilitate strategic adaptive management, e.g. changes to contracted outputs or targets revised to meet changing circumstances. Culture and ambition: The DHSC recognises that tackling AMR is a long-term project and that its stated objectives are unlikely to be achieved even by the end of phase 2. Further support, either extending phase 2 or through a new Phase 3 is anticipated. Future funding will in part require the DHSC to show that funding has been used effectively and that the DHSC is a reliable spender. This imperative is more acute in the context of cross-Whitehall spending pressures including on ODA budgets in the context of the Ukraine war.

##### Effectiveness

Finding 2.3.10: Effectiveness: Overall there is evidence across the 16 countries in our sample that the Fleming Fund has contributed to improvements in establishing surveillance systems and data use. The headline finding varies slightly when we look at HH, AH, and data use separately. The category of the country (level of surveillance system in place at the start of the grant) does not seem to be related to performance. However, there is alignment between the length of grant implementation and performance – i.e. the longer the grant has been running the more change and contribution seen.

Overall, there is evidence, across the 16 countries in our sample, that the Fleming Fund has contributed to improvements in establishing surveillance systems and data use. KPI data show steady progress in the number of Fleming Fund-supported HH and AH surveillance sites showing progress through the LSHTM roadmap functions/stages. In 2019, 23 HH sites were making progress, which had increased to 118 by mid-2022; equivalent figures for AH sites were 47 in 2020 up to 51 by mid-2022 (see Figure 12 and Figure 13 for details). There is evidence that the Fleming Fund has been particularly effective in five countries ; and in its contribution to improvements in seven countries . However, there is evidence of fewer contributions and improvements in four countries ; although we note findings in section 2.1 that show that progress was expected to have continued in the remainder of phase 1 and the availability of evidence was influenced by the specific timing of our data collection efforts in each country.

The headline finding varies slightly when we look at HH, AH, and Use separately. For example, some countries performed better in HH and Use than in AH. This is as expected as the AH data used is specifically AMC/U data, which was less of a focus in the current phase.

The category of the country (level of surveillance system in place at the start of the grant) does not seem to be related to performance. For example, countries with systems established (category C: Countries where modest surveillance system is established, gaps need to be filled and activities need to be connected) appear at higher  and lower  ends of performance ranking. However, Sierra Leone was rated category A (Countries with the least capacity to conduct surveillance, typically have no NAPs in place and little evidence of political will) and performed least well.

There is a general alignment between the length of grant implementation and performance. Where alignment is not strong, the explanations are clear. However, there are likely to be other factors that explain differences in performance between the CGs.

##### Coherence

Finding 2.3.11: Coherence: The model has created challenges in terms of delivering internal coherence between CGs, RGs, and Fellowships. External coherence between all Fleming Fund grants and other DPs interventions was found to be strong in a majority of the focus countries but does not focus on linkages to wider (non-surveillance) aspects of the AMR response

Internal coherence

The model also created challenges in terms of delivering internal coherence between CGs, RGs and Fellowships, with internal coherence found to be strong in seven countries, medium in seven others, and poor in the remaining two. As already highlighted under efficiency, the Fleming Fund operational model and ecosystem are complex and achieving internal coherence in this context has proved challenging. Based on our cross-country analysis of findings generated through our third round of country -level data collection (presented in Vol. II, Annex 24), internal coherence was rated as strong in seven of the 16 countries , medium in another seven , and as poor in the remaining two . Collaboration and alignment seem to have worked better between some RGs and CGs with multiple examples of joint activities and avoiding duplications, although awareness of RGs at the country level remains sometimes low. Collaboration and alignment between Fellowships and CGs appear to have been more problematic, with Fellowships and CGs sometimes happening ‘in parallel’. Evidence from our country-level data collection shows that in-country awareness of/interactions with Global Projects was also reported as low.

Challenges in achieving internal coherence have been compounded by several design, management and contextual factors. Based on evidence from country as well as global-level KIIs, as well as our observation of the programme through its entire phase 1 implementation, several design features made achieving internal coherence more difficult; these include: (1) the MA’s decision to avoid interdependencies between grants (to avoid one grant delaying the implementation of another) which led to challenges of sequencing in grant implementation between CGs, RGs, and Fellowships; (2) the fact that the Fellowships have always been conceived as individual rather than organisational capacity strengthening activities; and (3) the decision not to develop a country-level ToC in each country to articulate how each grant was supposed to contribute to joint country-level objectives. This was exacerbated by some aspects of the management of the grants portfolio: Fellowships and RGs were managed directly by the MA team in London while CGs reported to regional teams, some grants (the Global Projects) were managed directly by the DHSC, which also had to contract UN agencies directly when these were lead of CG consortia (rather than the MA doing this); there was also extensive use of sub-contracting within some CG/RG consortia. Furthermore, HIs did not have direct leverage on beneficiary institutions in which Fellows worked, and there was a lack of clarity regarding whether it was the MA’s or HI’s responsibility to liaise with beneficiary institutions. These arrangements were made more complicated, as described in Box 6, by operational constraints required by COVID-19 restrictions – such as the inability of many grantees (including mentors from HIs) and the MA to travel, and the additional workload HH Fellows had to bear due to the pandemic.

Over the years, efforts have been made by the DHSC and the MA to increase coherence and coordination among the various partners and funding streams. The MA was not originally explicitly mandated or resourced to ensure coordination among all Fleming Fund grants at the country level, and the DHSC was not resourced to do so either. Responding to the need to strengthen coordination, the DHSC created a DP Portal with key information on the activities of all grantees; and developed a portfolio-level ToC to clarify expected contributions from each Fleming Fund grantee. In 2020, at the DHSC’s request, the MA country grantees started to convene regular country coordination meetings including Fleming Fund grantees and other key AMR stakeholders. According to participants and observations by the evaluation team, these proved to be a good mechanism to bring representatives of various grants together and for information sharing.

However, the bases for true coordination and collaboration are still missing. Country coordination meetings were not in themselves sufficient to ensure internal coherence. KIs and observations by the evaluation team highlighted that these were too short, infrequent (as happening on a quarterly basis), and included too many participants (and with inconsistent stakeholder participation across meetings) to consistently ensure synergies and avoid duplications. Moreover, there was no/limited joint work planning and only limited sharing of workplans between different grants (including Global Projects) while annual reviews were happening in isolation rather than jointly measuring success against country-level objectives.

This has likely led to some missed opportunities to enhance synergy. The complex set-up and decisions just described probably led to some missed opportunities (in terms of linkages to other relevant agendas) and potential synergies/efficiencies remaining untapped. Although duplications seem to have been largely avoided, some opportunities for synergies/efficiencies also remained untapped; these included, for instance, sharing of training materials/courses/learning among HIs for more joint training between different grants and for further leveraging of RGs and Fellowships to contribute to country-level objectives.

External coherence

The MA-managed Fleming Fund investments have generally been well aligned with national priorities. According to evidence gathered through our country-level data collection, in 12 out of the 16 focus countries (75%) alignment with governments’ plans and priorities, and with the AMR surveillance objective in AMR NAPs, was strong, with the Fleming Fund often being the main or only funder of NAP activities. Main enablers cited by KIs for strong alignment included thorough consultations and assessments conducted by the MA during scoping and positioning activities, the alignment of grant proposals with NAPs, close collaboration/frequent meetings between the Fleming Fund Country Grantee and the government, and joint work on AMR-related policies and plans.

On some occasions, however, alignment with government systems and long-term needs could have been stronger. In four out of 16 countries (25%), alignment was rated as medium. These ratings are associated with reports of the Fleming Fund having on some occasions worked outside existing government structures , or of equipment not always being utilised/relevant/affordable after Fleming Fund support ended  or of national stakeholders not feeling complete ownership/access to the data . Limited attention to defining specific strategic outcomes or targets with national governments (beyond alignment with NAPs and agreement of request for proposals), and lack of joint reviews of performance with governments may have led to an operational focus on AMR surveillance and potentially missed opportunities to strengthen ownership and effectiveness.

External coherence between all Fleming Fund grants and other DP interventions was found to be strong in most of the focus countries. As shown in Vol. II, Annex 24, in 10 of the 16 countries (62%) external coherence was rated as strong, with good examples of collaborations and alignment with the work of other DPs, while in the other five (18%) – it was rated as medium. Coordination was generally reported as strong with WHO and FAO country offices, with some examples of collaboration around point prevalence surveys. In some cases, however, communication, especially with WHO country offices, could have been stronger. Coordination was reported as slightly more challenging with bilateral actors such as US CDCs and the United States Agency for International Development (USAID). Unsurprisingly, external coherence appears stronger when the number of players involved is more limited (e.g. Bhutan where the Fleming Fund is the only donor in this space), the same partners receive funds from multiple donors  and when they are already used/ structured to coordinate themselves/are already familiar with each other .

External coherence and coordination are hard to achieve, more so in the AMR space. Achieving external coherence depends on many factors outside of the control of one programme. Ultimately, this should be the responsibility of a strong AMRCC, although experience suggests this is not always a realistic assumption (especially as some of them have not been meeting regularly, also due to the pandemic). Moreover, AMRCCs are by their nature cross-sectoral coordinating mechanisms while binding decisions are taken within each ministry.

Managing for VfM

Finding 2.3.12: The approach taken by DHSC and the MA to VfM generally aligns with FCDO and ICAI guidance. Overall, there are strong systems in place to manage economy and efficiency. However, the Fleming Fund has been weaker at establishing systems managing for effectiveness. In spite of some existing and planned adaptations to strengthen in this area, and Fleming Fund experience is not uncommon compared with other equivalent programmes, this is a key strategic requirement for phase 2.

The approach taken by the DHSC and the MA to VfM generally aligns with FCDO and ICAI guidance for efficiency and economy but less so for effectiveness. This entails embedding VfM considerations into management processes and establishing metrics to track performance.

Overall, there are strong systems in place to manage economy and efficiency. This is evidenced by performance against VfM measures reported above and in VfM grant reviews. The MA has put in place processes to manage economy and efficiency of activity implementation. This means savings have been made at the set-up (e.g. contract negotiations) and implementation stages through routine review of unit costs and expenditures. Some grantees noted these processes were burdensome and others describe them as expected for this type of grant. By setting up standard processes which are suitable for a range of grantees (government, non-government, commercial contractors), the MA has provided some assurances on the use of resources. However, this leads to some constraints including on adaptive management at the output and outcome levels. Grant activities have been planned, reviewed, revised and completed with support provided by the regional teams. While there have been delays in implementation (as discussed in section 1.4), budgets have been reprogrammed with 39 no-cost extensions agreed upon in CGs and RGs.

However, the Fleming Fund has been weaker at establishing systems for managing for effectiveness, despite some existing and planned adaptations to strengthen this area. Fleming Fund experience is not uncommon when compared with other equivalent programmes. During the early stages of implementation, the evaluation supplier highlighted issues related to how the programme had been set up to manage for results at the (intermediate) outcome level. This gap has been a recurring theme throughout the evaluation and has formed a key part of learning and adaptation in relation to VfM. Several steps have been taken during implementation to address these issues. The MA undertook a VfM Deep Dive into Managing for Effectiveness in 2020 which identified the mechanisms in place (formal and informal) to manage for results and made a series of recommendations for how to strengthen this area. While many of these recommendations have not been addressed during phase 1, some are being considered for implementation in phase 2, e.g. agreeing on output level indicators, focusing monitoring at the output (rather than activity) level, and formalising a monitoring, evaluation, and learning strategy. Other recommendations have not yet been implemented that would strengthen the MA’s approach to tracking and delivering VfM, such as an output quality review framework to ensure a standard approach across grants; and including outputs within the grants for government commitments/budgeting for the procurement of reagents, consumables and maintenance and implementing (see Vol. II Annex 6 for more details). The Managing for Effectiveness VfM Review also included a review of progress through the ToC in four case study countries, which presented performance on outputs and quality of outputs in a level of detail not seen in the quarterly and annual reviews.

Conclusions

Conclusions focus on the strengths and weaknesses of a programme in meeting its objectives. In the absence of a clear articulation in phase 1, we have used those from the phase 2 Business Case where the Fleming Fund’s higher-level objectives are defined in terms of HH goals. Objectives related to AH and One Health are defined as a means to achieving objectives related to HH.

Phase 1 has mainly focused on supporting 23 LMICs to develop and sustain national programmes for the surveillance of AMR and AMU. Findings related to the challenge of contributing to higher-level objectives have mostly fallen under findings related to data use. As discussed earlier in the report, the findings above have mainly been focused on what has happened in the first phase of the Fleming Fund in 16 out of 23 countries. While specifics may vary in the remaining seven countries, where we did not collect data due to a combination of the level of resources available to the evaluation and status of implementation and likely observable results, we are confident that their exclusion has not significantly affected the robustness of the conclusions below.

We present two groups of conclusions: (1) in relation to the current programme design to support LMICs develop and sustain national AMR/U surveillance programmes (which remains a key priority for phase 2 of the Fleming Fund); (2) in relation to longer-term objectives in ensuring AMR is prioritised by policymakers and other stakeholders, which the Business Case for phase 2 states as:

To ensure AMR is prioritised, key international, national, and local stakeholders need to have evidence of both the trends of resistance and the impact that this is having on the health of their populations or, importantly, the efficacy of the medicines they are buying.

AMR has rarely been seen as a top priority issue by policymakers, clinicians or by the aid organisations working in LMICs. Although the Fleming Fund has improved, the amount of data available on AMR surveillance takes time and requires resources to become embedded. AMR may get lost amidst the other, more immediately obvious priorities to decision makers who may not receive AMR data on a regular basis. Treatment failure is common, but often not ascribed to AMR, and disentangling the cause between poor diagnosis, poor care, substandard drugs, comorbidities, and AMR (or a combination of all), is almost impossible.

Strengths and weaknesses of the current programme design in terms of supporting low- and middle-income countries to develop and sustain national programmes for surveillance of AMR and AMU.

Progress towards strategic goals

Conclusion 1: During phase 1, the Fleming Fund has made significant progress in supporting countries to develop foundations for national AMR and AMU surveillance programmes. Laboratory functions have been strengthened compared to international norms, capacities of key members of the laboratory workforce have been strengthened, and surveillance functions have been established in some countries. Broadly, within this narrow focus on building foundations, phase 1 has achieved what was agreed upon between the MA and the DHSC. We highlight some key achievements below using the investment types which have underpinned the MA design:

Laboratory infrastructure enhancement. The Fleming Fund has contributed to establishing the building blocks for AMR testing in all of our focus countries, albeit with substantial (expected) variation across and within countries; the Fleming Fund has played a key role in driving the increase in the quantity of HH and AH data but more varied on whether it has driven an increase in quality of data.

Human resource strengthening and workforce reforms. The Fleming Fund has contributed towards building a workforce with the skills required to do quality AMR testing, and to provide leadership and oversight of AMR surveillance through the Fleming Fellows.

Surveillance systems strengthening. The Fleming Fund has supported laying the foundations for effective One Health AMR surveillance (albeit with interesting regional variation emerging), including providing a focus on AH and One Health.

Conclusion 2: Building on these necessary foundations it is reasonable to expect that the Fleming Fund will be able to make progress towards achieving its higher-level goals for phase 2 (in terms of the use of data for clinical improvement, policy and behaviour change), providing there is a stronger focus on understanding the needs and priorities of decision-makers. However, processes to achieve these goals are inherently political, complex, unpredictable and will take time to work through. In phase 1, the AMR NAPs developed by country governments neither identified prioritised outcomes nor provided a strong framework within which the Fleming Fund could easily engage with key national stakeholders. It cannot be assumed that this will change without support to strengthen NAPs and AMRCCs. There are early indications of progress which present an opportunity to build on, including:

Building foundations for AMR surveillance data use. These outputs and activities have contributed to creating some foundations for the use of data, and while expectations in this area were limited in terms of high-level outcomes, change is starting to emerge and there are prospects for continuing progress as feedback cycles complete and Fleming Fund initiatives mature (such as the Policy Fellows).

Rational use of antimicrobial medicines. While this was also not expected to be a major focus of the Fleming Fund during phase 1, a substantial number of examples of data use at the facility level were confirmed across the evaluation focus countries (35 examples from 13 out of 16 countries), with most focusing on the use of AMC/U data rather than laboratory-derived AST data of the type prioritised in Fleming Fund phase 1. These examples suggest an encouraging picture of local data use dynamics in many Fleming Fund countries. But clearly, the examples are not necessarily representative of overall local change dynamics within a particular country. Examples were typically difficult to obtain; they were specific to local circumstances and implicitly described activities that resulted from extraordinary initiative and effort, often apparently cutting against norms in wider systems.

However, tackling AMR requires a multidimensional response – across different sectors, different types of data (AMR/C/U), and different pathogens. The nature of these complex interactions varies materially depending on the context, between and within countries. A tailored, country-specific response is therefore essential, with evidence-informed reflection and feedback as a core component.

There appears to have been limited agreement with governments on specific strategic outcomes or targets, beyond alignment with NAPs, and no joint reviews of performance were held with governments. Pressure to deliver against agreed upon budgets and workplans, which was constant after the late start of the programme and exacerbated by COVID-19, appears to have squeezed the space for both understanding countries’ demands and needs for AMR-related data and for meaningful country-specific adaptation and this is a key area of focus for phase 2.

Observations on programme design

Conclusion 3: The programme has operated during a challenging context, which will continue into phase 2. The Fleming Fund has proven flexible enough to respond effectively, even though some features of the programme design made responding more challenging. The context within which phase 1 has been implemented cannot be overlooked in interpreting the progress achieved. The majority of grants were starting to come on stream in late 2019. The COVID-19 global pandemic was subsequently announced in March 2020. This had significant implications for the implementation of the grants programme (described in section 1.5). Major consequences were that the anticipated CG1s and CG2s were not implemented in all countries, many CGs were subject to (multiple) extensions, whether on a no-cost or costed basis, and Fleming Policy Fellows were established in 14 countries with limited time to deliver (see section 1.5 and Box 6 for more details). Having key management and delivery capacity located at the regional rather than country level meant that it was not possible to implement important activities as originally planned.

Looking forward, the political and economic impacts of COVID-19 and other global factors are still emerging. These include economic disruption (global recession and inflation), supply chain issues, high LMIC indebtedness, high-income country budgetary issues, the impacts of climate and environment change, and the introduction of new technologies. A recent analysis by the World Bank suggests that per capita government health spending will decline annually in many LMICs, remaining lower than 2019 expenditures each year to 2027. The social environment for vaccines is also problematic, with the emergence of strong anti-vaccination movements (vaccines being a comparatively low-cost but effective response to AMR). All will provide significant headwinds for governments seeking to make rapid progress against AMR. The Fleming Fund made a range of changes in response to COVID-19, such as refocusing and extending grants. However, having key MA management and delivery capacity located at the regional rather than country level meant that it was not possible to implement important activities as originally planned.

Conclusion 4: The MA has successfully operationalised strong and effective procedures to manage for economy and efficiency at the activity level. With further use of laboratory capacity established during phase 1, the overall VfM of the programme will be enhanced. Delivering efficiently has been challenging in the context, and with the operational model that has been chosen, which affects VfM in terms of internal and external coherence, as well as management overheads. Efficiency has also been challenging to track given the focus on reporting implementation rates and the lack of a link between financial reporting and outputs; this seems to be driven by systems and cultures within the DHSC. Notwithstanding these challenges, the evidence suggests the delivery of efficiency and economy. On economy, there is evidence of significant cost savings delivered by the MA; savings of around £2.3 million were made on negotiating central procurement. Out of 25 CGs and RGs in our sample, 19 reported savings, and 11 grants reported savings of between 2% and 10% of the total spend, a level that benchmarks well to similar programmes. On efficiency, there is some evidence that the value of leveraged resources is reasonably significant in some grants . However, this indicator has not been reported or consistently tracked across all grants. The alignment between Fleming Fund expenditure, contribution, and progress in generating quality AMR data was found to be high, suggesting a positive VfM outcome.

The fact that laboratory functions have been strengthened compared to international norms, and the capacities of key members of the laboratory workforce have been built up means that effectiveness has also been delivered, albeit limited to lower-level or intermediate outcomes at this stage. The effectiveness of outputs delivered under phase 1 will be highly contingent on the success of phase 2 when the priority shifts to the use of AMR evidence.

Conclusion 5: Experience from phase 1 suggests the Fleming Fund can strengthen its approach through further reflection, including in terms of using a stronger and prioritised sustainability lens from the start in deciding what support to provide to laboratories, working at the organisational level to sustain capacity-building results, focusing on other data types as well as AMR, and differentiating more strongly between support provided to AH and HH.

Laboratory infrastructure enhancement. Specific choices about the nature of support provided and rationale for this – e.g. in terms of the sustainability implications of automating laboratory processes through sophisticated and expensive equipment, and the supply of consumables and reagents.

Human resource strengthening and workforce reforms. Working at the organisational/ institutional level to strengthen the sustainability of capacity building (health workforce training) efforts.

Focus on AMC/U and other types of data. A central assumption of the Fleming Fund is that key national and local stakeholders need to have evidence of both the trends of resistance and the impact that this is having on the health of their populations to ensure AMR is prioritised. However, since 2018, over half the focus countries have initiated significant policy and regulatory action on AMR at the national level without using significant analysis from Fund investments. This experience suggests that change at the country level can have other drivers and if identified, a wider range of opportunities for the Fleming Fund to contribute to its higher-level objectives.

Give greater priority to sustainability from the start. While phase 2 appears set to address some of the challenges noted in section 2.3 above, the detail on how this will happen remains unclear to the evaluation team. Sustainability is a shared responsibility between the DHSC, MA team and recipient governments. During phase 1, developing an approach to sustainability that might be effective has been constrained by a lack of consensus on what needs to be sustained. At the surveillance system level, the extent to which it is feasible and realistic to expect governments to allocate scarce domestic resources to AMR surveillance functions, particularly where the investment case is not clear needs to be carefully considered, alongside the question of whether some aspects need to be funded as a global public good. Developing plans and strategies for sustainability needs to be done based on a detailed, context-specific, politically informed analysis similar to that outlined in section ‎2.2 above.

Differentiation could also be strengthened by giving more detailed thought to the A–D categorisation that the MA presented in phase 1 but which has not been central to targeting change.

Conclusion 6: The Fleming Fund deserves recognition for prioritising One Health and for convening cross-sectoral dialogues. The lack of models on how this can be operationalised at a national scale has impacted the design of the Fleming Fund’s One Health approach. Experience from the joint research aspects of the Fellowship programme, which echoes wider experience in One Health, may help identify informal mechanisms to replicate during phase 2. As discussed in section 2.2 and Box 7, even though there was a strong impetus for fostering multisector One Health partnerships around AMR at the time the Fleming Fund started, it relied on limited practical guidance on how to successfully operationalise One Health in different country contexts. This is something that the international agencies have only now started to address, as demonstrated in the objectives of the recent World Health Assembly resolution on One Health and with the development of more structured approaches to implementing One Health. However, there are few examples of where effective One Health approaches are effectively implemented at a national scale – even in the UK, where perhaps the closest example is the Human Animal Infections and Risk Surveillance group which identifies and assesses emerging infection risks to HH. During this evaluation, we found that One Health partnerships can assume different forms across different countries, including varying levels of formality, and that formal and informal modes of partnerships often work together. For example, in Indonesia, the AMRCC under the Ministry of Health (KPRA) borrows its leadership from a professional network of AMR researchers. Similarly, countries such as Bangladesh have been home to active professional networks around One Health, such as One Health Bangladesh, that are able to mobilise research as well as policy action (see Annex 7 for more details).

Working with different degrees of formality/informality in One Health structures across Fleming Fund-supported countries is likely to be key during phase 2, and there is potential to draw on the Fleming Fellows’ joint research projects to learn lessons about supporting multisector collaboration.

Therefore, based on these examples, a more adaptive and country-specific approach to fostering One Health partnerships might be more effective in developing stronger and more sustainable One Health partnerships in member countries. This would mean that the Fleming Fund would need to go beyond developing shared datasets and relying on formal structures for promoting One Health. Other mechanisms of promoting One Health as a mechanism to understand and tackle AMR can build upon initiatives such as Fleming Fellows and develop newer opportunities for interaction and engagement across sectors, such as through joint research projects and convening multisector consultations.

Observations on programme management and implementation

Conclusion 7: During phase 1, planning by both the MA and DHSC was over-optimistic in terms of the time taken for design and approval and then delivery. It is not clear whether this has been fully addressed for phase 2. In practice, less than half of the 23 Fleming Fund countries had received 36 months or more support through CGs by June 2022, which was less than originally expected, although original plans were only ever for 16 countries to have received 36 months (or more) support by the end of phase 1. Less implementation has been achieved than expected due to a range of factors (some of which were outside MA and DHSC control) including two civil service purdahs, delays in contracting the MA, in part due to the length of negotiations between the DHSC and the MA during the inception phase and sign-off on the MA’s implementation plan (which was extended from eight to 17 months), due to country positioning and competitive tendering taking longer than expected (including in the approval of key documentation by DHSC), due to COVID-19, and due to the challenges of working in specific country contexts. The competitive tender process required by HMG procurement rules was time-consuming and of limited relevance in the context of a highly technical intervention where the pool of qualified suppliers is small. CG implementation, therefore, began two years after the start of the programme and the Fleming Fund has been playing catch-up from that point onwards. While these issues are well known by the MA and DHSC, there is an understandable risk that ambition and realism are not well balanced in setting expectations for what can be delivered in phase 2.

Conclusion 8: The complexity of the programme, with multiple Fund grantees operating at the country level, has made it challenging to deliver coherence across the Fleming Fund’s investments. This has been exacerbated by the DHSC’s decision to expand the number of grantees. The challenge was recognised, and progress was made but focused mainly on avoiding duplication. Less progress has been made in enhancing synergy and greater overall effectiveness. Evidence of external coherence with external partners is strong within limits but reflects the lack of working formal government coordination mechanisms: ultimately external coherence should be the remit of AMRCCs but these are not always fully functional and do not always include all relevant non-government stakeholders. Internal coordination has been hampered by management arrangements within the MA, decisions to keep different grant streams separate to avoid creating dependencies, and the lack of country-level capacity to fulfil a coordination function. This challenge was exacerbated by the DHSC’s decision to introduce a series of additional direct grants (e.g. to Common Pharmaceutical Association, FIND, and South Centre) during 2018/19 which meant that at times more than five different implementers were present at the country level, with no single voice, which increased transaction costs for country stakeholders. The advent of country coordination meetings has helped, but there is scope to further strengthen synergies between grant streams during phase 2.

The lack of sufficient coordination and external coherence means that opportunities to enhance effectiveness (in terms of linkages to other relevant agendas) have been missed. Progress on addressing external coherence may be key given the aspirations in phase 2 but the experience of phase 1 suggests that several of the contextual conditions that would have facilitated achieving external coherence (in terms of AMRCCs and NAPs) are missing and a feasible solution has not been identified. The assumption is that the Fleming Fund works within countries with AMR NAPs which identify prioritised actions and a functional multisectoral coordinating mechanism (AMRCC) and technical working groups with clear ToR, budget and an accountability framework. This is the institutional model assumed throughout the HH sector in LMICs and is the foundation for the business models of vertical funds such as the Global Fund to Fight AIDS, Tuberculosis and Malaria and the Global Vaccine Alliance (Gavi). External coherence between funds and interventions by all parties, whether within government or by external parties, should be delivered through this framework and depends upon strong leadership by the government.

Phase 1 experience is that AMR NAPs and AMRCCs have limitations in providing an organising, driving framework for action and external coordination. As discussed in section 2.2, the lack of NAP implementation in most countries has undermined the prospects for surveillance data sharing leading to national actions on AMR. The Fleming Fund has invested in the surveillance aspects of NAPs, but other important pillars have remained unfunded/underinvested. This Fleming Fund-specific experience reflects broader experience, as shown in TrACSS. Given this context, the Fleming Fund’s choice is either to provide more substantive support to strengthen AMRCCs and NAPs if not provided by others (although evidence would suggest this direction is fraught with challenges) or pay greater attention to the political economy of decision-making in each country to link Fund support better into institutional (sectoral) homes of the AMR agenda. For instance, there is potential for closer collaboration with related programmes, e.g. in the global health security space, and potential for the Fleming Fund to leverage donor funding for global health security for AMR-related investments – e.g. in strengthening broader laboratory capacity. This choice has not been taken.

This is linked to the challenge of ensuring external coherence with other donors that our KIIs suggest are investing in the HH AMR sphere – principally the Australian Department of Foreign Affairs and Trade (DFAT), CDC and USAID. Evidence suggests that, in the absence of prioritisation through AMRCCs, this coordination is happening to some degree in some countries, but ad hoc and based on existing relationships of grantees at the country level. However, KIIs also note that many decisions that frame the scope for coordination/coherence between investments at the country level are taken in the donor organisation capitals and during the design of the overall interventions (e.g. of regional programmes). This would suggest that enhancing external coherence needs to incorporate, at least for some donors and programmes, engagement at the donor headquarters level to complement country-level engagement through AMRCCs and relevant country-level decision-making bodies. This was started in phase 1 of the Fleming Fund but we are not aware that this has been taken forward substantively since the pandemic. Similar arguments apply in the One Health/AH arena, where the World Bank reports that it currently has over US$1.5 billion devoted to One Health in operations, including livestock and agriculture projects that include One Health approaches, and One Health-oriented projects that focus entirely on reducing the risk of emerging health threats.

Strengths and weaknesses of the current programme design in terms of contributing to the overall longer-term objectives of the Fleming Fund as articulated in the Business Case for phase 2

The previous conclusions include a number of strengths in the phase 1 approach that the Fleming Fund should build upon. Below we highlight a key conclusion that is critical for the Fleming Fund to address moving forward, given the evolving context and focus on contributing to the ultimate objectives of the Fleming Fund.

Conclusion 9: The Fleming Fund approach to managing for effectiveness could be strengthened at the country and portfolio levels. There has been progress in this regard during the course of phase 1, in terms of developing a portfolio-level ToC and a core set of indicators; and the challenges observed reflect factors common in many aid programmes. But some challenges are particular to the Fleming Fund, and addressing these will be of increasing importance in phase 2. The 2015 ICAI review of the UK’s former DFID’s approach to delivering impact concluded that:

To achieve lasting impact at scale, development programmes often require sustained engagement over several phases of programming. Alongside delivering direct improvements to the lives of poor people, they need to influence the policies and priorities of partner countries and [to] build institutions and organisational capacity (at national, regional, and community levels), in order to achieve lasting impact. Getting the balance right between direct impact and policy and institutional change emerges as a critical factor for successful impact. It calls for clear, long-term goals, combined with considerable flexibility as to the steps required to achieve them.

We note that while the rationale for the Fleming Fund echoes this conclusion, the programme is not unique in facing the challenge of managing for effectiveness and the required use of adaptive management. ICAI’s 2018 review of Department for International Development (DFID) approach to VfM in programme and portfolio management finds the same problem, as does a 2019 review of experience with results-based management across development organisations.

Notwithstanding this being a common challenge, the Fleming Fund did not start out with clear and realistic goals on what could be achieved during phase 1. The lack of clarity around expected results may have been due to the innovative nature of the programme, or to the lack of certainty on fundamental questions about the purpose of the Fleming Fund at the outset, but has substantially undermined the clarity of strategic focus and effectiveness of implementation at the outcome level during phase 1. Through a lack of country-specific targets (not established due to an initial lack of detailed understanding of the status of countries’ AMR surveillance and laboratory infrastructure, and the need to establish this through some implementation experience), the late development of a portfolio and country-level ToC and associated monitoring infrastructure, and the separation of accountability for the delivery of outputs from outcomes by the DHSC, the Fleming Fund did not equip itself with the ability to manage strategically and maintain focus on delivery against outcomes of interest. These challenges were exacerbated by the incentives for DHSC programme managers to focus on the immediate, set out in Box 11.

As discussed above, fundamental questions about the purpose of the Fleming Fund should have been addressed upfront – such as what were priorities in terms of national policy, regulatory and behaviour change (and for which target audiences) and how AMR surveillance was expected to contribute to that. We note that this was not a strong focus of what DHSC commissioned the MA to deliver, as set out in the original ToR that the MA responded to – which prioritised generating additional data, and that being clear on these points required at least some early implementation in each country. Establishing clear, long-term goals and mechanisms to track and adapt the steps required to achieve them would have provided a strategic focus behind which data generation efforts aligned. This outcome-focused adaptation is standard practice in developing programmatic interventions of this kind, although not routinely implemented. Related to establishing clear expectations:

Establishing goals at a strategic level will help manage the risk of rigidly maintaining focus on operational plans at the cost of strategic adaptation. The extent to which the DHSC systems and culture allow for this kind of adaptation needs careful consideration during phase 2.

Establishing expectations needs to be done with country counterparts (conclusion 11) and the country investment strategy process provides a good opportunity to do this. However, given the advent of phase 2, and expectations that exist for how phase 2 will shift, there is a risk that country investment strategy processes are overloaded and unable to deliver. In this scenario ‘delivering’ key strategic shifts will be more challenging and so the importance of establishing clear, shared expectations cannot be overstated.

Ultimately phase 2 is short, and tackling AMR requires a long-term response, and it will be essential to define success for phase 2 in ambitious but realistic terms; experience from phase 1 provides a clear basis for calibrating ambition appropriately.

Recommendations

The recommendations we present below follow from the findings and conclusions set out above, and summarised in Annex 21. They are a set of equal priorities and should be implemented as a package for the best results.

- The DHSC and the MA should ensure that clear, ambitious, realistic goals for phase 2 are in place from the outset, with targets to track progress. These should be established at the country and portfolio levels, based on understanding the current status of AMR surveillance systems and their use as developed during phase 1. This recommendation links to conclusion 9, and findings on VfM (section ‎2.3). Key areas to cover are around the phase 2 strategic shifts and key principles, particularly on the use of data (for clinical outcomes, national-level policy and behaviour change, and international-level sharing), and sustainability.

- The DHSC and the MA should agree on clear, well-defined (and differentiated as appropriate) expectations for what can be achieved during phase 2 at the country and portfolio level of outcomes. This should be the basis for prioritising the most appropriate support in developing surveillance systems and the basis for holding the MA accountable for a functioning approach to managing outcomes.

- What needs to be sustained and how the MA will deliver this should be part of the agreement of the implementation plan. It is recommended that policymakers and clinicians should work to ensure that AMR becomes a top priority issue. This is a precondition for driving resource decision-making within a government and at the facility level. So, at the national level, build on the finding that over half the focus countries have initiated significant policy and regulatory action on AMR at the national level since 2018 without significant analysis from Fleming Fund investments. At the facility level, on the other hand, build on the finding that phase 1 interventions have started stimulating positive changes to practices and attitudes as clinicians and other stakeholders start to interact differently with improved laboratories as the precursor to budget discussions.

- The MA’s implementation plan should be based on phase 1 experience on both absorptive capacity at the country level and how long individual grant development and approval and contracting take. The DHSC should verify that the agreed implementation plan is realistic. In turn, the DHSC should ensure that the trade-offs between the benefits of developing new grants and the additional transaction costs that come with this are fully weighed and documented.

- The DHSC and MA should ensure that systems and processes for establishing expectations and tracking progress are proportionate, timely and sufficiently flexible to deal with uncertainty and the need for strategic adaptation. These must strike the right balance between strategic reflection and accountability and avoid focusing too heavily on tracking the implementation of inputs and activities. This recommendation links to conclusion 4, and findings on VfM (section ‎2.3).

- The DHSC should ensure that specific challenges relating to the start-up of phase 1 are not replicated in phase 2 – such as delays in contracting and in agreeing on implementation plans, an extended inception phase, delays in competitive tendering and grant placement, and contracting for outcomes. This may have implications for DHSC systems e.g. for contracting and tracking performance. DHSC (at the organisational level, rather than at the level of the Fleming Fund team) should seek to learn from how FCDO and UK Health Security Agency have approached these issues with their internal systems and procedures.

- The VfM approach to delivering efficiency and economy under phase 1 should continue but the DHSC and the MA should ensure that they have internal systems and processes in place that are fit for purpose (focused at the outcome level, based on clear, well-defined targets and indicators, based on evidence of what is and is not working as expected) which support strategic adaptation and managing for effectiveness. If the change in practice at the facility level becomes the main priority in phase 2, the VfM approach should expand to examining the equity implications.

- The process of establishing goals at the country level should be focused on understanding the priorities and needs of key decision-makers on AMR, recognising inter alia that (a) AMR action will take place through multiple policy processes and that differentiation between HH and AH is of fundamental importance; and (b) that achieving higher-level goals requires action by other actors and therefore effective collaboration with key stakeholder groups. This recommendation links to conclusions 2,6 and 7, and findings on use of AMR surveillance data (section ‎2.2).

- The DHSC and the MA should avoid overloading country investment strategy processes, create realistic expectations, and allow space for country-level dialogue to promote ownership and sustainability, internal and external coherence, and adaptation to changing contexts.

- The entire Fleming Fund (not just the MA) should work more politically (i.e. engaging with governments to understand their priorities, opportunities, incentives, decision-making processes and drivers of change) to ensure higher-level goals are in place, drawing on published literature to identify ways in which the Fleming Fund could be strengthened. Ensure PEAs are conducted sufficiently early to inform country strategy, and that the emphasis with PEAs is on the process as much as the analysis that emerges. Published literature points to changes that the Fleming Fund can seek to pursue with AMR surveillance systems to strengthen the use and uptake of AMR surveillance data:

- Be realistic about the strengths and limitations of NAPs as a tool for prioritisation, coordination, and driving the broader agenda forward.

- Be in a position to respond when opportunities arise (rather than having to react from a low starting point).

- Be proactive in terms of who the stakeholders are and identify potential policy entrepreneurs.

- Have a flexible and experimental approach, particularly on data sharing/information systems, organisational design, and development.

- The MA and the DHSC should focus more on a) demand for ASTs and b) demand for/intended use of data to ensure that investments are strategically focused. Achieving intended results, especially in a way that is sustainable and presents good VfM, depends on linking data supply to AMR-related action or demand. This implies identifying opportunities that exist within multiple AMR-relevant policy agendas (e.g. for IPC, AMS, laboratory or broader health system strengthening), most of which are likely to depend on factors outside of AMR-specific governance structures. This could help maximise the use of AMR surveillance data even if there is a lack of overall progress in prioritising AMR.

- If the focus for use in phase 2 is to include facility-level use, this should address known challenges of scaling up specific examples of use in individual facilities to ensure genuine systematic change.

- The DHSC should build on its existing efforts to ensure external coherence both with other donors working directly on AMR, such as DFAT, CDC, USAID and World Bank (One Health), engaging with relevant decision-makers at the headquarters level and those within the broader global health security sphere and linking to relevant non-AMR-specific interventions. The DHSC should set and track expectations or assumptions on the involvement of other donors and government partners in the country investment strategy development and review processes.

- The Fleming Fund should make adaptations to or emphasise specific aspects of its technical approach for phase 2, that are supported by experience from phase 1. These should include focusing on AMU and other data sources, identifying informal approaches to One Health multisector collaboration, and maximising the prospects for sustaining laboratory functions. This recommendation links to conclusion 5, and findings on use of AMR (section ‎‎2.2) and sustainability (section ‎2.3).

- The MA should strengthen engagement in generating AMU data as a potentially influential source of data for decision-makers.

- The MA should move away from its current standardised approach to One Health towards a more flexible method to cross-sector collaborations. Using a less formal way of collaborating, such as research networks, is likely to result in more effective One Health partnerships. In fostering this approach, the MA should build on its relevant experience with the Fleming Fellowships and consider the use of a challenge fund approach.

- The MA should continue to support AMR surveillance functions in the areas it focused on in phase 1 but give more priority to implications for sustainability in what is supported. In terms of laboratory infrastructure enhancement, the decisions on automating laboratory processes through the supply of sophisticated and expensive equipment and the supply of consumables and reagents should be reviewed. The approach to developing capacity should expand beyond training individuals to developing a sustainable way of delivering such training, embedded in government systems.

- The Fleming Fund should place greater emphasis on internal and external coherence and coordination from the outset of phase 2, including strengthening AMRCCs and NAPs to play this role and their linkages to institutional homes. This recommendation links to conclusion 8 and findings on coherence and alignment (section ‎2.3).

- The DHSC and the MA under phase 2 should either provide more substantive support to strengthen AMRCCs and NAPs if not provided by others (although evidence would suggest this direction is subject to challenges around mandate, ownership and ensuring effectiveness in terms of contributing to strategic goals) or pay greater attention to the political economy of decision-making in each country, so as to link Fund support better into institutional (sectoral) homes of the AMR agenda where priorities are set (both within government and professional bodies).

- The MA should supplement country investment strategy processes, building on its evolving approach to supporting internal coherence between individual grantees working in a particular country (which is currently focused on information sharing to avoid duplication). This could be done by expanding the focus to look at opportunities to enhance synergy between grantees (joint planning and review of progress between all Fleming Fund grants) in order to enhance overall programme effectiveness.

https://amr-review.org/sites/default/files/160525_Final%20paper_with%20cover.pdf

One Health is a multiple disciplinary effort to attain optimal health for people, animals and the environment. https://www.avma.org/onehealth

https://www.flemingfund.org/our-approach/programme-design/

The Fleming Fund started in 23 countries (see Figure 3) but subsequently pulled out of Sri Lanka and Myanmar.

E.g. data on AMC/U also increased in some countries.

Contribution to drivers was rated against the following scale: vital / important / some / limited / none / negative. See Annex 3 section 1.3.1 for more details on the methodology applied and Annex 22 for a visual summary of the results.

This assessment differs from MA reporting on data sharing because it is undertaken on a different basis.

As discussed in section 3.1.1.

Kurowski, Christoph; Evans, David B; Tandon, Ajay; Eozenou, Patrick Hoang-Vu; Schmidt, Martin; Irwin, Alec; Salcedo Cain, Jewelwayne; Pambudi, Eko Setyo; Postolovska, Iryna. 2021. From Double Shock to Double Recovery: Implications and Options for Health Financing in the Time of COVID-19. Health, Nutrition and Population Discussion Paper; © World Bank, Washington, DC. http://hdl.handle.net/10986/35298

We note the Tricycle protocol could potentially play a role in providing a tried and tested model; however, it was published in 2021, so not available for Fleming Fund use for the majority of phase 1. https://apps.who.int/iris/handle/10665/340079

https://apps.who.int/gb/ebwha/pdf_files/WHA75/A75_19-en.pdf

https://www.who.int/initiatives/tripartite-zoonosis-guide

Purdah is a period of pre-election sensitivity when Government departments and councils will normally observe discretion about making new announcements or decisions that could influence voters. https://commonslibrary.parliament.uk/research-briefings/sn05262/

https://icai.independent.gov.uk/wp-content/uploads/ICAI-report-DFIDs-approach-to-Delivering-Impact.pdf

ICAI’s 2018 review of DFID’s approach to VfM in programme and portfolio management finds the same problem, as does a 2019 review of experiences with results-based management across development organisations.

DHSC Terms of Reference: Management Agent for The Fleming Fund – para 2.4 and 2.5, which lists eight indicative focus areas for the grants portfolio, only one of which mentions ‘Policy and advocacy work with national governments, using AMR data and analysis collected to make the case for evidence-based public health interventions’.

Workstreams 1 and 2 were outside the evaluation scope.

List EQs or focus areas.

The report has been written during the inception phase of Phase 2 of the programme but it does not fully cover the extent to which the design of phase 2 responds to the findings, conclusions and recommendations of this summative report as comprehensive details of phase 2 design were not available in time.

However, we have not structured the report using the EQs. A mapping of where EQs are covered in the report is included in Annex 5.

Phase 1 of the Fleming Fund was subsequently extended to March 2023, and a second phase with £193.5 million investment over a three-year period (FY2023/24 to 2025/26) was approved in late 2021.

One Health is the integrative effort of multiple disciplines working together locally, nationally, and globally to attain optimal health for people, animals, and the environment. https://www.avma.org/onehealth

Review on Antimicrobial Resistance.(2016). Chaired by Jim O’Neill. Retrieved from Review on Antimicrobial Resistance: amr-review.org

LMIC impact was DHSC’s rationale for using ODA funding for the Fleming Fund. The burden of AMR in LMICs has subsequently been modelled by Global Research on Antimicrobial Resistance, with findings underlining the potential impact in these countries.

Including the UK government’s 2015 aid strategy – UK aid: tackling global challenges in the national interest; and 2016 Fleming Fund Business Case.

DHSC contracted a range of direct grantees (e.g. to support the Commonwealth Partnership for Antimicrobial Stewardship (CWPAMS), to the Foundation for Innovative New Diagnostics (FIND), and the South Centre) during 2018/19, to deliver specific objectives. These are not within the scope of this evaluation, but did make it more complicated to understand delivery outcomes delivered by the Fleming Fund.

Note that the ordering of workstreams in Figure 2 differs from the order of workstreams presented in the evaluation ToR (Annex 1) but the content across the five workstreams remains the same.

Workstream 1 was implemented by the London School of Hygiene and Tropical Medicine; workstream 2 was through WHO, FAO and OIE (now WOAH); workstream 5 was implemented by Itad, culminating in this summative report. DHSC also commissioned a number of global grants (see section 1.2 for more details).

The distinction between outputs and outcomes is important in terms of findings on effectiveness in section 2.3. See Vol.II, Annex 18 for a visual overview of outputs and outcomes.

As noted below, a portfolio-level ToC was developed in mid-2019 after phase 1 implementation had commenced.

E.g. Mali and Burkina Faso have all experienced security situations making it difficult for the MA to operate as required.

The 23 Fleming Fund countries which received some form of support: Sierra Leone, Ghana, Senegal, Zambia, Tanzania, Kenya, Bhutan, Bangladesh, Indonesia, Laos, Pakistan, Nigeria, Uganda, Nepal, Timor-Leste, Vietnam, Myanmar, Zimbabwe, India, Sri Lanka, Malawi, Eswatini and Papua New Guinea (see Figure 3). As noted above, the Fleming Fund started country grants in these 23 countries but subsequently pulled out of Sri Lanka and Myanmar.

The LSHTM roadmap, published in 2017, was designed for use in LMIC settings. Seale, A., Gordon, N., & Islam, J. e. (2017). AMR Surveillance in low and middle-income settings – A roadmap for participation in the Global Antimicrobial Surveillance System (GLASS). Wellcome Open Research, 2(92). Available at: https://researchonline.lshtm.ac.uk/id/eprint/4574689/ There was no equivalent developed for AH at the same time.

Living in a relationship in which one organism derives food or other benefits from another organism without hurting or helping it. https://www.rxlist.com/commensal/definition.htm

As discussed in section 1.5, DHSC also contracted a number of direct grants that were not under the management of the MA team.

RGs were defined through expert consultation in the form of a SurveyMonkey.

For example, initial versions of some NAPs did not specify which laboratories would serve the function of national reference laboratories (NRLs).

These are taken from the MA’s implementation plan (v2.5, 2018), which did not (and could not have been expected to) take into account the implications of subsequent political changes in the UK and the COVID-19 pandemic. We also note that these were not used as key metrics for reporting: a results framework was developed midway through phase 1 which has been the focus of reporting since 2019, along with KPIs. See sections 2.1.2-3 and Vol. II, Annex 8 for more on KPI data.

We note, however, that the evaluation cut-off for data collection was the end of June 2022 and, whilst we have attempted to note where further progress is expected to end in December 2022, most of our analysis reflects progress to June 2022.

IP states that ‘the programme aims to have active grants in all 24 countries by the end of 2019. This assumes a start date of October 2017 for implementation. The original end date of the Fleming Fund was March 2021.

Purdah is a period of pre-election sensitivity when Government departments and councils will normally observe discretion about making new announcements or decisions that could influence voters. https://commonslibrary.parliament.uk/research-briefings/sn05262/

Scoping and positioning work took longer than the six months initially expected, with delays in start-up of grants ranging from 1–20 months and averaging 6–25 months.

E.g. the MA seems to have started taking learning from professional fellowships into account in the early Policy Fellows implementation, for example encouraging better tailoring of ToRs to country priorities.

As noted in section 1.1, these direct grants are outside the scope of our evaluation.

For which grants were made to both the Commonwealth Pharmaceutical Association and the Tropical Health and Education Trust (THET).

At times more than five different implementers were present at the country level, with no single voice, which increased transaction costs and potential for confusion for country stakeholders, acknowledged by the MA team as early as December 2018 (DPE Tanzania).

Findings from research conducted by Itad on ‘Remote Delivery during COVID-19: Lessons learned from best practice and from Fleming Fund implementing partners’ experience’. Submitted to the DHSC in 2022.

Loft, P., & Brien, P. (2021). Reducing the UK’s aid spend in 2021. House of Commons Library. Available at: https://commonslibrary.parliament.uk/research-briefings/cbp-9224/

There were two spending reviews during the period covered by phase 1.

World Health Organisation. (2021, November 17). Antimicrobial Resistance. Retrieved from World Health Organisation: https://www.who.int/news-room/fact-sheets/detail/antimicrobial-resistance

WHO; FAO of the United Nations; UNEP; WOAH. (2022). Antimicrobial Resistance Multi-Partner Trust Fund annual report 2021. Geneva: UN MPTF Office.

World Health Organisation. (2020, August 10). Global Leaders Group ToR. Retrieved from World Health Organisation: https://www.who.int/news-room/articles-detail/global-leaders-group-terms-of-reference

Although in practice this is limited to the start of country-level implementation in August 2018 up to mid-2022 which was the cut-off point for data collection for the evaluation summative report.

In most countries there were limited relevant informants with sufficient knowledge of AMR surveillance and/or Fleming Fund support. Potential inclusion was on basis of understanding and ability to provide informed perspective on Fleming Fund design and implementation. Categories included those involved in implementation (country grantee, laboratory staff), intended users of AMR data (policymakers), other key stakeholders involved in supporting AMR surveillance (UN bodies, other donors, civil society organisations), and MA/DHSC staff. Similar categories applied across both AH and HH sectors.

Snowball sampling is an approach for identifying KIs. The process begins by asking well-situated people ‘Whom should I talk to?’ By asking a number of people who else to talk with, the snowball gets bigger and bigger as you accumulate new information on relevant KIs. Patton M Q, (2002) Qualitative Research and Evaluation Options (3rd ed.) Thousand Oaks, California. Sage Publications

The literature often talks about reaching ‘analytic saturation point’ – the point during the analysis of the data where the same themes are recurring, and no new insights are given by additional sources of data.

It should be noted that the main analytical methods used in the summative evaluation have changed from what was outlined in the inception report. The analytical methods used were selected to best answer the EQs and the overarching evaluation objective.

https://www.gov.uk/government/publications/dfid-ethical-guidance-for-research-evaluation-and-monitoring-activities

Wave 1 (Q1 2022) Bangladesh, Bhutan, Indonesia, Nigeria, Senegal, Sierra Leone, Vietnam and Timor-Leste. Wave 2 (Q2&3 2022) Kenya, Nepal, Uganda, Ghana, Tanzania, Zambia, Pakistan and Laos.

For more detail on stakeholder participation, see Vol. II, Annex 16.

Such as the production of findings, conclusions and recommendations in different formats to promote accessibility.

See section 1.2 for more on the LSHTM roadmap

Contribution to drivers was rated against the following scale: Vital / Important / Some / Limited / None. See Annex 3 section 1.3.1 for more detail.

Data collated during the second round of evaluation data collection (2019/20).

Although as shown in Vol. II, Annex 8.1, table 25, four countries reported disbursement of government funding.

See Vol. II, Annex 8.1, table 25.

One Health Trust. (2022). GARP. Retrieved from One Health Trust: https://onehealthtrust.org/projects/global-antibiotic-resistance-partnership/

Ibid. These all noted varying degrees of research data on AMR trends in both HH and AH (albeit less in AH).

Data was mostly self-reported by CGs, and we have seen a few of the laboratory assessments that the MA/CG teams were meant to complete (although the MA notes these were done for almost all sites during scoping or shortly afterward). Data on quality at baseline is also lacking for Fleming Fund sites that were added during CG implementation. See Vol. II, Annex 8 for more details.

Early investment countries (EICs) were treated in the same way in the evaluation as all of the 23 countries. The main difference was that work in the EICs started earlier and these countries provided a longer period of data from which to learn lessons and explore the evaluation questions. EICs were: Nepal, Uganda, Ghana and Myanmar.

All but Sierra Leone and Senegal.

See Vol II, Annex 8.1, Table 26 for more on this, including note of caution on specific numbers.

We note that the MA team reported 12/16 countries (75%), but we were unable to corroborate one of these.

This was based on early scoping of data availability, which suggested this data would be difficult to consistently obtain due to lack of national systems to consistently report this; and the MA did not report on this. We anticipated difficulties in terms of data sharing around AST and in particular results of ASTs.

See Vol. II, Annex 15 for details on A-D categories.

In terms of farmers’ incentives to use laboratory services, and the extent to which these sit within the private or public sector and can be accessed by national surveillance systems.

https://www.who.int/initiatives/glass/resource-centre#glassreports. There is also some evidence that data is being generated in Senegal but this has neither been reported to GLASS, nor was it possible to establish a firm picture on this through evaluation data collection. The remaining three that do not appear to have generated data at this stage are Eswatini, Sierra Leone and Zimbabwe (although the evaluation did not undertake data collection in Eswatini or Zimbabwe and so cannot comment on whether data is available in these countries but just not reported to GLASS).

see Vol. II, Annex 15 for description of categories and mapping of categories to Fleming Fund countries.

This metric was only introduced in 2020, whereas it was tracked from 2019 in HH

Of the 72 fellowships completed, 52 (72%) had data available from end vs baseline self-assessments to enable changes against a core competency framework. Of these, 37 (71%) reported improvement in 80% or more of the competency framework dimensions/domains relevant to their Fellowships. See Annex 8 for more details.

The specific metric is the % of fellows that reported improvement in 80% of dimension / domains in their self-assessments. By mid-2022 performance against this metric was 80%.

The types of issues that were rated as ‘governance’ in this specific context: Effective oversight, coalition-building, regulation, attention to system design and accountability and Increased focus by policymakers and senior staff within the system creating signals about importance.

Ibid.

Note that ‘changes in the number of pathogens tested for’ was not identified as a driver of ‘quantity of data’ by KIIs in any country.

Although it is not feasible to isolate the extent to which increases are due to this driver.

Hence noting in section 2.1 that many countries expected further progress in data generation during the remainder of 2022.

See Annex 22 for a visual summary.

This is the case for the first wave of AMR NAPs. There is some evidence of the Fleming Fund’s contribution to more recent AMR NAP documents.

For example, the Fleming Fund supports 100% of surveillance sites in Timor-Leste but 38% in Nigeria.

This is the emphasis within Fleming Fund’s own monitoring frameworks for phase 1. Notably MA quarterly matrix indicators: ‘Number of countries where the national body in charge of the country AMR strategy receives AMR data report(s) generated by … surveillance sites at least once a year’ – HH (5.2)/AH (5.3).

For example, in TrACSS: ‘Country using relevant AMC/U and/or AMR data to amend national strategy and/or inform decision making’ (7.6).

including data sharing with AMRCC, equivalent One Health committees in the context of wider national governance structures, any relevant national actions on AMR in terms of policy or regulation, plus decision-making processes relevant to transforming information into action.

considered exclusively in terms of data sharing with GLASS and WOAH, with related action and decision making not included in the scope of this report.

examples of data sharing, action and/or decision making, including practices and attitudes, involving any local uses of data direct from Fleming Fund supported microbiology facilities.

Interagency Coordination Group on Antimicrobial Resistance. (2018). Antimicrobial resistance: national action plans. Available at: https://cdn.who.int/media/docs/default-source/antimicrobial-resistance/iacg-amr-national-action-plans-110618.pdf?sfvrsn=53e4eb22_4

Department of Health and Social Care. (2020). Fleming Fund annual review: January to December 2019. Available at: https://www.gov.uk/government/publications/fleming-fund-annual-review-2019/fleming-fund-annual-review-january-to-december-2019#theory-of-change

Global Antimicrobial Resistance and Use Surveillance System (GLASS): GLASS provides a standardized approach to the collection, analysis, interpretation and sharing of data by countries and seeks to actively support capacity building and monitor the status of existing and new national surveillance systems https://www.who.int/initiatives/glass. Note that the data reported to GLASS lags by two years: the 2018 GLASS report shows 2016 country data. 2018 reporting is an indicator of country participation in relevant international processes, rather than the availability of data, at that time.

World Organisation for Animal Health (WOAH, formerly OIE). https://www.woah.org/en/what-we-do/global-initiatives/antimicrobial-resistance/

As of November 2022, none of the Fleming Fund countries were making their data publicly available.

When reporting to WOAH, countries can choose from three reporting options: Reporting Option 1: allows countries to distinguish quantities of antimicrobial agents by type of use (therapeutic or growth promotion);

Reporting Option 2: allows countries to distinguish quantities of antimicrobial agents by type of use and animal groups (food-producing terrestrial and aquatic species and companion animals); Reporting Option 3: allows countries to distinguish quantities of antimicrobial agents by type of use and routes of administration (distinguishing by group of animals is optional)

For example, the MA suggested a potential indicator at this level at the proposal stage (see Implementation Plan).

Forecasted Results from Implementation Plan – ‘Primary data generated and used for policy and improving guidelines’ in 3 countries after 12 months; 8 countries after 24 months; 16 countries after 36 months; 18 countries after 48 months. Also Matrix Indicators from Monitoring Data Report Q2 2022 (June 2022): Number of countries where the national body in charge of the country AMR strategy receives AMR data report(s) generated by HH surveillance sites at least once a year – 12 reported against milestone 18; Number of countries where the national body in charge of the country AMR strategy receives AMR data report(s) generated by AH surveillance sites at least once a year – 13 reported against milestone 15.

In one of these countries, the MA subsequently provided evidence of data sharing efforts, including piloting an integrated AMR data sharing platform for AMR/AMU/C data from all the sectors – suggesting some sharing is happening and with potential for substantial data sharing in future.

Targets taken from MA implementation plan v2.5. Target was 16/24 (66%), adjusted for (16) evaluation focus countries = 11 (16 x 66%).

Latest MA reports indicate, based on broader definitions, that data sharing is taking place in all Fleming Fund countries or in 13/16 countries [Q2 report 2022]. Our assessment for this report, which complied with indicators as defined in the phase 1 implementation plan, differed from MA’s endline assessment mainly in that it: retained the perspective of the decision-taker, or data consumer (rather than focusing on the point of view of the sender of information, or data producer); required evidence of some concrete relationship of data to AMR action in ‘policymaking’; and sought actively to triangulate data gathered from multiple sources, including stakeholders not benefitting directly from Fleming Fund investments. Our summary findings were more consistent with reports from other sources on this subject, including country self-reporting. We note a high degree of sensitivity in relevant indicators to apparently minor changes in wording or data collection approaches.

Reflecting 2020 data collected in 2021. See Annex 8.1, table 28 for details.

Pathogens currently included in GLASS-AMR are: Acinetobacter spp., E. coli, Klebsiella pneumoniae, Neisseria gonorrhoeae, Salmonella spp., Shigella spp., Staphylococcus aureus, and Streptococcus pneumoniae. https://www.who.int/initiatives/glass/glass-routine-data-surveillance

We also note that two countries reduced the number of pathogens tested.

The implementation plan goal is 12/24, by 2022 17/23 countries were reporting to GLASS.

We use the 2020 report as this reports on 2018 data (our baseline year) collected during 2019.

Note that this differs slightly from the data presented in Vol. II, Annex 8 because it comes directly from WOAH and our Annex 8 is from our country-level data collection. Data from WOAH is not disaggregated by country, and we were unable to obtain relevant data in four of our focus countries.

e.g. AMR-specific technical references such as AWaRE (Access, Watch and Reserve), international AH/food frameworks and regional trade standards as well as the AMR GAP framework more generally.

So that the MA could prioritise implementation of surveillance-focused activties.

See Box 4 in Annex 9.2 for background on the Kingdon Multiple Streams Analysis approach on which this statement is based. It is important to address the point that Fleming Fund results at outcome level are subject to external factors outside the programme’s control including national policy agenda dynamics. Policy agenda dynamics should not be subjected to rational assumptions.

Defined as increased availability of data in sufficient quantity/quality to share.

Defined as adequate data sharing processes and systems.

See Annex 22 for a visual summary.

Regional Antimicrobial resistance Data Analysis for Advocacy, Response and policy.

As noted in section 1.3, the contribution of RGs was not simple to identify at country-level. This is in part due to the short (c.2-years) duration of RGs – so limited time to demonstrate progress at country-level; and to the timing of our data collection: e.g. it is clear that work undertaken through the CAPTURA and MAAP regional grants has potential for use by policymakers at country-level but final country specific reports from both grants were still being finalised which likely constrained key informants ability to refer to this work.

Overseas Development Institute.

The Commonwealth Partnerships for antimicrobial stewardship

Although we recognise that not all of these investments were implemented in all countries which may provide some explanation.

See, for example, the Thinking and Working Politically Community of Practice https://twpcommunity.org/

Meaning that the Fleming Fund has contributed in a vital or important way to fewer key drivers of change in international data sharing than compared to its contribution of key drivers for production of more and better data. This indicates that the incentives/enabling factors to report to GLASS are perhaps wider than those behind producing more and better data.

See Annex 22 for a visual summary.

Comprising a Sustainability strategy in June 2017, and Operational Guidance in October 2018.

E.g. through an update to the Sustainability Strategy in November 2019.

E.g. in CMO update slides – November 2018.

MA Update of Fleming Fund Grant Programme Sustainability Assessment, November 2019; KIIs with MA team.

Evidence from broader literature; see https://www.flemingfund.org/publications/common-elements-of-good-practice-for-sustainability/Also highlighted at the country level – e.g. in Uganda, it was noted that HIV programmes are still dependent after 30 years.

E.g. the CG2 in Pakistan was designed to strengthen the strategic underpinning (and therefore potential sustainability) of the surveillance system through development of key strategic documents in AH, including Surveillance in Healthy food animals, Surveillance in Diseased food animals, Khyber Pakhtunkhwa (KP) AMR surveillance strategy, AMR in food, animal, and environment, Pakistan vet lab policy and guidelines, Antibiotic prescription guideline in food animals, Sampling plan in aquaculture. In Uganda, sustainability was pursued through e.g. getting a written agreement signed by the government that the MoH would eventually absorb Fleming Fund supported lab posts (even though this has not yet happened); on supplies, the CG tried to drive long-term ownership by the government, for example by supporting the 10 year National Health Supply Chain roadmap to increase local financing for microbiology services.

The MA Operational Manual for Cross-cutting themes (October 2018) notes: ‘The Fleming Fund Grants Programme will focus assistance on national systems with a view to long-term sustainability. Investment size and scope should, as far as possible, be aligned with national government spending so that systems created with Fleming Fund grants are sustainable within the public health system.’

KIIs noted a lack of systematic use of sustainability strategies as the basis for work planning or a specific focus on sustainability in interactions between the MA and CGs.

The IP did set out intentions to develop exit plans after 12 months of implementation in each country.

Only in Bangladesh was there an expectation that a plan for sustainability in HH would be established, although more countries anticipated some progress in AH .

See Vol. II, Annex 10

Ibid.

Brown, C., & Shorten, T. (2021, 07 21). Common elements of good practice for sustainability. Retrieved from The Fleming Fund: https://www.flemingfund.org/publications/common-elements-of-good-practice-for-sustainability/

‘Partial resourcing’ is used to mean that some resources were available to support relevant AMR functions but that this would be insufficient to cover the entire cost.

Three countries expected progress in resource allocation, and one expected a worsening situation.

See subheading ‘capacity building and governance’.

Implementation Plan pp93/121: It includes eight items considered as capital equipment, five of which should be covered by a service contract covering after-sales service, training, installation and/or maintenance/repair (see MA IP, Annex 9.4).

IP pp92; IP Annex 9.4. Assumed or indicative budget for requirements for each facility were £120,847 of which £17,963 (15%) was assumed for reagents and media, and £4,173 (4%) was assumed for consumables.

Note that this is the budget for all activities (excluding staff salary), and the AMR budget within this is around US$5,000.

such as manual disc diffusion AST testing, although we note that there are pros and cons of both automated and manual methods.

There is no discussion of the implications of this distinction in the MA’s implementation plan (v2.5).

The MA’s TOR does spell out objectives for strengthening availability of data on the sale and use of antimicrobial medicines, particularly antibiotics (sections 2.2, 2.4) but the operational emphasis is more on AMR than AMU (section 3.9–3.20 of the MA ToR).

Although covering costs through user fees is on the agenda in some countries, e.g. in Ghana and Laos and payment for laboratory services is an ongoing concern (as discussed above 2.3.1).

See section 2.3.1 for more detail on sustainability assessments.

Fellowships use a train-the-trainer model, with Fellows intended to cascade training to their peers.

Note the lack of activity of AMRCCs in many countries once their job of creating NAPs had been accomplished.

As noted in Fleming Fund TAG discussions on phase 2.

3E’s refer to economy, efficiency and effectiveness. Note 4th E (equity) is not tracked since phase 1 does deliver outputs that directly affect primary beneficiaries and possible effects on equity and poverty of decisions informed by surveillance evidence will depend upon the decision taken.

DFID. (2020). DFID’s Approach to VfM – Guidance for External Partners. London.

ICAI. (2018). DFID’s approach to VfM in programme and portfolio management: a performance review. London: ICAI.

MA. 2021. Fleming Fund Management Agent. Phase II Technical Proposal. March 2021.

Which cover the grantees’ overhead costs i.e. a portion of their operating costs

Expense directly attributable to the grant such as personnel (Project Managers/administrators/finance staff/etc) and expenses (office costs, rent, etc)

Direct comparison between programmes is limited due to variance in accounting practice for overhead costs. A survey of UK grant management civil society organisations found overhead costs (central and programme support costs) range from 20–28%. (BOND Mango cost recovery: what it means for CSOs, February 2016).

Leveraged resources are those contributed by stakeholders including government and other institutions to implement programme activities. These include in-kind resources, such as consumables and meeting facilities, and cost-sharing.

This metric was only introduced in 2020, whereas it was tracked from 2019 in HH

This was particularly challenging given delays multiple contracts and delays in placing some of these (see Figure 6)

MA implementation plan v2.5

Although whilst country grants delivered by UN agencies had to be contracted by DHSC, these were still managed and overseen by the MA.

KIIs with CG and RG implementers.

KIIs with Fellows and MA.

In Laos for example, some laboratories are still reporting to Mahosot hospital (supported by Lao-Oxford-Mahosot Hospital-Wellcome Trust Research Unit – LOMWRU) who then reports to the National Reference Laboratory (the NRL) instead of reporting directly to the NCLE.

The OECD DAC defines external coherence as ‘the consistency of the intervention with other actors’ interventions in the same context. This includes complementarity, harmonisation, and coordination with others, and the extent to which the intervention is adding value while avoiding duplication of effort.’ OECD. 2021. Applying Evaluation Criteria Thoughtfully. Available online at: https://www.oecd-ilibrary.org/development/applying-evaluation-criteria-thoughtfully_543e84ed-en

As discussed in section 3.1.1.

DFID. (2020). DFID’s Approach to VfM – Guidance for External Partners. London: DFID.

ICAI. (2018). DFID’s approach to VfM in programme and portfolio management: a performance review. London: ICAI.

This is a positive finding: although there were delays in implementation, resources have been reprogrammed and timelines extended without additional funding from DHSC in most cases

The evaluation noted that their progress towards IOs was not tracked and consequently the Fleming Fund was not able to course correct to maximise effectiveness at the level of IOs. This was in part due to the MA not being contracted to deliver IOs, and so not accountable for progress at that level.

Business Case, paragraphs 5.6 and 5.5.

Recognising that other things need to be in place in order for data to be used, as discussed in section 0.

Kurowski, Christoph; Evans, David B; Tandon, Ajay; Eozenou, Patrick Hoang-Vu; Schmidt, Martin; Irwin, Alec; Salcedo Cain, Jewelwayne; Pambudi, Eko Setyo; Postolovska, Iryna. 2021. From Double Shock to Double Recovery: Implications and Options for Health Financing in the Time of COVID-19. Health, Nutrition and Population Discussion Paper; © World Bank, Washington, DC. http://hdl.handle.net/10986/35298

We do note the potential role that the Tricycle protocol could play in providing a tried and tested model, but also that this was published in 2021, so not available for Fleming Fund use for the majority of phase 1. World Health Organisation. (2021). WHO integrated global surveillance on ESBL-producing E. coli using a ‘One Health’ approach. Geneva: WHO.

World Health Organisation. (2022). Strengthening WHO preparedness for and response to health emergencies: Strengthening collaboration on One Health. World Health Organisation.

World Health Organisation. (2022). Tripartite Zoonoses Guide: Operational tools and approaches for zoonotic diseases. Retrieved from World Health Organisation: https://www.who.int/initiatives/tripartite-zoonosis-guide

UK Health Security Agency. (2015). Human Animal Infections and Risk Surveillance group (HAIRS). Retrieved from Gov.uk: https://www.gov.uk/government/collections/human-animal-infections-and-risk-surveillance-group-hairs#:~:text=Contents&text=The%20Human%20Animal%20Infections%20and%20Risk%20Surveillance%20(%20HAIRS%20)%20group%20is,threat%20to%20UK%20public%20health

Purdah is a period of pre-election sensitivity when Government departments and councils will normally observe discretion about making new announcements or decisions that could influence voters. https://commonslibrary.parliament.uk/research-briefings/sn05262/

Scoping and positioning work took longer than the six months initially expected, with delays in start-up of grants ranging from 1 to 20 months and averaging 6.25 months.

World Bank. (2021, June 3). The World Bank. Retrieved from Safeguarding Animal, Human and Ecosystem Health: One Health at the World Bank. Available at: https://www.worldbank.org/en/topic/agriculture/brief/safeguarding-animal-human-and-ecosystem-health-one-health-at-the-world-bank

ICAI. (2015). DFID’s approach to delivering impact. Available at: https://icai.independent.gov.uk/wp-content/uploads/ICAI-report-DFIDs-approach-to-Delivering-Impact.pdf

Vähämäki, J. & C. Verger (2019) Learning from Results-Based Management evaluations and reviews. OECD Development Co-Operation Working Paper 53. OECD. Paris. March 2019. https://www.oecd-ilibrary.org/docserver/3fda0081-en.pdf?expires=1586440136&id=id&accname=guest&checksum=EDDD4196D5257F2D6DD73BB8157AB7BE

DHSC Terms of Reference: Management Agent for The Fleming Fund – para 2.4 and 2.5, which lists eight indicative focus areas for the grants portfolio, only one of which mentions ‘Policy and advocacy work with national governments, using AMR data and analysis collected to make the case for evidence based public health interventions’.

See FCDO Programme Operating Framework, section 5.3: https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/1115116/Programme-Operating-Framework-Nov22.odt